INTER-AMERICAN AGENCY FOR COOPERATION AND DEVELOPMENT

(IACD)

XXII MEETING OF THE MANAGEMENT BOARD	OEA/Ser.W/XXI.2.18

March 19 and 20, 2009	AICD/JD/doc.66/09

Gabriela Mistral Room	26 March 2009

Washington, D.C.	Original:  Spanish

DECISIONS OF THE MANAGEMENT BOARD

(Adopted at the meeting of March 19 and 20, 2009)

The Twenty-second Meeting of the Management Board of the Inter-American Agency for Cooperation and Development (IACD) was held at OAS headquarters on March 19 and 20, 2009 and chaired by Mr. Máximo Romero Jiménez, Director General of Technical and Scientific Cooperation of the Secretariat of Foreign Affairs of Mexico and Chair of the IACD Management Board.

Participants:

The following member states on the Management Board took part in the meeting:

Chair of the Management Board:

-	Mr. Máximo Romero Jiménez, Director General of the General Directorate for Scientific and Technical Cooperation of the Secretariat for Foreign Affairs of Mexico

Members of the Management Board:

- Donna Michelle Forde, Alternate Representative of Barbados

- Marcia Maro Da Silva, Alternate Representative of Brasil

- Agustín Vásquez, Alternate Representative of El Salvador

- Margarita Riva-Geoghegan, Alternate Representative of the United States

- Patricia D.M. Clarke , Permanent Representative of Grenada

- Elsa Liliana Samoya de Gonzalez, Alternate Representative of Guatemala

- Ann Scott, Acting Representative of Jamaica

- Juan Gabriel Morales, Alternate Representative of Mexico

Also present were: the Director General of the IACD, Ambassador Alfonso Quiñónez, and representatives of the delegations of Argentina, Belize, Canada, Colombia, Costa Rica, Dominican Republic, Ecuador, Nicaragua, Panama, and Peru.

- Consideration and Adoption of the Proposed Programming of FEMCIDI 2008 Partnership for Development Activities

Decision No. 1:	To adopt the Programming of FEMCIDI 2008 Partnership for Development Activities, contained in document AICD/JD/doc. 113/09 add. 1. After taking into consideration the comments of the delegations, the Secretariat subsequently circulated a revised version of said document (AICD/JD/doc. 113/09 add. 2).

In order to complete the financing for Programming FEMCIDI 2008 Partnership for Development Activities, and in particular the Sustainable Development Sector Account, to authorize the transfer of US$54,636.34 from the Integral Development Account to the Sustainable Development Account.

- Consideration of an extension of the deadline for executing projects included in the FEMCIDI 2007 cycle

Decision No. 2:	To authorize a one-month extension of the deadline for executing all FEMCIDI 2007 projects, until April 30, 2009, in response to a request of the Executive Secretariat for Integral Development and due to consultations required for administrative adjustments, which delayed the start of the FEMCIDI 2007 cycle.

Decision No. 3:	In addition to the month authorized by Decision No. 2, and at the express request of the executing entities, to authorize extensions to the deadlines for executing the following projects:

- Mexico – Liaison, Communication, and Training for Schools Resources Center [Centro de Recursos de Enlace, Comunicación y Capacitación para las Escuelas – CRECE] (AE-299/07).  Extension through to June 30, 2009.

- Grenada – Export Competency Development Project (AE-020/07).  Extension through to June 30, 2009.

- Haiti - Tourism Public Attitudes and Awareness Project (AE-043/07).  Extension through to December 31, 2009.

- St Kitts and Nevis - Rural Agro/Eco/Tourism Project (ME-297/07). Extension through to December 31, 2009

- El Salvador – Development of the Competitive Advantages of Fruit Processing Micro, Small and Medium-sized Enterprises in El Salvador [Desarrollo de Ventajas Competitivas de las MIPYMES procesadoras de Frutas en El Salvador (AE-284/07)]. Extension through to May 31, 2009.

- Dominican Republic – Strengthening Disaster Response Capacity [Fortalecimiento de la Capacidad de Respuesta a los Desastres (AE-312/07).     Extension through to June 30, 2009.

- Panama – Strengthening of Panamanian Small Farmers for Insertion into International Markets [Fortalecimiento de los Pequeños Agricultores Panameños para su Inserción en los Mercados Internacionales (AE-309/07)]  Extension through to September 30, 2009

- Nicaragua – Citizen Participation in Management of the Office of the State Attorney for Human Rights [Participación de la Ciudadanía en la Gestión de la Procuraduría de Derechos Humanos (AE-304/07)].  Extension through to September 30, 2009.

- Barbados – “Flexible, continuing and professional education” (AE-271/07).  Extension through to December 31, 2009

Decision No. 4:

Ecuador - Program of Assistance to Small Hotels in the Andean Region [Programa de Asistencia a Pequeños Hoteles de la Región Andina (AE283/07)].  Extension through to May 31, 2009.

The Management Board decided that, since this is a continuation project, the appropriate thing to do would be for the executing entity to adjust its activities execution plan for 2009, so as to incorporate those pending from the previous cycle. This decision does not affect the origin of funds to finance those activities, i.e. the same financing sources will be maintained: FEMCIDI 2007 for the activities pending and FEMCIDI 2008 for the new cycle.

Decision No. 5	To remit the following projects to the respective CENPEs for them to examine the ongoing validity of the terms of reference established when each project was approved, the capacity of the executing entities, and the rescheduling of activities based on the extension granted by the Management Board.  This extension was subject to the recommendation of the CENPE and will take effect once it has been ratified by the Management Board following a consultation via e-mail with its members.

It was agreed that such consultations should be conducted within 30 days from the date of the meeting of the Management Board.

.

- Guyana – Building Capacity in the Education Sector in Guyana for Sustainable Human Development  (ME-244/07).  Extension subject to recommendation of the CENPE: through to December 31, 2009.

- Nicaragua – Strengthening the Capacity of Women to Play an Active Part in the Local and National Political Agenda [Fortalecimiento de las Capacidades de las Mujeres para su Efectiva Participación en la Agenda Política Local y Nacional (AE-302/07)].  Extension subject to recommendation of the CENPE: through to December 31, 2009.

- Nicaragua – Promoting the Technological Development of Micro, Small and Medium-sized Enterprises through local use of information and communication technologies – ICTs [Fomento al Desarrollo Tecnológico de la MIPYMES a través del uso de la tecnología de la información y la comunicación en los Territorios (AE-303/07)]   Extension subject to recommendation of the CENPE: through to December 31, 2009.

Decision No. 6:	Colombia – “Improving the Management and Certification of State Pre-School, Basic, and Secondary Education Establishments” [Mejoramiento de gestión y certificación de establecimientos públicos de educación preescolar, basica y media (AE-280/07)].  To allow Colombia time until April 30 to carry out consultations and inform the Management Board regarding Chile’s participation in the project.

To authorize an extension until December 31, 2009, subject to the project’s compliance with the requirements of a multilateral project and to the CENPE’s reassessment, which will be based on additional information provided by the Government of Colombia to the Management Board, and to the ongoing validity of the terms of reference, including the viability of the rescheduling of activities. This extension will take effect after it has been ratified by the Management Board following electronic consultation of its members.

Decision No. 7: 	Antigua and Barbuda - Supporting Caribbean Enterprises (SOURCE) (AE-263/07).  Given that, due to an oversight, not all relevant data were supplied on time, the project must be sent for reconsideration by the corresponding CENPE.

Once it receives the CENPE’s recommendation, the Management Board will consider including the project in the Programming of FEMCIDI 2008 Partnership for Development Activities.

Decision No. 8: 	Colombia – Promotion of Ownership of the ScienTI Network in Latin America and the Caribbean [Fomento de la Apropiación de la Red ScienTI en América Latina y el Caribe (AE-232/07)].    To allow time, until April 30, 2009, for the executing agency to complete the activities scheduled for the FEMCIDI 2007 cycle and to present progress reports for presentation to the corresponding CENPE, for a review of its recommendation to continue the project.

Once it receives the CENPE’s recommendation, the Management Board will consider including the project in the Programming of FEMCIDI 2008 Partnership for Development Activities.

In addition to the decisions taken regarding the Programming of FEMCIDI 2008 Partnership for Development Activities and postponement of the deadlines for FEMCIDI 2008 projects, participants in the Meeting analyzed the proposed Work Plan outline ((AICD/JD/doc.109 rev. 1 cor.1).  Each of the main themes in that outline was examined and it was then agreed that the document could serve as a thematic guide for the Management Board’s next Work Plan.  It was also agreed that it would be useful to circulate a questionnaire among members of the Management Board in order to elicit from them specific proposals on how best to address each of the main subject areas.

It was also decided that the Chair of the Management Board would present a report to the Fourteenth Regular Meeting of CIDI, scheduled for May 5, on deliberations regarding the main subject areas agreed upon in the proposed Work Plan Outline, pursuant to resolution AG/RES. 2390 (XXXVIII-O/08), “Strengthening Partnership for Development: Policy Dialogue, Technical Cooperation, Structure, and Mechanisms.”

Máximo Romero Jiménez	Alfonso Quiñónez

Chair of the Management Board:	Director General of the IACD

# Text boxes

CEPCD01874E06