INTER-AMERICAN AGENCY FOR COOPERATION AND DEVELOPMENT

(IACD)

OEA/Ser.W/XX.2.18

AICD/JD/doc.116/09

18 September 2009

Original: Spanish

DRAFT WORK PLAN OF THE MANAGEMENT BOARD OF THE

INTER-AMERICAN AGENCY FOR COOPERATION AND DEVELOPMENT 
2009 - 2010

(Presented by the Chair)

DRAFT WORK PLAN OF THE MANAGEMENT BOARD OF THE INTER-AMERICAN AGENCY FOR COOPERATION AND DEVELOPMENT 
2009 - 2010

(Presented by the Chair)

This plan of action describes activities to follow up on the “Proposed Structure for the Work Plan” document (AICD/JD/doc.109/09 rev 1 corr. 1) presented by the Chair (Mexico) and approved by the Management Board in March 2009. The idea is also to put together a joint proposal with the members of the IACD Management Board, to be adopted at the next meeting of the MB on September 24.

| Actions | Months | Outcomes | Body/person responsible |
| --- | --- | --- | --- |
|  | S | O | N | D | J | F | M | A | M | J | J |  |  |
| THEMATIC AREA 1: STRENGTHENING DIALOGUE AND LINKAGE AND COORDINATION MECHANISMS |
| 1.1. Institutionalize the CIDI Meeting of High-Level Cooperation Authorities |  |  |  |  |  |  |  |  |  |  |  | CIDI Meeting of High-Level Cooperation Authorities institutionalized | Chair of the Management Board |
| 1.1.1. Consultations with the Management Board regarding this proposal to be presented at the Preparatory Meeting for the Specialized CIDI Meeting of High-Level Cooperation Authorities and regarding the role that the Board could play as the political-technical body for following up on agreements reached by the cooperation authorities |  |  |  |  |  |  |  |  |  |  |  | Proposal to institutionalize the Meeting of High-Level Cooperation Authorities (this would move up and the other one would move down) | Chair of the Management Board |
| 1.1.2. Present the proposal to institutionalize the Specialized CIDI Meeting of High-Level Cooperation Authorities to the member states |  |  |  |  |  |  |  |  |  |  |  | Proposal drafted and agreed upon by consensus by the members of the Management Board for presentation to the Meeting of High-Level Authorities in Bogotá | In reality, it is not up to the Management Board to take a final decision regarding institutionalization of the Meeting |
| 1.1.3. If the proposal is accepted, present the recommendations of the Board to the Preparatory Meeting for the Specialized CIDI Meeting of September 24 |  |  |  |  |  |  |  |  |  |  |  | Presentation of the recommendations | Chair of the Management Board |
| 1.2 Implement actions designed to revitalize the role of the Management Board so that it gradually becomes more effective in the performance of the functions assigned to it |  |  |  |  |  |  |  |  |  |  |  | Proposal to reactivate the MB of the IACD | Management Board (pending appointment at the meeting of the Management Board on September 24 of a body/person responsible) |
| 1.2.1 Name the person responsible for drafting an MB reactivation proposal from among the members of the Management Board at the meeting of September 24 |  |  |  |  |  |  |  |  |  |  |  | Member of the Management Board responsible for drafting this proposal | Management Board |
| 1.2.2 Evaluate options for involving cooperation authorities in the work of the Management Board |  |  |  |  |  |  |  |  |  |  |  | Cooperation authorities engaged in the work of the Management Board and of the IACD. If necessary, amendment of the Rules of Procedure of the MB to guarantee their participation | Member States – Management Board |
| 1.2.2 Identify priority areas for reactivation |  |  |  |  |  |  |  |  |  |  |  | A report on MB functions that can be boosted at this stage in the revitalization process | Management Board (pending appointment at the Meeting of the MB on September 24 of a body/person responsible) |
| 1.2.3 Draft the document containing the proposals for reactivating the MB of the IACD |  |  |  |  |  |  |  |  |  |  |  | Proposed amendment of the Statute presented to CEPCIDI by the IACD | Management Board |
| 1.3 Define a mechanism specifically to coordinate ministerial and inter-American cooperation processes |  |  |  |  |  |  |  |  |  |  |  | Model mechanism for enhanced coordination between ministerial and inter-American cooperation processes | Management Board - SEDI |
| 1.3.1 Craft a proposal for coordinating ministerial and MB processes that includes assistance with preparation of ministerial meetings, reports on cooperation matters considered at ministerial meetings, and the subsequent support lent by the IACD. |  |  |  |  |  |  |  |  |  |  |  | Document with the proposed report | SEDI |
| 1.3.2 Assist, by way of pilot projects, with implementation of the coordination proposal at the Social Development and Culture ministerials scheduled for 2010 |  |  |  |  |  |  |  |  |  |  |  | Report on the assistance process | Management Board |
| 1.3.3 Present a document to CEPCIDI containing the recommendations for the coordination process. |  |  |  |  |  |  |  |  |  |  |  | Document with recommendations | Management Board |
| THEMATIC AREA 2: DIVERSIFY THE FORMS OF HEMISPHERIC COOPERATION |
| 2.1. Draft a proposal for strengthening FEMCIDI |  |  |  |  |  |  |  |  |  |  |  | Document with the proposal for strengthening FEMCIDI, for presentation to CEPCIDI | Management Board SEDI |
| 2.1.1. Drafting of a report on the 2009 FEMCIDI Programming Cycle, to be presented at the meeting of the Management Board on September 24 |  |  |  |  |  |  |  |  |  |  |  | Report on the 2009 FEMCIDI programming cycle | SEDI |
| 2.1.2 Drafting of proposed recommendations for strengthening FEMCIDI, to include inputs from the SEDI Report and comments of the Management Board, so that they can be adopted as commitments at the meeting of High-Level Authorities in Bogotá |  |  |  |  |  |  |  |  |  |  |  | Document with the proposed recommendations | Chair of the Management Board |
| 2.1.3 Presentation of the final report with recommendations to CEPCIDI |  |  |  |  |  |  |  |  |  |  |  | Final Report | Chair of the Management Board |
| 2.2. Generate precise information regarding the units and sources of cooperation within the OAS |  |  |  |  |  |  |  |  |  |  |  | Report on the units and sources of cooperation at the OAS | SEDI |
| 2.3. Draft proposed recommendations to boost innovative and viable cooperation mechanisms in the OAS framework (triangular and South-South cooperation, and so on). |  |  |  |  |  |  |  |  |  |  |  | Proposed recommendations | Management Board (pending appointment at the Meeting of the MB on September 24 of a body/person responsible) |
| 2.3.1 Conduct an analysis of the initiatives under way with these cooperation mechanisms in the Hemisphere |  |  |  |  |  |  |  |  |  |  |  | Report containing the analysis | Management Board (pending appointment at the Meeting of the MB on September 24 of a body/person responsible) |
| 2.3.2 Prepare a draft pilot hemispheric work program to promote new forms of cooperation |  |  |  |  |  |  |  |  |  |  |  | Proposed pilot scheme | Management Board (pending appointment at the Meeting of the MB on September 24 of a body/person responsible) |
| THEMATIC AREA 3: FUNDRAISING PLAN |
| 3.1. Prepare a plan for raising outside funding to strengthen hemispheric cooperation |  |  |  |  |  |  |  |  |  |  |  | Proposed plan for raising outside funding to strengthen hemispheric cooperation | SEDI – Management Board |
| 3.1.1. Identification of priority options and fresh opportunities for cooperation between the OAS and other agencies and sources of cooperation |  |  |  |  |  |  |  |  |  |  |  | Report, based on the deliberations of the meeting of High-Level Authorities in Bogotá, indicating opportunities for linkage and complementarity between cooperation within the OAS and from other sources and agencies | Chair of the Management Board - SEDI |
| 3.2 Establishment of fundraising panels within and outside the OAS, on the basis of prior reports |  |  |  |  |  |  |  |  |  |  |  | Document with the proposal on the panels and a schedule of activities | Management Board (pending appointment at the Meeting of the Management Board on September 24 of a body/person responsible) |
| 3.3 Drafting of a report on the conclusions of these panels, for presentation to the Management Board and CEPCIDI |  |  |  |  |  |  |  |  |  |  |  | Final report on fundraising opportunities to strengthen inter-American cooperation | Chair of the Management Board and a member who volunteers for this task |
| THEMATIC AREA 4: PROCEDURES FOR REPORTING, RECORDING, AND MEASURING THE IMPACT OF COOPERATION |
| 4.1. Support the consolidation of COOPERANET, as mechanisms for information and coordination on hemispheric cooperation |  |  |  |  |  |  |  |  |  |  |  | A consolidated COOPERANET as a mechanism for information on and coordination of hemispheric cooperation | SEDI |
| 4.1.1. Draft a document on the conclusions of the Specialized CIDI Meeting of High-Level Cooperation Authorities regarding COOPERANET, which provides guidance on new developments and changes in this mechanism for cooperation and dialogue among the Hemisphere’s cooperation authorities |  |  |  |  |  |  |  |  |  |  |  | Report containing conclusions on the presentation of COOPERANET to the states | SEDI |
| 4.1.2. Establish a proposal on recommendations for strengthening COOPERANET and implement them |  |  |  |  |  |  |  |  |  |  |  | Document with the proposal for strengthening COOPERANET | Management Board (pending appointment at the Meeting of the Management Board on September 24 of a body/person responsible) |
| 4.2. Exchange and transfer of technology on national information systems on international cooperation |  |  |  |  |  |  |  |  |  |  |  | Proposal on the exchange and transfer technology on national information systems on international cooperation | Chair of the Management Board |
| 4.2.1. Design a work proposal for the exchange and transfer of technologies on national information systems on international cooperation at the hemispheric level, based on the needs of the less developed countries |  |  |  |  |  |  |  |  |  |  |  | Document with the work proposal for the exchange of national information systems | Chair of the Management Board |
| 4.2.2 Identify options for implementation of the proposal by the IACD and for launching of the pilot project |  |  |  |  |  |  |  |  |  |  |  | Document identifying options for implementation of the pilot project | Chair of the Management Board - IACD |
| THEMATIC AREA 5: REVIEW AND UPDATING OF THE CURRENT REGULATORY FRAMEWORK |
| 5.1 Draft a document containing reform proposals based on an analysis of existing rules and regulations and on the work of the Management Board/ |  |  |  |  |  |  |  |  |  |  |  | Document with the proposed reform | SEDI |
| 5.2. On the basis of this analysis, present recommendations to CEPCIDI on the strengthening of technical cooperation sufficiently in advance for them to be considered by the Working Group to Strengthen CIDI 1/ |  |  |  |  |  |  |  |  |  |  |  | Recommendations to CEPCIDI | Management Board |
| 5.3. Submit contributions-inputs on the draft resolution presented on the strengthening of CIDI and its bodies in CEPCIDI or in the Working Group |  |  |  |  |  |  |  |  |  |  |  | Document with inputs on the draft resolution | Chair of the Management Board - IACD |
| 5.4. Present recommendations to CIDI on the preparation of the next Strategic Plan for Integral Development, based on inputs from the Specialized CIDI Meeting of High-Level Cooperation Authorities and from the Management Board |  |  |  |  |  |  |  |  |  |  |  | Document with recommendations | Chair of the Management Board |
| REPORTS OF THE MANAGEMENT BOARD |  |  |  |  |  |  |  |  |  |  |  | Report of the Management Board to CIDI and report of the current Chair at the end of his term | Chair of the Management Board |

# Footnotes

.	Resolution AG/RES. 2469 (XIII-O/09), “Strengthening Partnership for Development:  Policy Dialogue, Technical Cooperation, Structure, and Mechanisms,” establishes that the CEPCIDI Working Group to Strengthen CIDI is to present its recommendations by December 31, 2009.  In view of this deadline, the proposal would be to revise the working timetable in consultation with the CEPCIDI Chair and the Working Group, once the former has been elected by CEPCIDI.

# Text boxes

CEPCD02033E01