PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CAAP/GT/RVPP-110/11

8 August 2011

COMMITTEE ON ADMINISTRATIVE	Original: English

AND BUDGETARY AFFAIRS

Working Group on the Review

of OAS Programs

_________________________________________________________________________________

CHAIR`S NOTE ON METHODOLOGY AND WORKPLAN FOR THE CAAP WORKING GROUP ON REVIEW OF OAS PROGRAMS

(August 2011 to May 2012)

- Overview of the activities of the Working Group on the Review of the OAS programs

The review of OAS programs now enters its third year of activities. It was preceded by a year of debates at the CAAP on the methodology to arrive the work plan for the Working Group, approved by the CAAP on March 27, 2009 (see CP/CAAP-2988/09 rev.3). This work plan defined four Work Packages:

- Determination of priorities and review of existing OAS mandates

- Review of General Assembly Mandates

- Reengineering options for the OAS

- Austerity measures

Substantial progress has been made on all four Work Packages over the 2009-2010 and 2010-2011 calendar cycles. The May 24, 2011 report of the Chair of the CAAP to the Permanent Council, of which the relevant extract is presented in Annex 1, gives us an overview of the accomplishment of the 2010-2011 cycle.

The Chair would like to review these accomplishments for each Work Package and point out some of the challenges remaining.

- On Work Package 1, Determination of priorities and review of existing OAS mandates, the Secretariat under the guidance of the WG has produced a compendium of all current mandates of the Organization, with a structure of information at three levels: pillar, sub pillar and group of mandates. The WG has also produced a survey of mandate priorities by Members based on the 35 sub pillars of compendium. This covers the two first activities originally planned, leaving the WG to address this year the third activity on the original work plan, prioritization decision. This will be a major undertaking. Although there is a general agreement that some priority must be set in determining which of the 1800 plus current mandates the OAS should be undertaken under the limited funds available and which should be either postpones or deleted, as well as which ones should be undertaken under the regular budget and which ones should be funded by specific funds there is no consensus on how we should reach such a decision. Some methodological discussions on priority setting and the provision of decision making tolls and information for decision making will be needed before the Members can actually come to decisions on priorities. The Chair will propose some approaches on this matter in future meetings of the WG, should the delegates wish to pursue this activity.

- On Work Package 2, Review of General Assembly Mandates, the WG has made substantial progress through Resolution CP/RES.93 (1797/11) on the costing process for the resolutions adopted by the General Assembly. This covers both activity 1 and 2 of the original Work Package. The issue of funding choices for resolutions is still pending, but would be covered under the priority setting discussion, as well as under reengineering topics. The Chair would suggest that this Work Package be considered completed in planning of activities for the 2011-12 cycle, leaving the option to define future issues under this topic should the need arise.

- On Work Package 3, Reengineering, the WG has made progress on both original activities. Most of the initial topics where discussed and several new ones where added to the list of desired reengineering topics. Chairman`s note CAAP/GT/RVPP-69/10 of November 17, 2010 provides a list of the topics put forward last year (see Annex 2). The CAAP meeting of August 1, 2011 underlined that issues such as Human Resources Policy and Management, Funding sources for OAS programs and activities and management of specific funds, Property Management, Indirect Cost Recovery and the role of the Inspector General, as well as the implementation of the recommendations of the External Auditors, are topics close to the heart of the delegates. The Chair would argue that the low hanging fruits where picked in the previous years and that the task before us is more complex as the topics are more controversial. The Chair proposes that we do a preliminary round of discussions on the desired topics for reengineering, from which the Chair will put forward a list of priority topics out of which the WG will select a limited number (not more than 4-5) with the purpose of proposing a decision before the next General Assembly, either through a Resolution for the next GA or a directive/executive order by the Secretary General.

- On Work Package 4, Austerity measures, the Chair will commend the excellent work by the Secretariat in reporting in the Quarterly Resource Management reports the austerity measures undertaken. The Chair will note that, here again, most of the lower hanging fruits where picked and that future austerity measures risk showing declining marginal benefit. Two sectors are however open for further work: costing and measuring the austerity gains and extending the reporting to Secretariat areas beyond the SAAF.

- Calendar of activities for the Working Group

The number of meetings of the Working group will determine the amount of work we will be able to undertake. As a basis, the Chair proposes that the working group meet every two week, alternating with the CAAP meeting. As the time from now to the end of October will be essentially taken by the discussions on the 2012 Budget Resolution for the October 30 Special General Assembly, the WG will be able to start its work effectively only from November. Fortunately for us, the next GA will occur in July 2012, which will give us an extra month of work. From November 2011 to May 2012, we could therefore count on some 14 meetings of the working group. The Chair would propose that we add to these one or two meetings between now and October intertwined between Budget discussions, so that the WG may complete it 2011-2012 methodology discussion and agree on a firm work plan as to allow un to address substantive issues from the onset of our November meetings.

- Conclusion

The Chair would appreciate having the general views of the delegates on the issues raised in this note as to propose a draft work plan for discussion and approval at the WG meeting.

Annex 1

Extract of CP/CAAP-3116/11 may 24, 201 REPORT OF THE CHAIR OF THE

Committee on Administrative and Budgetary Affairs

ON THE ACTIVITIES OF THE COMMITTEE

(For the period from July 2010 through May 2011)

- WORKING GROUP ON THE Review OF OAS PROGRAMS

The Working Group began its work for the 2010-2011 term on November 2, 2010, chaired by Counselor Pierre Giroux, Alternate Representative of Canada.  During that meeting the Chair submitted its draft Work Plan and Calendar of Meetings, document CAAP/GT/RVPP-63/10, which was approved.

The Work Plan proposed a series of work packages to be implemented simultaneously for the purpose of providing a series of recommendations for the Permanent Council and General Assembly. The aim is to make the Organization financially sustainable in the long term, with better performance, in support of the priorities clearly defined by the member states. The work packages are as follows:

# Work Package 1: 	Determination of priorities. Definition, distinction, and review by the CAAP of existing OAS mandates.

- Work Package 2: 	Review of General Assembly resolutions.

# Work Package 3: 	Realignment options for the OAS.

# Work Package 4: 	Austerity measures.

  - Work Package 1:  Determination of priorities

The member states discussed and negotiated the priority-setting procedure and decided to launch it in December.  The results of this exercise have been received from 30 member states.

  - Work Package 2:  Review of OAS resolutions

The Working Group on the Review of OAS Programs and, subsequently, the CAAP considered and adopted the draft resolution “Update of Resolution CP/RES. 965 (1733/09) on the costing process for resolutions to be referred to the General Assembly for consideration,” which was later adopted by the Permanent Council as resolution CP/RES. 983 (1797/11).

The purpose of this process is to facilitate the work flow in clear and accurate identification of costs and the inclusion of complementary technical information.  Thus, this process will give the Committees a general idea of the costs that they will incur from the resolutions.

Implementation of the process began with all the draft resolutions to be referred to the forty-first regular session of the General Assembly

  - Work package 3:  Realignment options for the OAS

With respect to Work Package 3, the Working Group continued to discuss potential options for realignment with OAS programs and activities, with a view to the potential restructuring of some of the activities to improve performance and limit costs.

The Working Group has considered the following matters to date:

- The costing process for resolutions.

- Internal management: proposals, options, and discussions about conference and translation services.

- Report to define the priorities for action by the member states.

- Indirect cost recovery policy.

- Sources of financing for the activities of the Organization.

- Cash flow of the Organization.

- Reevaluation of the prompt payment discount policy.

- Revision of the scale of quota assessments.

- Comprehensive human resources management plan.

- Hiring mechanisms.

  - Work package 4:  Austerity measures

The purpose of the austerity measures is for the General Secretariat to continue implementing measures to increase the efficiency of the Organization’s work processes. In that connection, the General Secretariat presents a quarterly report to the CAAP on the efforts made to contain spending, improve processes, and encourage saving and prudent use of the resources allocated for its operations and those of its dependencies, as well as those appropriated for fulfillment of its assigned responsibilities.

ANNEX 2

LIST OF POSSIBLE REENGINEERING THEMES FROM CAAP/GT/RVPP-69/10 CHAIR`S NOTE OF NOVEMBER 17, 2010

From Working Group activities in 2009-10:

- Management of the Organization’s meetings (January 26, 2010)

- Reengineering and streamlining of Human Resource Management (February 16, 2010)

- Offices of the General Secretariat in the member states (February 23, 2010)

- Scholarship program (February 23 and March 9, 2010)

- Financing of the budget of the Regular Fund (March 16, 2010)

- Subsidies of the Regular Fund (March 23, 2010)

- Review of the budget cycle (March 23, 2010)

- Funding of the inter-American human rights system (March 19, 2010)

From the Resolution AG/RES. 1 (XL-E/10) – 2011 Budget resolution:

- Report, strategies and plan presentation

- Annual Budget cycle

- Implementation of the recommendations from the Board of Auditors

- End of fiscal year report on the use Regular Budget financial resources

- Use of Quarterly administrative and financial management reports

- Indirect cost recovery policy

- Reporting on fundraising efforts

- Fundraising strategy

- Prompt payment discount policy

- Revision of the assessment percentage scale

- Report on results achieved

- Implementation of an integrated planning process

- Program evaluation

- Results based budgeting

- Alignment process

- Comprehensive human resource management plan

- Human resource management policies

- Code of value and ethics

- Trust appointment policy

- Review of the General Standards

- Streamlining and improvements in management, oversight and internal control of the Offices of the General Secretariat

- Coordination mechanism with the National Offices

- Operational planning and results reporting for National Offices

- Improvement of Scholarship and Training programs

- New funding mechanism for Scholarship

- Reporting on travel policy

- Work plan process for the Inspector General

- Improvement of Conference and meeting management

- Improvement of the Budget preparation process

- Adoption and use of auditing reports

- Multi-year budget planning process

- Implementation of International Public Sector Accounting Standards (IPSAS)

From other suggestions by Members:

- Management practices of specific funds

- Review of Inter American Defence Board funding

- Streamlining OAS activities and mandates with other multilateral organisation’s activities and mandates to reduce duplication

- Status of the Inspector General

# Text boxes

CP26850E01