PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CAJP/GT/DHPM-100/13 rev. 3

31 October 2013

COMMITTEE ON JURIDICAL AND POLITICAL AFFAIRS	Original: Spanish

# Working Group on Protection

of the Human Rights of Older Persons

WORK PLAN OF THE WORKING GROUP ON PROTECTION

OF THE HUMAN RIGHTS OF OLDER PERSONS

(2013-2014)

(Approved by the Working Group at the meeting held on September 5, 2013; 
schedule amended at the Working Group meeting held on September 23 
and at the CAJP meeting held on October 11)

- Introduction

Through resolutions AG/RES. 2455 (XXXIX-O/09) and AG/RES. 2562 (XL-O/10), the General Assembly of the Organization of American States (OAS) urged the Permanent Council to convene a "special meeting on human rights and older persons, with the participation of national representatives and experts from the academic sector and civil society, as well as from international organizations, for the purpose of sharing information and best practices and examining the feasibility of preparing an inter-American convention on the rights of older persons." That meeting was held on October 28, 2010, with the participation of the Inter-American Commission on Human Rights (IACHR), the Pan American Health Organization (PAHO), the United Nations Population Fund (UNFPA), civil society representatives and specialists of the OAS General Secretariat.

In June 2011, through resolution AG/RES. 2654 (XLI-O/11), the General Assembly requested that the Permanent Council establish a working group, which, after preparing a report analyzing "the situation of older persons in the Hemisphere and the effectiveness of binding universal and regional human rights instruments with regard to protection of the rights of older persons," would prepare “a Draft Inter-American Convention for the protection and promotion of the rights of older persons.”

In 2012, the General Assembly, through resolution AG/RES. 2726 (XLII-O/12), asked the Permanent Council to extend the mandate of the Working Group to enable it to conduct the process of formal negotiation of the Draft Convention and in June 2013, through resolution AG/RES. 2792 (XLIII-O/13), requested it to extend the mandate of the Working Group to enable it to conclude the process of formal negotiation of the Draft Inter-American Convention on Protection of the Rights of Older Persons.

- Officers

The Working Group for the period under review was installed by the Committee on Juridical and Political Affairs on August 28, 2013. Pursuant to Article 28 of the Rules of Procedure of the Permanent Council, on that same day Ms. Ana Pastorino, Alternate Representative of Argentina to the OAS, was elected Chair. On September 5, 2013, the Working Group elected as its vice chairs Mr. Ivan Chanis Barahona, Alternate Representative of Panama to the OAS, and Ms. Wendy Jeannette Acevedo Castillo, Alternate Representative of El Salvador to the OAS.

- Mandate

On July 10, 2013, the Permanent Council assigned to the CAJP the task of monitoring and implementing resolution AG/RES. 2792 (XLIII-O/13), “Draft Inter-American Convention on Protecting the Human Rights of Older Persons.”/ According to the mandate contained in that resolution, the Group must conclude “the process of formal negotiation of the Draft Inter-American Convention on the human rights of older persons, preferably during the second half of 2013,” and seek “to present it to the General Assembly at a special session convened for that purpose.”

- Participation of Civil Society

The Working Group will promote participation by civil society organizations entered in the OAS register and which have special expertise in the subject area, in keeping with the requirements stipulated in the “Guidelines for the Participation of Civil Society Organizations in OAS Activities,” adopted by the Permanent Council through resolution CP/RES. 759 (1217/99).

- Activities of the Working Group

To comply with the mandate contained in resolution AG/RES. 2792 (XLIII-O/13), the Working Group will hold its meetings as per the attached schedule. The Group's activities will focus on formal negotiation of the Draft Inter-American Convention on protecting the human rights of older persons, based on document CAJP/GT/DHPM-37/12 add. 17 and in accordance with the provisions of the methodology contained in document CAJP/GT/DHPM-99/13.

This Work Plan and the tentative calendar will serve as a general framework for the Group's activities in 2013-2014. They may be amended as required by advances in the tasks entrusted to the Group, in order to ensure optimum results.

I would like to take this opportunity to say that suggestions by the delegations regarding this Draft Work Plan are very welcome and that I thank them for their support of the Working Group’s effort to carry out the tasks assigned to it.

# Ana Pastorino

# Chair of the Working Group

# On Protection of the Human Rights of Older Persons,

# Alternate Representative of the Argentine Mission to the OAS

APPENDIX I

| TENTATIVE CALENDAR OF MEETINGS FOR 2013/ |
| --- |
| September – November 2013 |
| September 5, 2013 2:30 p.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Election of the Vice Chair Presentation and approval of negotiation procedures Presentation and approval of the Draft Work Plan Start of formal negotiation of the Draft Inter-American Convention on the human rights of older persons, topics to be discussed: General provisions of the Draft Convention – Articles 36 to 45 Preamble |
| September 23, 2013 10:00 a.m. – 1:00 p.m. Dr. José Gustavo Guerrero Room | Amendment of the schedule of meetings of the Working Group. Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, topics to be discussed: Follow-up mechanism Other articles that delegations may deem relevant |
| October 8, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, topics to be discussed: Follow-up mechanism General provisions of the Draft Convention – Articles 39 to 45 Other articles that delegations may deem relevant |
| November 8, 2013 10:00 a.m. – 1:00 p.m. Simón Bolívar Room (to be confirmed) | Presentation of the study done by the IACHR and dialogue with the member states |
| November 25 and 26, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, topics to be discussed: Prior informed consent Right to independence and autonomy Universal design and physical accessibility, and Responsibility of the state and engagement of family under domestic laws Article 5 New article (after Article 10) Article 11 Other articles that delegations may deem relevant |
| December 5, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, topics to be discussed: Article 12 Article14 Article 18 New article 19 – Right to Culture Article 19 – Right to property Article 20 New article – right to a healthy environment Consideration of paragraphs pending from previous meetings Other articles that delegations may deem relevant |
| December 16-18, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, topics to be discussed: Judicial guarantees plus articles 33, 34, and 35 New article – Conference of States Party Article 13 Article 15 Article 16 Article17 Article 21 Article 22 New article– Freedom of association and of assembly Article 24 Article 25 Article 31 Consideration of paragraphs pending from previous meetings Other articles that delegations may deem relevant |
| January 2014 | Presentation of the Draft Inter-American Convention approved by the Working Group to the CAJP |

# Footnotes

.	Distribution of mandates assigned by the General Assembly at its forty-third regular session and ongoing mandates from previous years (Approved by the Permanent Council on July 10, 2013), document (CP/doc.4924/13 rev. 1).

.	This calendar is subject to any changes that are needed in accordance with the progress made with the tasks assigned to the Group, in order to ensure optimum results.

# Text boxes

CP29223E04

CP29223E04

cp29223s01

CP31828E04