PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CAJP/GT/DHPM/INF.14/12

4 September 2012

COMMITTEE ON JURIDICAL AND POLITICAL AFFAIRS	Original: Spanish

# Working Group on Protecting

the Human Rights of Older Persons

_________________________________________________________________________________

DRAFT WORK PLAN OF THE WORKING GROUP ON PROTECTION
 OF THE HUMAN RIGHTS OF OLDER PERSONS

(2012-2013)

(Informal proposal presented by the delegation of Argentina, 
as agreed at the informal meeting held on August 29, 2012)

- Introduction

In April 2009, during the Fifth Summit of the Americas held in Port of Spain,/the Heads of State and Government of the Americas pledged to continue “working to incorporate issues of aging into public policy agendas” and to promote “in the regional framework and with support from PAHO and ECLAC, a review of the feasibility of preparing an inter-American convention on the rights of older persons.”

Through resolutions AG/RES. 2455 (XXXIX-O/09) and AG/RES. 2562 (XL-O/10), the General Assembly of the Organization of American States (OAS) urged the Permanent Council to convene a "special meeting on human rights and older persons, with the participation of national representatives and experts from the academic sector and civil society, as well as from international organizations, for the purpose of sharing information and best practices and examining the feasibility of preparing an inter-American convention on the rights of older persons." That meeting was held on October 28, 2010, with the participation of the Inter-American Commission on Human Rights (IACHR), the Pan American Health Organization (PAHO), the United Nations Population Fund (UNFPA), civil society representatives and specialists of the OAS General Secretariat.

Subsequently, through resolution AG/RES. 2654 (XLI-O/11), the General Assembly requested that the Permanent Council establish "a working group composed of national representatives and experts from the academic sector and civil society, as well as from international organizations and specialized agencies," which, after preparing a report analyzing "the situation of older persons in the Hemisphere and the effectiveness of binding universal and regional human rights instruments with regard to protection of the rights of older persons," would prepare a draft inter-American convention for the protection and promotion of the rights of older persons," to be presented to the Permanent Council before the end of first half 2012.

Recently, the General Assembly, in resolution AG/RES. 2726 (XLII-O/12), asked the Permanent Council to extend the mandate of the Working Group on Protection of the Human Rights of Older Persons to enable it to conduct, with technical support from the Department of Social Development and Employment, the process of formal negotiation of the draft inter-American convention on the human rights of older persons and seek to present it to the General Assembly of the Organization of American States (OAS) for adoption at its forty-third regular session.

- Officers:

The Working Group for the period under review was installed by the Committee on Juridical and Political Affairs on September XX, 2012. Pursuant to Article 28 of the Rules of Procedure of the Permanent Council, on that same day XXXXXXX, Alternate Representative of XXXXXX to the OAS, was elected Chair. The election of the Vice Chair was left pending for a subsequent meeting of the Working Group.

- Mandate

On August 22, 2012, the Permanent Council assigned to the CAJP the task of monitoring and implementing resolution AG/RES. 2726 (XLII-O/12), "Protecting the Human Rights of Older Persons"/. According to the mandate contained in that resolution, the Group is to conduct the process of "formal negotiation of the draft inter-American convention on the human rights of older persons and seek to present it to the General Assembly of the Organization of American States (OAS) for adoption at its forty-third regular session."

- Activities of the Working Group

To comply with the mandate contained in resolution AG/RES. 2726 (XLIIO/12), the Working Group will hold seven two-day meetings, as per the attached schedule. The Group's activities will focus on formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12,enriched with any agreements reached as a result of the proposals and comments included in the Compendium of Proposals, document CAJP/GT/DHPM-44/12 and applying the negotiation methodology approved by the Working Group and contained in document CAJP/GT/DHPM-xx/12.

This Work Plan will serve as a general framework for the Group's activities in 2012-2013. It may be amended by the Working Group itself or as required by advances in the tasks entrusted to the Group, in order to ensure optimum results.

APPENDIX I

| CALENDAR OF MEETINGS FOR 2012-2012/ |
| --- |
| October 2012– April 2013 |
| October 15 and 16, 2012 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Election of the Vice Chair. Presentation and approval of negotiation procedures. Presentation and approval of the Draft Work Plan. Start of formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12, |
| November 19 and 20, 2012 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12 |
| December 3 and 4, 2012 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12 |
| January 7 and 8, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12 |
| February 11 and 12, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12 |
| March 18 and 19, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12 Presentation of the draft resolution. |
| April 15 and 16, 2013 10:00 a.m. – 5:30 p.m. Dr. José Gustavo Guerrero Room | Formal negotiation of the Draft Inter-American Convention on the human rights of older persons, document CAJP/GT/DHPM-37/12 Negotiation of the draft resolution. |

# Footnotes

.	Reservation by Nicaragua.

.	Assignment of mandates issued by the General Assembly at its forty-second regular session approved by the Permanent Council on August 22, 2012), document (CP/doc.4793/12 rev. 1).

.	This calendar is subject to any changes the Group itself might approve or that are needed in accordance with the progress made with the tasks assigned to the Group, in order to ensure optimum results.

# Text boxes

cp29223s01

CP29223E04

CP29223E04

CP29223E04