THE INTER-AMERICAN COUNCIL	OEA/Ser.W/

FOR INTEGRAL DEVELOPMENT	CIDI/GT/FORCIDI/doc.67/13

8 January 2012

CIDI Working Group to Strengthen CIDI	Original: Spanish

IMPLEMENTATION STATUS OF THE SPECIAL MULTILATERAL FUND OF THE INTER-AMERICAN COUNCIL FOR INTEGRAL DEVELOPMENT (FEMCIDI) AREAS UNDER THE TRANSITION PROCESS

(Report as of January 8. 2013)

Below is a summary of the current status of each of the areas that are undergoing the transition period as approved by the countries in October 2010. Included are the steps of the process that have already been taken under the approved Programmatic Flow and the tentative dates on the steps to come (shadowed).

Education

| Phase I | Approved Key Themes on Education - Early Childhood Education - Secondary Education These themes will focus primarily, but not exclusively, on teacher training | March 10, 2011 |
| --- | --- | --- |
|  | Programmatic approach on education consolidated and approved | September 12, 2011 |
| Phase II | Project concept call for proposals | November 4, 2011 deadline |
| Phase III | Design Meeting (CIE) | December 13-14, 2011 |
| Phase IV | Programming Meeting | TBD |
| Phase V | Submission of the Project’s final versions | April 2, 2012 |
|  | Technical evaluation CENPES | July 9-19, 2012 |
|  | Approval of the Framework Program by Management Board | September 7, 2012 |
| Phase VI | Project Implementation | December 2012 – January 2013 |
| Phase VII | Results Delivered | After 1st year of implementation |

Science and Technology

| Phase I | Approved Key Themes on Science and Technology - Strengthening national quality infrastructures, with emphasis on metrology, to ensure competitiveness of micro, small and medium enterprises (MSMEs) - Promoting improvements in science and engineering education to foster innovation, entrepreneurship and competitiveness (including specialized networks, technology parks and business incubators for MSMEs) | July 19, 2011 |
| --- | --- | --- |
|  | Programmatic approach on science and technology consolidated and approved | September 12, 2011 |
| Phase II | Project concept call for proposals | December 2, 2011 |
| Phase III | Meeting for CENPES (online) | March 19-23, 2012 |
|  | Design Meeting (COMCYT) | June 18-22, 2012 |
| Phase IV | Programming meeting | TBD |
| Phase V | Submission of the Project’s final versions | November 15, 2012 |
|  | Technical evaluation (CENPES) | January 2013 (programmed) |
|  | Approval of the Framework Program by Management Board | February 2013 (tentative) |
| Phase VI | Project implementation | March 2013 (tentative) |
| Phase VII | Results delivered | After 1st year of implementation |

Culture

| Phase I | Approved Key Themes on Culture - Expanding economic growth and promoting development through culture - Fostering social inclusion through culture | September 12, 2011 |
| --- | --- | --- |
|  | Programmatic approach on culture consolidated and approved | December 12, 2011 |
| Phase II | Project concept call for proposals | February 29, 2012 |
| Phase III | Online Design Meeting (CIC) | November 2012 |
| Phase IV | Programming Meeting | TBD |
| Phase V | Submission of the Project’s final versions | March 8, 2013 (programmed) |
|  | Technical evaluation (CENPES) | April 2013 (tentative) |
|  | Approval of the Framework Program by the Management Board | TBD |
| Phase VI | Project implementation | July 2013 (tentative) |
| Phase VII | Results delivered | After 1st year of implementation |

Under the FEMCIDI 2011 Programming, projects have been initiated in the Tourism sector:

Tourism

| Phase I | Approved Key Themes on Tourism: - Tourism industry competitiveness, particularly among microenterprises and small and medium-sized companies, and support for human capacity building in the public and private spheres through training and the use of information and communication technologies (ICTs), - Promotion of the sustainable development of tourism, through the mitigation of negative environmental impacts, increased public awareness about the importance of preserving ecological balance in tourist areas, relations between tourism and other sectors of the economy, and support for ecotourism and sustainable tourism by means of dialogue between the public and private sectors. | September 30, 2011 |
| --- | --- | --- |
|  | Programmatic approach in tourism consolidated and approved | December 12, 2011 |
| Phase II | Profile presentation | September 7, 2012 |
| Phase III | Online Design Meeting (CITUR) | February 2013 (tentative) |
| Phase IV | Programming Meeting | TBD |
| Phase V | Presentation of Final Projects | April 2013 (tentative) |
|  | Technical Evaluation (CENPES) | May 2013 (tentative) |
|  | Approval of Framework by Management Board | TBD |
| Phase VI | Project Implementation | July 2013 (tentative) |
| Phase VII | Results delivered | After 1st year of implementation |

# Text boxes

CIDI03915E01

CIDI03915E01