PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CP/CAAP-3211/13 rev. 5

4 April 2014

COMMITTEE ON ADMINISTRATIVE	Original: Spanish

AND BUDGETARY AFFAIRS

_____________________________________________________________________________________

INTEGRATED REAL PROPERTY STRATEGY/

SUMMARY

During the CAAP meeting on April 1, 2014 the Chair of the Working on the Review of OAS Programs presented the document CAAP/GT/RVPP-232/14 which contained an updated version of the Integrated Real Property Strategy for consideration of the CAAP.  It was decided that the Chair of the CAAP will present the Strategy document to the Permanent Council, which includes the following suggestions and changes:

- Eliminates the sale of the Casa del Soldado

- Eliminates the conversion of the Ruben Dario conference room into offices

- Eliminates the private events options

- Lists the potential options for funding deferred maintenance.

- Includes Annex IX which provides additional quota assessment for deferred maintenance.

- Includes Annex X Administrative Memorandum 68. Rev. 2

CONTENTS

Page

Revised Integrated Real Property Strategy for 2013-2017	2

Annex I:	Background	9

Annex II:	Summary List of Documents sent to the CAAP	11

Annex III:	List of Deferred Maintenance Projects Completed in 2009 -2012	13

Annex IV:	List of Outstanding Deferred Maintenance and Estimated Cost	17

Annex V:	2013-2017 Plan for Implementation of deferred Maintenance Projects

(prioritized in order of urgency)	23

Annex VI 	Operating Costs of the Casa Del Soldado	27

Annex VII:	Operating Costs of the Inter-American Children’s Institute Building	29

Annex VIII:	Building Use and Restrictions 	33

Annex IX:	Special Quota Assessment Distribution	35

Annex X:	Administrative Memorandum 68 Rev. 2	37

INTEGRATED REAL PROPERTY STRATEGY FOR 2013-2017

Introduction

The Real Property of the Organization of American States (OAS) consists of the following buildings owned and/or operated by the OAS./

Table 1:  Real Property of the Organization of American States (OAS)

|  | Building | Year of Construction | Address | Construction Area (sq. ft) | Estimated Market Value * (in USD millions) | Regular Fund Budgetary Subprogram responsible for Operating and Maintenance Costs |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | OAS Main Building (MNB) | 1908 | 17th Street and Constitution Ave N.W., Washington D.C. 20006 | 109,609 | 145.3 | 113D (Building maintenance and Management) |
| 2 | OAS Art Museum of the Americas (Museum) | 1908 | 201 18th Street N.W. Washington D.C. 20006 | 9,606 |  | 113D |
| 3 | Casita | 1880 | 18th and C Streets N.W. Washington D.C. 20006 | 3,240 |  | 113D |
| 4 | OAS Administration Building (ADM) | 1948 | 19th Street and Constitution Ave N.W Washington D.C. 20006 | 63,799 | 60.2 | 113D |
| 5 | OAS General Secretariat Building (GSB) | 1978 | 1889 F Street N.W. Washington D.C. 20006 | 362,217 | 134.3 | 113D |
| 6 | OAS Secretary General’s Residence | 1990 | 2944 University Terrace NW Washington DC 20016 | 7,996 | 3.3 | 113D |
| 7 | OAS Secretary General’s Residence Annex | 1949 | 2908 University Terrace NW Washington DC 20016 | 1,440 | 1.1 | 113D |
| 8 | Casa del Soldado | 1905 | 2600 16th Street N.W Washington D.C. 20441 | 33,500 | 18.5 | 43A (Inter-American Defense Board) |
| 9 | Inter American Children’s Institute | 1908; 1940 | Av. 8 de Octubre 2904 – 2802, Montevideo, Uruguay | 21,560 | 1.0 | 33D (Inter-American Children’s Institute) |

* Construction value plus land value, as estimated in the 2008 Existing Conditions Report (ECR)

The operating and maintenance costs associated with these buildings are all funded by the Regular Fund of the Organization.  Buildings 1-7 in Table 1, above, are managed by the Department of General Services, and maintenance costs are funded by Subprogram 113D, Building Maintenance and Management, in Chapter 11, “Basic Infrastructure and Common Costs” of the 2014 Program Budget.  Building 8 is managed by the Inter American Defense Board (IADB), and maintenance costs are funded by the corresponding subprogram, 43A.  Building 9 is managed by the Inter American Children’s Institute (IIN), and maintenance costs are funded by the corresponding subprogram, 33D.   This Strategy assumes that buildings 8 and 9 will continue to be managed and funded by the IADB and the IIN, respectively.  Information on the operating costs of these buildings is provided in Annexes VI and VII.

In 2007, the General Secretariat contracted an expert study of the state of maintenance of the historic buildings of the Organization’s headquarters (buildings 1-4 in Table 1, above).  A separate structural study of the Casa Del Soldado, also a historic building, was conducted the same year.

In 2008, the General Secretariat submitted to the Permanent Council the results of the Existing Conditions Report (ECR) on buildings 1-4 and the Structural Study of the Casa del Soldado.  These studies found that there was a significant backlog of deferred maintenance needs in these historic buildings.  The studies estimated the cost of carrying out this deferred maintenance at approximately $38 million in buildings 1-4 and approximately $1.8 million in the Casa del Soldado. /

The Board of External Auditors of the Organization, in its report for the years 2010-2011, recommended that the Organization adopt an integrated real property strategy to address these deferred maintenance needs (see Annex I).    The General Secretariat, in response to these recommendations, prepared a series of documents in 2011 and 2012 setting forth options to address deferred maintenance.  However, no consensus emerged in the Permanent Council regarding any of these options.

Taking account of the above outcome of the deliberations in the Permanent Council during 2008-2012 on the Real Property Strategy, the General Secretariat has prepared the present Revised Integrated Real Property Strategy for 2013-2017.

Revised Real Property Strategy 2013 - 2017

This revised strategy includes the following components:

- An updated estimate of the cost of implementing deferred maintenance projects (see item 2 below);

- An estimate of the funds available from all existing sources for outstanding deferred maintenance (see item 3 below);

- An estimate of the cost to implement remaining deferred maintenance projects for which funds are not available in 2013-2017 (see item 4 below).

- A list of potential options for funding the outstanding deferred maintenance projects (see item 5 below).

- Deferred Maintenance Experience in 2008-2012

In the last five years, a number of deferred maintenance projects were completed, using the funds available from existing resources for this purpose. The funds available for deferred maintenance during 2008-2012 are shown in Table 2 below.

Table 2

Sources and Uses of Funds Devoted to OAS Building Maintenance*

| Sources of Funds | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
|  | US$ thousands |
| RF Subprogram 113D (Building Mgmt & Maintenance) | 5,021 | 5,090 | 5,090 | 5,090 | 5,201 |
| Rental Income Contribution | 1,346 | 1,330 | 1,493 | 1,409 | 1,516 |
| Hall of the Americas Contribution |  |  |  | 112 | 20 |
| Parking Fund Contribution |  |  | 84 | 19 |  |
| ICR Contribution |  |  |  |  | 37 |
| Special Reserve PC (831 Account) | 25 | 203 | 29 | 395 |
| Total Sources of Funds | 6,367 | 6,445 | 6,870 | 6,659 | 7,169 |
| Uses of Funds |  |  |  |  |  |
| Repayment of Demand Notes (F Street Renovation) | 2,050 | 2,207 | 2,040 | 1,882 | 2,141 |
| HQ Buildings Utilities | 1,306 | 1,377 | 1,458 | 1,366 | 1,205 |
| HQ Buildings Security | 782 | 821 | 938 | 762 | 855 |
| HQ Cleaning and General Services | 1,159 | 1,261 | 1,312 | 1,431 | 1,515 |
| a HQ Buildings General Maintenance | 1,065 | 718 | 737 | 1,022 | 581 |
| b HQ Deferred Maintenance (ECR) | 0 | 62 | 383 | 194 | 723 |
| Sub Total Maintenance (a+b) | 1,065 | 779 | 1,120 | 1,216 | 1,304 |
| Total Uses of Funds | 6,362 | 6,445 | 6,868 | 6,657 | 7,020 |
| Returned to Regular Fund | 5 | 0 | 2 | 2 | 149 |

*This table covers maintenance activities for buildings 1-7 in Table 1, above.

The actual total costs of the deferred maintenance projects completed in 2008-2012 are shown in the “Headquarters Deferred Maintenance”, line b in Table 2, above.  The full list of these projects is contained in Annex III.  In 2008, resources were not separately budgeted for deferred maintenance, since the Existing Conditions Report was presented to the CAAP in February of that year.

The projects implemented from 2009-2012 were projected in the Existing Conditions Report at a cost of $3,051,665. However, through the use of competitive bidding, application of new technologies, and selection of lower-cost alternative solutions, the GS/OAS was able to reduce the actual cost of implementation to $1,361,810.

Based on this experience in implementing these projects, the GS/OAS strategy assumes for the purpose of future implementation planning an average discount factor of 55% against the cost estimated in the ECR.

- Updated estimate of the cost of implementing deferred maintenance projects

The GS/OAS has prepared a newly updated estimate of the cost of implementing remaining outstanding deferred maintenance projects, attached at Annex IV.  The ECR estimated the total cost of these projects at $34.9 million in 2008 dollars.  Applying the 55% discount factor referenced above, the GS/OAS’s projection of the total cost for these projects is estimated at $15.7 million in current dollars.

- Estimate of the funds available from all existing sources for deferred maintenance

The estimate of funds available for deferred maintenance is updated based on the following assumptions:

  - The OAS will continue to occupy all existing buildings, including the Casa del Soldado.  The IADB will continue to fund maintenance of the Casa del Soldado.

  - Regular Fund building maintenance allocations in the Program Budget will remain stable for the next five years.

  - Space utilization will be optimized to free up 6,000 square feet of additional office space in the F Street building for rental.  The start date for new lease agreements is projected at July 1, 2014.

  - Hall of the Americas Fund overall income projected to remain stable in 2013-2017 at the level reached in 2012, ($380,000), and the Fund’s contribution to deferred maintenance is projected at $110,000 annually.

  - Parking fund income projected to remain stable in 2013-2017 at $626,000, and the Fund’s contribution to deferred maintenance is projected at $50,000 annually.

  - HQ Building Utilities costs will increase at 1% per annum, based on 3% average utilities rate increases and continued progress in adopting energy-saving technologies and policies.

  - Building Security, Cleaning and General Services will increase at 3% per annum.

Based on these assumptions, and if no additional sources of financing are identified, Table 3, below, shows the estimated funds available for deferred maintenance 2013 – 2017.

Table 3

Estimated Sources and Uses of Funds for OAS Building Maintenance*

| Sources of Funds | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- |
| RF Subprogram 113D (Building Mgmt. & Maintenance) | 5,363 | 5,363 | 5,363 | 5,363 | 5,363 |
| Rental Income Contribution | 1,478 | 1,815 | 1,900 | 1,930 | 1,955 |
| Hall of the Americas Contribution | 355 | 110 | 110 | 110 | 110 |
| Parking Fund Contribution | 174 | 50 | 50 | 50 | 50 |
| Special Reserve Approved by the PC (831 Account) | 184 | 49 | 40 | 40 | 40 |
| China Voluntary Contribution |  | 86 |  |  |  |
| Total Sources of Funds | 7,555 | 7,473 | 7,463 | 7,493 | 7,518 |
| Uses of Funds |  |  |  |  |  |
| Repayment of Demand Notes (F Street Renovation) | 2,123 | 2,167 | 2,207 | 2,247 | 2,282 |
| HQ Buildings Utilities | 1,277 | 1,229 | 1,242 | 1,254 | 1,266 |
| HQ Buildings Security | 875 | 925 | 953 | 981 | 1,011 |
| HQ Cleaning and General Services | 1,531 | 1,639 | 1,688 | 1,739 | 1,791 |
| a HQ Buildings General Maintenance | 1,152 | 850 | 839 | 865 | 893 |
| b HQ Deferred Maintenance (ECR) | 484 | 664 | 535 | 407 | 276 |
| Sub Total Maintenance (a+b) | 1,636 | 1,513 | 1,374 | 1,272 | 1,169 |
| Total Uses of Funds | 7,442 | 7,473 | 7,463 | 7,493 | 7,519 |
| Returned to Regular Fund | 113 | 0 | 0 | 0 | 0 |

*This table covers maintenance activities for buildings 1-7 in Table 1 above

Based on the above projections, a total of $2.4 million will be available for deferred maintenance projects in 2013-2017.  A detailed plan for use of these resources is provided in Annex V.

- Estimate of the cost to implement remaining deferred maintenance projects for which funds are not available in 2013-2017.

In Annex IV are listed all of the outstanding deferred maintenance projects not completed by December 31, 2012.  The revised projected cost completing these projects is $15,700,000.  The five-year plan set forth in Table 3, above, would provide $2.4 million during 2013-2017 for the top priority deferred maintenance projects, as determined by the GS/OAS expert engineering consultants.  Thus under this plan, at the end of 2017, deferred maintenance projects that continue to be outstanding will require an estimated additional $13.4 million to complete.

- Potential Options for Funding Outstanding Deferred Maintenance

Following is a list of options resulting from several discussions on how to fund outstanding deferred maintenance in the Organization’s historic buildings.  Table 4, below, includes an estimate of the potential proceeds from each option over a 5-year period to raise the remaining $13.4 million.

- Reallocate Funds from the Regular Fund.  CAAP may wish to allocate additional funds to deferred maintenance projects and diminish allocations to other projects.  Considering the current budget situation, this redistribution option is not realistic.

- Increase Rental of Parking.  Currently the C Street parking lot is rented for 10 events annually, and experience suggests an increase is not practical.

- Annual Rent Increase: The strategy already provides for maximum additional income from optimizing office space and leasing free space. The Secretariat estimates that the vacant space may be leased by July 1, 2014 and that the 3% annual increment will generate $7,200 and $36,000 in 5 years.

- Voluntary Contributions.  Estimated $100,000 voluntary contribution from Members and Observer States. Chile currently contributes $20,000 annually to the Building Improvements Maintenance Services (BIMS) account;

- Special Quota Assessment. An estimated $12,764,000 is needed as a special quota assessment from the Member States in order to raise the unfunded portion of the deferred maintenance projects.  The Member States may consider paying this as a one-time assessment or as a recurring assessment over a 5 year period.  Annex IX shows the assessment distribution to each Member State.

- Cooperation with Historic Preservation Institutions. Contacts to date with such institutions indicate cash contributions are unrealistic, but in-kind consultative services may be possible;

- Fellowship Cooperation.  Cooperation with Scholarship recipients might be expected to contribute in-kind consultative services, but not cash.

Table 4

POTENTIAL PROCEEDS FROM EACH OPTION OVER 5 YEAR PERIOD

| OPTION | Description | Potential Additional Annual Revenue | 5 year TOTAL Additional Revenue |
| --- | --- | --- | --- |
| a | Reallocate funds from the Regular Budget | 0 | 0 |
| b | Parking Fund from additional rentals outside business hours | 0 | 0 |
| c | Rental Income (annual rent increase) | $7,200 | $36,000 |
| d | Voluntary contributions from observers and outside entities | $120,000 | $600,000 |
| e | Special quota assessment | $2,552,800 | $12,764,000 |
| f | Cooperation with institutions dedicated to preservation | (in kind only) | 0 |
| g | Cooperation with OAS Scholarship recipients | (in kind only) | 0 |
| TOTAL | $2,680,000 | $13,400,000 |

ANNEX I

BACKGROUND:

INTEGRATED REAL ESTATE STRATEGY FOR THE

ORGANIZATION OF AMERICAN STATES

1.	REAL ESTATE STRATEGY RECOMMENDED BY THE BOARD OF EXTERNAL AUDITORS

The Board of External Auditors, in its report for 2010 and 2011, made the following recommendations regarding Real Property Strategy:

“1.7. The Board reaffirms its recommendation that the OAS implement a sustainable real property strategy that addresses the current deferred maintenance problems and preserves the assets for future use.

1.8. The Board recommends that the funding and responsibility for the maintenance and repairs of the Casa del Soldado be transferred to the OGS.”

2.	ACTIONS TAKEN BY THE GENERAL SECRETARIAT IN RESPONSE TO THE RECOMMENDATIONS OF THE BOARD OF EXTERNAL AUDITORS

In response to the recommendations made by the Board of External Auditors relating to Real Estate Strategy, the General Secretariat submitted a series of strategy documents in 2011 and 2012 to the CAAP (listed in Annex II) which had in common three components:

- An updated estimate of the cost of implementing outstanding deferred maintenance projects

- An updated estimate of funds available to cover deferred maintenance projects from:

  - Existing Regular Funds for Building maintenance budgetary allocations;

  - Existing Other Funds, including Rental Income, Hall of the Americas Fund, and Parking Fund; and

  - Additional funds potentially generated by optimizing GS/OAS use of existing space and maximizing rental income from unused office space;

- Options to generate additional funds to cover the gap between (1) and (2), including:

Sale/leaseback of the F Street Building and construction of smaller structure at C Street.

In discussions in the CAAP on the strategy documents described above, no consensus emerged regarding the proposed options to generate additional funds to cover the gap between the estimated funds needed for deferred maintenance and the estimated funds available.

ANNEX II

SUMMARY LIST OF DOCUMENTS SENT TO CAAP

ANNEX III

List of Deferred Maintenance Projects Completed in 2009 -2012

MNB = Main Building, Museum = Art Museum of the Americas, Casita = Casita, ADM = Administrative Building, SITE = Grounds Surrounding

| Implementation Year | Building | Area to be Repaired | ECR Estimate $US (2008) | Actual Cost $US | Variance |
| --- | --- | --- | --- | --- | --- |
| 2009 | MNB | Replace marble cracked in exterior steps | 500,000 | 37,384 | 462,616 |
| 2010 | MNB | Replaced 3 ea. 5 TON AC Units | 27,090 | 21,500 | 5,590 |
| 2010 | MNB | Replaced Radio 3 TON AC Unit | 7,447 | 5,910 | 1,537 |
| 2010 | MNB | Structural repairs/ reinforcement to patio fountain | 19,908 | 15,800 | 4,108 |
| 2010 | SITE | Resurface C St. Parking lot | 200,000 | 208,539 | -8,539 |
| 2010 | SITE | Resurface service driveway | 79,141 | 62,810 | 16,331 |
| 2011 | ADM | New plumbing on G level men's room | 5,494 | 4,360 | 1,134 |
| 2011 | ADM | Minor repair at title roof | 4,523 | 3,590 | 933 |
| 2011 | Casita | Remove exterior cement stucco | 73,080 | 0 | 73,080 |
| 2011 | MNB | Restore lighting in patio | 13,442 | 10,668 | 2,774 |
| 2011 | MNB | Restore lighting in historic exterior lighting fixtures | 48,000 | 37,700 | 10,300 |
| 2011 | MNB | Repair areas of damaged or deteriorated interior plaster | 75,600 | 60,000 | 15,600 |
| 2011 | MNB | Replaced AHU #6 | 34,217 | 27,156 | 7,061 |
| 2011 | MNB | AHU #7 duct work upgrade | 6,017 | 4,775 | 1,242 |
| 2011 | MNB | Replaced 20 TON Patio AC Unit | 32,489 | 25,785 | 6,704 |
| 2011 | MNB | Restore plumbing in patio fountain | 44,915 | 35,647 | 9,268 |
| 2011 | MNB | Service Driveway remove paving and replace waterproofing | 35,589 | 24,277 | 11,312 |
| 2011 | SITE | New Gate C St. Parking Lot | 23,869 | 18,944 | 4,925 |
| 2011 | SITE | Propagate the pace tree | 29,018 | 23,030 | 5,988 |
| 2011 | SITE | Restore historic planting scheme in gardens | 120,609 | 95,721 | 24,888 |
| 2012 | ADM | Replace Cooling Tower supply fan | 6,599 | 5,237 | 1,362 |
| 2012 | Casita | Clean and paint gutters & downspouts | 8,253 | 6,550 | 1,703 |
| 2012 | Casita | Install new high lime stucco at 1/4 exterior walls | 59,046 | 9,100 | 49,946 |
| 2012 | MNB | Repair/paint interior areas/restrooms | 11,340 | 7,825 | 3,515 |
| 2012 | MNB | New smoke detector and fire alarm | 475,000 | 197,500 | 277,500 |
| 2012 | MNB | Replaced 2 30 TON HOA AC Units | 100,624 | 79,860 | 20,764 |
| 2012 | MNB | Replaced 200 TON Cooling Tower | 100,000 | 79,990 | 20,010 |
| 2012 | MNB | New Surveillance Cameras | 3,348 | 2,657 | 691 |
| 2012 | Museum | Exterior Lighting | 9,576 | 7,600 | 1,976 |
| 2012 | Museum | Verified Smoke detector & Alarms | 491 | 390 | 101 |
| 2012 | Museum | Clean & Repair masonry at building base | 384,300 | 14,130 | 370,170 |
| 2012 | ADM | Install Smoke detection & Fire alarm system | 475,000 | 197,500 | 277,500 |
| 2012 | Museum | Replaced 10 Ton. AC Unit | 37,643 | 29,875 | 7,768 |
|  |  |  | 3,051,665 | 1,361,810 | 1,689,855 |

ANNEX IV

List of Outstanding Deferred Maintenance and Estimated Cost

MNB = Main Building, Museum = Art Museum of the Americas, Casita = Casita, ADM = Administrative Building, SITE = Grounds Surrounding; ADA=Americans with Disabilities Act (U.S. law governing accommodations for persons with disabilities)

| Building | Area to be Repaired | ECR Estimate $US (2008) | GS/OAS Estimate $US (2013) |
| --- | --- | --- | --- |
| ADM | New exit stairs | 37,800 | 17,010 |
| ADM | New ADA ramp | 44,100 | 19,845 |
| ADM | Re-equip elevator to ADA safety & compliance | 132,300 | 59,535 |
| ADM | Demo rest rooms | 567,000 | 255,150 |
| ADM | Remove floor to create two exit stairs from 2nd floor | 416,430 | 187,394 |
| ADM | Clean bronze doors & windows | 297,360 | 133,812 |
| ADM | Repair/Replace hardware as needed | 6,615 | 2,977 |
| ADM | 2 New doors and frameset two exits | 31,500 | 14,175 |
| ADM | Provide new exit signs | 63,000 | 28,350 |
| ADM | Provide emergency egress lighting | 75,600 | 34,020 |
| ADM | Restore Exterior light fixtures | 157,500 | 70,875 |
| ADM | Complete renovation of electrical system | 2,094,750 | 942,638 |
| ADM | New finishes in restrooms | 119,700 | 53,865 |
| ADM | New finishes in two exit ways | 126,000 | 56,700 |
| ADM | New sprinkler system. | 873,200 | 392,940 |
| ADM | Reset & regrout paver stones at front and terrace | 56,700 | 25,515 |
| ADM | Modify two exit window to become exit doors | 170,100 | 76,545 |
| ADM | Remove ferrous metal from stone | 31,500 | 14,175 |
| ADM | Remove sealant from marble joints and re-point | 3,276,000 | 1,474,200 |
| ADM | Remove sealant from brick parapet at flat roofs | 1,575,000 | 708,750 |
| ADM | Partial renovation HVAC | 2,179,501 | 980,776 |
| ADM | Create two new exit stairs from second to first floor | 181,440 | 81,648 |
| ADM | Renovate rest rooms for ADA access | 246,506 | 110,928 |
| ADM | Install Backflow prevention | 6,300 | 2,835 |
| ADM | Install ADA drinking fountains on two floors | 12,600 | 5,670 |
| ADM | Install back water valve on sewage pumps | 6,300 | 2,835 |
| ADM | Clean test and repair terrace drains | 12,600 | 5,670 |
| ADM | Repair fountain drainage system | 75,600 | 34,020 |
| ADM | Plumbing Upgrade | 66,150 | 29,768 |
| ADM | Upgrade surveillance cameras | 20,541 | 9,243 |
| ADM | Clean and repair roof drains & gutters | 7,560 | 3,402 |
| ADM | Seal all base flashings at parapet walls | 10,597 | 4,768 |
| ADM | Remove terrace pavers, replace waterproofing drainage | 7,560 | 3,402 |
| ADM | Repair/waterproof cracks at the four joints in the underground tunnel | 8,190 | 3,686 |
| Casita | Repair main entry door & hardware | 2,520 | 1,134 |
| Casita | Install lighted exit signs | 6,300 | 2,835 |
| Casita | Create emergency lighting system | 29,862 | 13,438 |
| Casita | Paint exterior cupola, soffits, windows, & doors | 39,946 | 17,976 |
| Casita | Paint metal Roof | 31,500 | 14,175 |
| Casita | Install new high lime stucco at 2/4 exterior walls | 59,046 | 26,571 |
| Casita | Install new high lime stucco at 3/4 exterior walls | 59,046 | 26,571 |
| Casita | Install new high lime stucco at 4/4 exterior walls | 59,046 | 26,571 |
| Casita | Verify smoke detection & fire alarm systems | 18,900 | 8,505 |
| Casita | Install sprinkler system | 80,640 | 36,288 |
| Casita | Install duct mounted humidifier | 18,900 | 8,505 |
| Casita | Provide back flow preventer | 20,790 | 9,356 |
| Casita | Upgrade surveillance cameras | 22,746 | 10,235 |
| Casita | Install counter flash over skirt flashing at cupola | 12,600 | 5,670 |
| MNB | New Pool base | 315,000 | 141,750 |
| MNB | Elevator shaft | 63,000 | 28,350 |
| MNB | Repair interior & exterior doors & windows | 141,120 | 63,504 |
| MNB | Upgrade door hardware/accessibility | 6,300 | 2,835 |
| MNB | New door for handicapped entrance | 56,700 | 25,515 |
| MNB | Upgrade HOA lighting | 56,700 | 25,515 |
| MNB | Create emergency lighting system for egress | 126,000 | 56,700 |
| MNB | Surge Protection | 44,100 | 19,845 |
| MNB | Install battery backed up exit signs to comply with life safety | 31,500 | 14,175 |
| MNB | Complete renovation of electrical system | 844,499 | 380,024 |
| MNB | Remove inappropriate interior lighting | 6,300 | 2,835 |
| MNB | Cleaning and restore historic light fixtures | 189,000 | 85,050 |
| MNB | Replace the main service switchboard 480VAC and transformer | 630,000 | 283,500 |
| MNB | Majority of the panels are over 45 years old. | 567,000 | 255,150 |
| MNB | Upgrade sound systems public rooms | 138,600 | 62,370 |
| MNB | Install new elevator | 226,800 | 102,060 |
| MNB | Paint Metal Roof - Skylight | 47,502 | 21,376 |
| MNB | Paint Exterior window frames | 63,000 | 28,350 |
| MNB | Paint metal Balconies | 18,900 | 8,505 |
| MNB | Paint skylight, metal | 56,700 | 25,515 |
| MNB | Cleaning refinishing pubic areas | 10,156 | 4,570 |
| MNB | Repair terrazzo floors | 425,048 | 191,272 |
| MNB | Install sprinkler system | 1,184,420 | 532,989 |
| MNB | Replace storage shack at Parking Lot entry | 31,500 | 14,175 |
| MNB | Remove existing concrete in Reflecting Pool | 1,031,940 | 464,373 |
| MNB | Make one new rough opening in exterior wall | 315,000 | 141,750 |
| MNB | Reset/regrout terrace flagstone | 37,800 | 17,010 |
| MNB | Create new handicap entrance | 157,500 | 70,875 |
| MNB | Restore pink marble fountain in patio | 56,700 | 25,515 |
| MNB | Remove all ferrous metal attachments in stone | 31,500 | 14,175 |
| MNB | Remove mortar and sealant in exterior marble joins & repoint | 2,336,111 | 1,051,250 |
| MNB | Remove mortar and sealant in exterior marble joins & repoint - partial - Skylight base seal and structural reforced | 628,890 | 283,001 |
| MNB | Conserve marble sculptures | 945,000 | 425,250 |
| MNB | Replace marble balusters | 1,071,000 | 481,950 |
| MNB | Clean all exterior marble surfaces with low pressure heated water and rinse a biocide | 1,852,200 | 833,490 |
| MNB | Modify control system | 1,260,000 | 567,000 |
| MNB | Upgrade HVAC systems | 906,756 | 408,040 |
| MNB | Repair/replace steel skylight | 50,400 | 22,680 |
| MNB | Treat/repair corrosion revolving door | 36,792 | 16,556 |
| MNB | Treat all corrode exposed steel structural members in drainage | 44,100 | 19,845 |
| MNB | Repair steel structure at canopy driveway | 18,900 | 8,505 |
| MNB | Back flow preventers on domestic water Fire protect and drainage. | 31,500 | 14,175 |
| MNB | Renovate restroom for greater capacity ADA | 152,460 | 68,607 |
| MNB | Make exterior fountains operational | 74,785 | 33,653 |
| MNB | New back water valves sewage pumps | 12,600 | 5,670 |
| MNB | Restore fountain reflecting pool | 50,400 | 22,680 |
| MNB | Cameras and system upgrades | 92,922 | 41,815 |
| MNB | HOA Acoustical improvements | 66,024 | 29,711 |
| MNB | Toilet partitions | 37,800 | 17,010 |
| MNB | Skylight complete repair, flash capping | 89,726 | 40,377 |
| MNB | Design and install overflow drainage system for the Skylight | 15,750 | 7,088 |
| MNB | Install new flashing | 21,853 | 9,834 |
| MNB | Wheel house: install new roofing & siding | 6,300 | 2,835 |
| MNB | Install subgrade waterproofing foundation walls | 20,790 | 9,356 |
| MNB | Waterproof subgrade mechanical room | 22,050 | 9,923 |
| MNB | Design & install new concierge desk/security | 45,990 | 20,696 |
| MNB | Frame & trim new handicap door | 63,000 | 28,350 |
| Museum | New Elevator Shaft | 50,400 | 22,680 |
| Museum | New elevator from basement to 2nd floor | 226,800 | 102,060 |
| Museum | Remove interior walls covering windows | 223,020 | 100,359 |
| Museum | Repair to doors & windows | 57,960 | 26,082 |
| Museum | ADA door hardware | 6,300 | 2,835 |
| Museum | Upgrade total lighting an panels through-out display areas | 373,464 | 168,059 |
| Museum | Install exit signs as needed | 18,900 | 8,505 |
| Museum | Replace existing lighting battery backup system due to its age | 56,700 | 25,515 |
| Museum | upgrade lighting in rear Loggia | 82,908 | 37,309 |
| Museum | Repair exterior plaster after downspout repairs | 22,050 | 9,923 |
| Museum | Paint Exterior Plaster | 37,170 | 16,727 |
| Museum | Paint exterior wood and metal | 18,900 | 8,505 |
| Museum | Repair interior walls after added display | 6,300 | 2,835 |
| Museum | Repair interior plaster after downspout repairs | 9,450 | 4,253 |
| Museum | Repair wood floors | 81,900 | 36,855 |
| Museum | Upgrade as needed | 36,667 | 16,500 |
| Museum | Sprinkler system | 151,200 | 68,040 |
| Museum | Bring Building fire alarm system up to code | 56,081 | 25,237 |
| Museum | Repair cracked terracotta pieces at soffits | 535,500 | 240,975 |
| Museum | Upgrade heating ventilation and cooling system | 65,970 | 29,686 |
| Museum | Install mechanical cooling & ventilation for logia | 85,388 | 38,424 |
| Museum | Reinforce staircase | 12,600 | 5,670 |
| Museum | Back water valve at drain | 36,540 | 16,443 |
| Museum | Back Flow preventers on domestic water supply | 32,130 | 14,459 |
| Museum | ADA access to rest rooms | 18,900 | 8,505 |
| Museum | System and surveillance camera upgrade | 20,059 | 9,027 |
| Museum | ADA Ramp | 107,100 | 48,195 |
| Museum | New movable display wall system | 315,000 | 141,750 |
| Museum | Repair or replace gutters | 31,500 | 14,175 |
| SITE | All Grounds | 1,794,408 | 807,484 |
|  |  | 34,891,091 | 15,700,991 |

ANNEX V

2013-2017 Plan for Implementation of deferred Maintenance Projects (prioritized in order of urgency)

MNB = Main Building, Museum = Art Museum of the Americas, Casita = Casita, ADM = Administrative Building, SITE = Grounds Surrounding

| Building | Implementation Year | Area to be Repaired | ECR Estimate | GS/OAS Estimate | Total per Building | Total per year |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | $US (2008) | $US (2013) |  |  |
| MNB+SITE | 2013 | Skylight complete repair | 888,890 | 319,384 |  |  |
| MNB+SITE | 2013 | Upgrade HVAC system- Partial - AHU #5 replacement | 65,000 | 28,640 |  |  |
| MNB+SITE | 2013 | Upgrade HVAC system- Partial - Temperature sensor E/P Transducer | 7,500 | 5,486 |  |  |
| MNB+SITE | 2013 | Upgrade HVAC system- Partial- Replace Water Heater | 9,500 | 6,964 |  |  |
| MNB+SITE | 2013 | Smoke detection & Fire Alarm System - Partial - Design & Dialers | 74,896 | 33,703 |  |  |
| MNB+SITE | 2013 | Metals - Partial -Main Stairs Handrail south side | 50,000 | 47,000 |  |  |
| MNB+SITE | 2013 | Repair interior & exterior doors & windows - partial - Café Azteca roll up doors | 20,000 | 12,460 |  |  |
| MNB+SITE | 2013 | Upgrade total lighting and panels - partial -Upgrade lighting Simon Bolivar & Marcus Garvey Hall | 6,000 | 4,554 | 458,191 |  |
| ADM | 2013 | ADM - Parking lot resurface - Partial - pre activities - conduits | 8,500 | 7,995 |  |  |
| ADM | 2013 | ADM Thermal & Moisture Protection - Partial - six panel replace office216 | 2,300 | 1,375 | 9,370 |  |
| Casita | 2013 | Install new high lime stucco at 2/4 exterior walls | 59,046 | 9,100 | 9,100 |  |
| MUSEUM | 2013 | Security Systems - partial - 2 windows guards and door guard Door | 7,000 | 5,300 |  |  |
| MUSEUM | 2013 | Repair or replace gutters | 25,000 | 1,800 | 7,100 | 483,760 |
| MNB+SITE | 2014 | Repair interior & exterior doors & windows - partial | 113,431 | 51,044 |  |  |
| MNB+SITE | 2014 | Upgrade HVAC system- Partial- New AHU President of the council | 17,500 | 7,875 |  |  |
| MNB+SITE | 2014 | Majority of the panels - partial - Feed 2 panels ( close to HOA & 1 Floor) | 175,000 | 78,750 |  |  |
| MNB+SITE | 2014 | Majority of the panels - partial -New panel in HOA and design | 85,000 | 38,250 |  |  |
| MNB+SITE | 2014 | Majority of the panels - partial - change and upgrade 3 panels ( close to HOA & 1 floor) | 214,000 | 96,300 |  |  |
| MNB+SITE | 2014 | Design & install new concierge desk/security and one coat attended desk | 45,990 | 20,696 |  |  |
| MNB+SITE | 2014 | Majority of the panels - partial - feed 2 Distribution panel Basement | 80,000 | 36,000 |  |  |
| MNB+SITE | 2014 | Install new flashing | 21,853 | 9,834 |  |  |
| MNB+SITE | 2014 | Create Handicap entrance | 157,500 | 70,875 |  |  |
| MNB+SITE | 2014 | Waterproof subgrade Mechanical Room | 22,050 | 9,923 |  |  |
| MNB+SITE | 2014 | Treat/repair corrosion revolving door | 36,792 | 16,556 | 436,102 |  |
| ADM | 2014 | Partial renovation HVAC - New chiller replace | 180,000 | 81,000 |  |  |
| ADM | 2014 | Reset & regrout paver stones at front and terrace | 56,700 | 25,515 | 106,515 |  |
| Casita | 2014 | Install counter flash over skirt flashing at cupola | 12,600 | 5,670 |  |  |
| Casita | 2014 | Install new high lime stucco at 3/4 exterior walls | 59,046 | 26,571 | 32,241 |  |
| MUSEUM | 2014 | ADA Ramp & access | 107,100 | 48,195 |  |  |
| MUSEUM | 2014 | Repair wood floors | 81,900 | 36,855 |  |  |
| MUSEUM | 2014 | Repair interior plaster downspout repairs | 9,450 | 4,253 | 89,303 | 664,160 |
| MNB+SITE | 2015 | Majority of the panels - partial - Replace 2 Switch boards | 225,000 | 101,250 |  |  |
| MNB+SITE | 2015 | Majority of the panels - partial - change 2 Distribution panel Basement | 147,500 | 66,375 |  |  |
| MNB+SITE | 2015 | Remove <mortar and sealant in exterior marble joins & repoint - partial 1 side | 250,000 | 112,500 |  |  |
| MNB+SITE | 2015 | Surge Protection | 44,100 | 19,845 |  |  |
| MNB+SITE | 2015 | Clear all exterior marble surfaces - partial 1/4 side | 95,000 | 42,750 |  |  |
| MNB+SITE | 2015 | Toilet partitions - Partial | 37,800 | 17,010 | 359,730 |  |
| ADM | 2015 | Seal all base flashings at parapet walls | 10,597 | 4,769 |  |  |
| ADM | 2015 | Modify two exit windows to become two exit doors | 170,100 | 76,545 |  |  |
| ADM | 2015 | 2 New doors and frameset two exits | 31,500 | 14,175 | 95,489 |  |
| Casita | 2015 | Install new high lime stucco at 4/4 exterior walls | 59,046 | 26,571 | 26,571 |  |
| MUSEUM | 2015 | Upgrade total lighting and panels - partial -Replace main panel | 85,000 | 38,250 |  |  |
| MUSEUM | 2015 | Upgrade feeder to main panel | 35,000 | 15,750 | 54,000 | 535,789 |
| MNB+SITE | 2016 | Upgrade HVAC system- Induction Units | 305,000 | 137,250 |  |  |
| MNB+SITE | 2016 | Renovate restroom for grater capacity ADA Partial | 37,500 | 16,875 | 154,125 |  |
| ADM | 2016 | Repair fountain drainage system | 75,600 | 34,020 |  |  |
| ADM | 2016 | ADM Thermal & Moisture Protection - Partial - six panel replace office216 | 14,166 | 6,375 |  |  |
| ADM | 2016 | Renovate restrooms and ADA access | 248,506 | 111,828 |  |  |
| ADM | 2016 | Create 2 new exits stairs from second to first floor | 181,400 | 81,630 |  |  |
| ADM | 2016 | New ADA Ramp | 44,100 | 19,845 | 253,698 | 407,823 |
| MNB+SITE | 2017 | Upgrade HVAC system- Partial-New Sum Pums | 150,000 | 67,500 |  |  |
| MNB+SITE | 2017 | Back flow preventers | 31,500 | 14,175 |  |  |
| MNB+SITE | 2017 | Clear all exterior marble surfaces - partial 2/4 side | 95,000 | 42,750 |  |  |
| MNB+SITE | 2017 | Upgrade HVAC system- Partial- New Feeding duct to Cooling Tower | 45,000 | 20,250 |  |  |
| MNB+SITE | 2017 | Repair terrazzo floors - partial | 250,000 | 112,696 | 257,371 |  |
| Casita | 2017 | Provide back flow preventer | 20,790 | 9,356 | 9,356 |  |
| MUSEUM | 2017 | ADA access to restrooms | 18,900 | 8,505 | 8,505 | 275,231 |
|  |  |  | 5,407,649 | 2,366,764 | 2,366,764 | 2,366,764 |

ANNEX VI

Operating Costs of the Casa del Soldado

| Sources of Funds | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
|  | US$ |
| RF (Building Mgm & Maintenance) | 137,358 | 192,406 | 304,712 | 173,988 | 156,343 |
| Rental Income Contribution |  |  |  |  | 45,000 |
| Total Sources of Funds | 137,358 | 192,406 | 304,712 | 173,988 | 201,343 |
| Uses of Funds |  |  |  |  |  |
| Buildings Utilities | 68,838 | 65,607 | 70,923 | 69,722 | 72,771 |
| Buildings Security | 1,654 | 2,018 | 156 | 1,701 | 77 |
| Cleaning and General Services | 32,789 | 27,870 | 27,843 | 32,372 | 31,151 |
| Buildings General Maintenance & Renovations | 24,867 | 87,106 | 196,224 | 59,368 | 84,852 |
| Insurance | 5,080 | 4,946 | 5,143 | 6,063 | 8,567 |
| Custodial Supplies | 4,130 | 4,859 | 4,423 | 4,76 | 3,925 |
|  | 137,358 | 192,406 | 304,712 | 173,988 | 201,343 |

Note:  The above table excludes approximately $240K for 2 military personnel assigned by the Member States for building administration/maintenance covered by Member States as "in kind" contribution.

ANNEX VII

Operating Costs of the Inter-American Children’s Institute

ANNEX VIII

Building Use and Restrictions

| Building | Use and Restrictions | Document |
| --- | --- | --- |
| OAS Main Building (MNB) | OAS Headquarters | Following the terms of set by the U.S. Congress regarding land and property rights ceded to the OAS, as well as the U.S. International Organizations Immunities Act, Article XI of the May 14, 1992 Headquarters Agreement Between the Organization of American States and the Government of the United States of America, provides: "If the Organization ceases to use for its Headquarters all of part of the Main Building or the Administration Building; or if the Organization ceases to use the Administration Building as an office building for its sole use; or if the seat of the General Secretariat and the Permanent Council is removed from Washington, D.C.; or if for any other reason the Organization decides to convey or otherwise dispose of its interest in the Main Building or the Administration Building, then: (a) The Organization shall give the Secretary of State prior |
| OAS Art Museum of the Americas (Museum) |  | notice, (b) If the notice pertains to the Administration Building, the Government shall have the option to purchase the interest of the Organization in the Administration Building at the purchase price that shall be the fair market value of the land and its improvements, less the fair market value of any portion of the land that was donated to the Organization by the Government. If any such notice pertains to the Main Building, the Government shall have the option to purchase the Main Building at a purchase price that shall be the fair market value of the land and its improvements. These options will expire if not exercise within a reasonable amount of time". |
| Casita |  |  |
| OAS Administration Building (ADM) | Office Building for OAS sole use |  |
| OAS General Secretariat Building (GSB) | OAS offices and offices and retail space for rental | By Resolution AG/RES 1697 (XXIX-0/99) the General Assembly authorized the Permanent Council to approve a plan for the renovation of the GSB that "would permit more effective and efficient use of space by the General Secretariat and improve the value of the space that could be rented to third parties". CP/RES. 775 (1251/00) Approval of the Plan for the Comprehensive Renovation of the General Secretariat Building. By resolution CP/RES 775 (1251/00) the Permanent Council Approved the GSB Renovation Plan. |
| OAS Secretary General’s Residence | General Secretary Official Residence | By Resolution CP/RES 678 (1067/96) the Permanent Council authorized the General Secretariat to purchase the property located at 2908-2944 University Terrace, N.W., Washington D.C., for the Organization Official Residence. This property was added to properties listed in the attachments to the Headquarters Agreement, and is listed as the Official Residence. |
| OAS Secretary General’s Residence Annex |  |  |
| Casa del Soldado | Inter-American Defense Board Headquarters | By Resolution AG/RES 1 (XXXII-E-06) the General Assembly established the Inter-American Defense Board as an "entity" of the Organization under Article 53 of the OAS Charter, an adopted the Statutes that provides on Chapter IX, Article 32 (32.1): "The IADB has it headquarters in the city of Washington, D.C., United States of the America. The OAS General secretariat shall allow the IADB to occupy and operate as its headquarters the property known as "Casa del Soldado", located at 2600 16th St., N.W., Washington, D.C. The IADB has the status of a public international organization and its own legal personality under the laws of the host country." One of the purposes of the Casa del Soldado, according to the Statute approved by the General Assembly, continues to be Headquarters of the IADB. |
| Inter American Children’s Institute | IIN | Property was acquired with previous authorization from the Board of Directors of the IIN. The Statute of the Inter American Children Institute provides on Chapter III, Article 9 (j) that it is function of the Directing Council “to dispose of the real estate or any other assets belonging to the Institute”. |

ANNEX IX

ANNEX X

Administrative Memorandum No. 68 Rev. 2 “Management of Resources and Facilities for Events at Headquarters”

http://www.oas.org/legal/english/admmem/admmem68Rev2.pdf

Annex A “OAS Facilities User Fees”

http://www.oas.org/legal/english/admmem/admmem68Rev2AnnexA.pdf

Annex B “Application and Agreement for the Use of the GS/OAS Resources and Facilities for Events at Headquarters”.

http://www.oas.org/legal/english/admmem/admmem68Rev2AnnexB.pdf

Annex C “Costs of the Use of OAS Facilities and Equipment for Special Events”

http://www.oas.org/legal/english/admmem/admmem68Rev2AnnexC.pdf

# Footnotes

.	This document stems from CAAP/GT/RVPP-232/14

.	Inter American Children’s Institute building is owned by the IIN.  See Annex VIII for Building Use and Restrictions

.	See Annex II for a complete list and links to these documents.

# Text boxes

CP31104E01

CP32584E01.DOC