PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES		CP/CSH-1349/11

9 September 2011

COMMITTEE ON HEMISPHERIC SECURITY		Original: Spanish

WORK PLAN OF THE Inter-American Defense Board

(Presented at the meeting held on September 8, 2011)

WORK PLAN

Inter-American Defense Board

1.	PURPOSE

The purpose of this Work Plan is to comply with resolution AG/RES. 2631 (XLI-O/11), “Support for the Activities of the Inter-American Defense Board,” which, in Article 5, resolves that the annual work plan and calendar of activities are to be presented to the Committee on Hemispheric Security.

2.	BASIS

a.	This plan was prepared in accordance with the Statutes of the IADB and the resolutions issued at the fourth plenary session of the OAS General Assembly held on June 7 in El Salvador.

3.	GENERAL CONSIDERATIONS

a.	The Statutes of the IADB, in Article 2, Purpose, and Article 3, Functions, provide the guiding principles for the activities and all the functions assigned therein to the various bodies of the IADB.

b.	All tasks listed in this plan are identified in terms of date and place, according to the following attachments:

- Annex A, Annual Calendar of Activities of the IADB;

- Annex B, Study Plan of the Inter-American Defense College.

4.	PURPOSE OF THE IADB (Article 2. of the Statutes)

a.	“The purpose of the IADB is to provide the OAS and its member states with technical and educational advice and consultancy services on matters related to military and defense issues in the Hemisphere in order to contribute to the fulfillment of the OAS Charter.”

b.	“In carrying out its purpose, the IADB shall take into account the needs of the smaller states, whose level of vulnerability is greater in the face of traditional threats and of new threats, concerns, and other challenges.”

5.	STRATEGIC OBJECTIVES

a.	In planning the tasks listed in this plan, account was taken of the following strategic objectives:

1)	Strategic Objective: To position the Inter-American Defense Board as the leading institution in terms of military advisory services, and the hemispheric point of reference on military and defense topics.

2)	Strategic Objective: To optimize interactions between the IADB and the various OAS bodies, especially with the Committee on Hemispheric Security and the member states, so as to meet advisory service requirements.

3)	Strategic Objective: To centralize information stemming from the regional and international defense forums so as to disseminate it properly in the Hemisphere.

6.	TIME FRAME

The Work Plan covers the period from September 2011 to July 2012 and reflects all activities in that period.

7.	IMPLEMENTATION OF THE PLAN

The implementation of this plan takes into account the functions established in the IADB Statutes, which are assigned to the IADB as objectives to be achieved by the various bodies that make up the Board (Council of Delegates, Secretariat, and Inter-American Defense College).

a.	Functions of the IADB (Article 3 of the Statutes)

1)	Objective: To provide technical and educational advice and consultancy services on matters related to military and defense issues.

- Tasks involved in meeting the objective

a)	Examine the resolutions of the fourth plenary session of the OAS General Assembly.

b)	Compile the Annual Work Plan of the IADB for presentation to the Committee on Hemispheric Security.

c)	Prepare the Annual Report of the IADB.

d)	Prepare the Annual Institutional Memory of the IADB.

e)	Prepare a proposal for organizing all existing legislation, lessons learned, and experiences of the various member states in relation to military and defense matters.

2)	Objective:  To offer to military officers and civilian officials from the OAS member states, through its Inter-American Defense College in Washington, D.C., advanced academic courses on matters related to military and defense issues, the inter-American system, and related disciplines.

- Tasks involved in meeting the objective

a)	The Calendar of Activities of the Inter-American Defense College, approved by the Council of Delegates, is attached as Annex B.

b)	Study the proposed measures to make the Inter-American Defense College an academic center of excellence and point of reference for the Hemisphere on matters of defense and security.

3)	Objective: To promote interaction and cooperation between and among ranking civilian officials and military officers from the OAS member states on matters related to military and defense issues.

- Tasks involved in meeting the objective

a)	Issue the appropriate invitations to the series of conferences organized by the IADB Secretariat when confirmation is received from the presenter as to the date and topic.

b)	Advise OAS officials of the regular meetings of the Council of Delegates and of any activities planned by the IADB where their attendance would be essential.

c)	Request a permanent office on OAS premises for a high-level IADB official to represent the Chair of the Council of Delegates.

d)	To replace Ship’s Captain (Federative Republic of Brazil) Simao Zoccolaro as liaison officer to the OAS, since he has completed his service as adviser of the IADB’s Subsecretariat for Advisory Services (SAS).

4)	Objective 1: To provide OAS member states with technical advisory services on comprehensive mine action in the Hemisphere, including cooperation with the OAS General Secretariat.

Objective 2: To request the Inter-American Defense Board to continue providing technical advice to the AICMA Program, AG/RES. 2630 (XLI-O/11), “The Americas as an Anti-Personnel Land-Mine Free Zone.”

- Tasks involved in meeting the objectives

a)	Inspect, through a special adviser on the ground in Colombia, the procedures employed by inter-American monitors to control the activity in that country.

b)	Attend the ceremony marking the change of command of the MARMINAS mission (Quito).

c)	Arrange a coordination meeting with the new chief of MARMINAS at the Casa del Soldado.

d)	Hold the Fifth Doctrine Meeting on Humanitarian Demining at the Casa del Soldado.

e)	Present to the OAS complete information and updates on humanitarian demining.

f)	Disseminate the Humanitarian Demining Manual and its updates to the various competent areas of the OAS and to the member states.

5)	Objective: To provide OAS member states with technical advisory services in the management, security, and destruction of weapon stockpiles.

- Tasks involved in meeting the objective

a)	Create the Management, Security, and Destruction of Weapon Stockpiles Section within the Military and Defense Matters Division.

b)	Appoint Colonel Víctor M. Del Orbe Frías (Dominican Republic) as head of that section.

6)	Objective: To provide OAS member states with technical advisory services in developing national defense doctrine and policy papers (“White Papers”).

- Tasks involved in meeting the objective

a)	Compile, through the IADB delegations, complete information on the activities, evolution, and requirements related to defense white papers of the member states and disseminate that information widely through the OAS General Secretariat (AG/RES. 2625).

b)	Organize, at the Casa del Soldado, a presentation on Brazil’s defense white paper.

7)	Objective: To provide OAS member states with technical advisory services in the development of transparency measures and confidence- and security-building measures.

- Tasks involved in meeting the objective

a)	Verify and analyze the reports received through the IADB delegations, so as to compile the reference document.

b)	Participate in meetings of the Committee on Hemispheric Security on confidence- and security-building measures (CSBMs), urging the member states to remit the necessary information.

8)	Objective: To maintain, for the OAS, updated inventories of confidence- and security-building measures both in the Hemisphere and in other regions, as well as an electronic database of the information contained in those inventories; and to prepare, when requested, studies on such measures and draft guidelines for the standardized presentation of reports on the application of such measures by member states.

- Task involved in meeting the objective

a)	Deliver annually to the OAS General Secretariat the updated document on the CSBMs, both in printed form and on a magnetic medium.

9)	Objective: To promote interaction and cooperation with other regional and global organizations of a similar nature related to technical aspects of military and defense issues.

- Tasks involved in meeting the objective:

Plan for optimizing compliance with the objective:

Promote coordination and interaction among the various specialized conferences of the armed forces at the Casa del Soldado, so as to compile and supplement the information and documentation issued by them.

a)	Support to the Conference of Defense Ministers of the Americas (CDMA)

1)	Attend the CHDS 2011 Regional Conference in Santiago, Chile, on the “New Security Environment, New Defense Alternatives: Responding to the Challenges of the IX CDMA.”

2)	Attend the workshop on the regional mechanism for a swift, coordinated response to natural disasters, in Costa Rica.

3)	Hold a coordination workshop on matters of interest to the X CDMA, at the Casa del Soldado.

4)	Participate in the second thematic meeting with the aim of compiling the contributions of the defense ministries into the thematic agenda for the X CDMA, in Montevideo.

5)	Participate in the X Conference of Defense Ministers of the Americas.

b)	Conference of American Armies (CAA)

1)	Attend the preparatory meeting of the XXIX Commanders’ Conference of the American Armies in Lima, Peru.

2)	Attend the XXIX Commanders’ Conference of the American Armies in Lima, Peru.

3)	Submit the corresponding report to the Committee on Hemispheric Security.

c)	Inter-American Naval Conference (CNI)

1)	Gather the reports of the IX Inter-American Naval Conference of Directors of Intelligence in Brazil.

2)	Gather the reports of the Inter-American Naval Conference on Naval Telecommunications in Mexico.

3)	Attend the IX Inter-American Naval Conference in Mexico.

d)	System of Cooperation among the Air Forces of America (SICOFAA) and the Conference of American Air Chiefs (CONJEFAMER)

1)	Participate in the meetings of the SICOFAA cycle committees.

2)	Gather and disseminate the reports of the SICOFAA committees.

3)	Participate in the preparatory meeting of the LII CONJEFAMER.

4).	Participate in the LII CONJEFAMER, to be held in Canada.

e)	Conference of Central American Armed Forces (CFAC)

1)	To attend the Conference of Central American Armed Forces (dates and place not yet confirmed).

10)	Objective: To provide OAS member states with technical advice and consultancy services for relief and humanitarian assistance in the case of disasters and for search and rescue.

- Task involved in meeting the objective

a.	Attend the SAR 8 meeting promoted by the Lima regional office of the International Civil Aviation Organization (ICAO), in Paraguay.

11)	Objective: In carrying out its purpose, the IADB shall take into account the needs of the smaller states, whose level of vulnerability is greater in the face of traditional threats and of new threats, concerns, and other challenges.

- Tasks involved in meeting the objective

a)	Strengthen cooperation with the appropriate OAS bodies, such as CICAD, CICTE, and CIFTA, maintaining a presence in those forums and seeking to provide advice on challenges in the small island states.

b)	Handle the necessary coordination with regional and subregional organizations on matters related to the special security concerns of small states, including the Regional Security System (RSS) and the Caribbean Community (CARICOM).

c)	Through the Director General, invite the diplomatic representatives of the small states that are not members of the IADB to participate in the various meetings of the Council of Delegates and others of interest, so as to encourage their presence in this multilateral forum.

d)	Handle coordination for a lecture by the Director of the National Police of the Dominican Republic on implementation of the democratic security plan and on the conclusions arising from the International Seminar on the Strategic View of Public Security: Dialogue between Dominican Society and the National Police, held from July 13 to 15, 2011, in Santo Domingo, D.R.

e)	Handle coordination for a lecture by the Director of the emergency operations center (COE) of the D.R. on lessons learned from the natural events that have hit the Caribbean region, especially the Dominican Republic.

12)	Objective:  To prepare the annual program-budget of the IADB for presentation to the Council for approval.

- Tasks involved in meeting the objective

a)	Prepare the program-budget for presentation to and approval by the Council of Delegates.

b)	Receive, and provide the necessary support to, the OAS auditors at the Casa del Soldado.

13)	Objective:  To approve the annual program-budget of the IADB and present it to the OAS Secretary General

- Task involved in meeting the objective

a)	Present the program-budget to the OAS General Secretariat and to the Committee on Administrative and Budgetary Affairs (CAAP).

14)	Objective:  The Council of Delegates shall hold regular and special meetings for the purpose of taking decisions necessary for carrying out its functions.

- Task involved in meeting the objective

a)	Conduct and broadly publicize the regular meetings of the Council of Delegates (Annex A hereto contains detailed information on the dates).

8.	PRESENTATION OF THE PLAN

The following plan will be presented to the Committee on Hemispheric Security on September 8, 2011, as provided in AG/RES. 2631 (XLI-O/11), “Support for the Activities of the Inter-American Defense Board.”

Washington, D.C., September 8, 2011

Lieutenant General Guy Thibault G.R., CMM, CD

Chair of the IADB

Annual Calendar of Activities of the IADB Secretariat

2011

| MONTH | DATE | ACTIVITY |  | PLACE |
| --- | --- | --- | --- | --- |
| AUGUST | 1 to 30 | Appointment of an adviser to participate in the activities of the Conference of Central American Armed Forces (CFAC) |  | IADB |
|  | 11 | Visit and presentation by the Commander of the Army of Uruguay |  |  |
|  | 16 | Regular meeting 1322 of the Council of Delegates |  |  |
|  | 8 to 12 | Participation of an adviser in the CICAD meeting on maritime drug trafficking in Santo Domingo |  | DOMINICAN REPUBLIC |
|  | 22 to 26 | Preparatory meeting for the XXIX Commanders’ Conference of the American Armies in Lima. Attendance by an IADB adviser |  | PERU |
|  | 23 | Visit and presentation by the Minister of Defense of Guatemala |  | IADB |
|  | 29 and 30 | Workshop of the Conference of Defense Ministers of the Americas (CDMA)–regional mechanism for a swift, coordinated response to natural disasters, in San José |  | COSTA RICA |
| SEPTEMBER | 1 to 30 | Preparation of the 2012-13 Work Plan |  | IADB |
|  |  | Preparation of the Annual Report |  |  |
|  |  | Preparation of the Annual Institutional Memory |  |  |
|  |  | Verification and analysis of reports received on CSBMs |  |  |
|  | 13 | Regular meeting 1323 of the Council of Delegates |  |  |
|  | 13 | Change of command of the MARMINAS mission in Quito |  | ECUADOR |
|  | 23 | Secretariat’s visit to Andrews Air Force Base |  | D.C. |
|  | 14 to 17 | Workshop - topics of interest to the CDMA |  | IADB |
| MONTH | DATE | ACTIVITY |  | PLACE |
| OCTOBER | 1 to 30 | Follow-up on activities related to the defense white papers of the member states |  |  |
|  |  | Preparation of report on analysis and review of technical, advisory, and educational assistance for presentation to the CSH in December |  |  |
|  | 5 to 7 | Meeting of the IX CNIE- Directors of Intelligence in Rio de Janeiro |  | BRAZIL |
|  | 11 | Regular meeting 1324 of the Council of Delegates |  | IADB |
|  | 24 to 28 | Travel by the IADB adviser to the GMI-CO in Bogotá |  | COLOMBIA |
|  | 24 to 28 |  | Commanders’ Conference of the American Armies in Lima – close of the XXIX CAA cycle / Attendance by the Chair and Director General of the IADB | PERU |
|  |  |  | Inter-American Naval Conference on Naval Telecommunications in Veracruz. Attendance by an IADB adviser | MEXICO |
|  | 24 to 28 |  | Attendance by an IADB adviser at the SAR8 in Asunción. Meeting promoted by the regional office of the International Civil Aviation Organization (ICAO) | PARAGUAY |
| NOVEMBER | 1 to 30 |  | Verification and analysis of reports received on CSBMs | IADB |
|  |  |  | Participation in meetings on CSBMs | OAS |
|  | 7 to 11 |  | V Doctrine Meeting on Humanitarian Demining | IADB |
|  |  |  | Meeting with new chief of MARMINAS |  |
|  | 8 |  | Regular meeting 1325 of the Council of Delegates |  |
|  | To be determined |  | Meeting of the operations committee of the System of Cooperation among the Air Forces of America (SICOFAA) | USA |

| MONTH | DATE | ACTIVITY | PLACE |
| --- | --- | --- | --- |
| DECEMBER | 6 | Regular meeting 1326 of the Council of Delegates | IADB |
|  | To be determined | Presentation of report on humanitarian demining | OAS |
|  |  | Presentation of the report on analysis and review of technical, advisory, and educational assistance to the CSH |  |
|  |  | Presentation of the Annual Report of the IADB to the CSH |  |

2012

| MONTH | DATE | ACTIVITY | PLACE |
| --- | --- | --- | --- |
| JANUARY | 10 | Regular meeting 1327 of the Council of Delegates | IADB |
|  | To be determined | Presentation of the IADB budget to the CAAP | OAS |
|  |  | Attendance at meetings on CSBMs |  |
| FEBRUARY | 01 to 30 | Preparation of a plan for improving the guidance and advisory services offered by the IADB to the inter-American system, optimizing natural disaster response capabilities in the Hemisphere | IADB |
|  | 14 | Regular meeting 1328 of the Council of Delegates |  |
| MARCH | 1 to 30 | Conclusion on the inventory of CSBMs (re. measures applied in 2010) |  |
|  | 13 | Regular meeting 1329 13th plenary |  |
|  | 20 to 23 | Inter-American Naval Conference in Veracruz | MEXICO |
|  | To be determined | Travel by an adviser to MARMINAS in Quito | ECUADOR |

| MONTH | DATE | ACTIVITY | PLACE |
| --- | --- | --- | --- |
| APRIL | 12 | Meeting of the Americas | BOWLING AIR FORCE BASE |
|  | 17 | Regular meeting 1330 of the Council of Delegates | IADB |
|  |  | Presentation on CSBMs and white papers to the Council of Delegates |  |
|  | 18 | Change of command of the GMI- CO in Bogotá | COLOMBIA |
|  | To be determined | Meeting with new chief of GMI-CO | IADB |
|  |  | Presentation of the plan for improving the guidance and advisory services offered by the IADB to the inter-American system, in response to natural disasters in the Hemisphere |  |
|  |  | OAS auditors |  |
| MAY | 15 | Regular meeting 1331 of the Council of Delegates |  |
|  |  | Presentation to the Council of Delegates of updates to the humanitarian demining manual |  |
|  | To be determined | Preparatory meeting, LII Conference of American Air Chiefs. Attendance by an IADB adviser | NICARAGUA |
|  |  | Presentation on CSBMs and white papers to the CSH | OAS |
| JUNE | 19 | Regular meeting 1322 of the Council of Delegates | IADB |
|  | To be determined | LII Conference of American Air Chiefs. Attendance by an IADB adviser | CANADA |
| To be determined |  | Biannual Conference of Defense Ministers of the Americas in Montevideo | URUGUAY |

http://scm.oas.org/pdfs/2011/CP27023E.xls

input.doc