PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CP/CAAP-3096/11 add. 5

23 February 2012

COMMITTEE ON ADMINISTRATIVE	Original: English

AND BUDGETARY AFFAIRS

_________________________________________________________________________________

Progress Report

comprehensive human resource management strategy

.

Progress Report

COMPREHENSIVE HUMAN RESOURCE MANAGEMENT STRATEGY

PRESENTED TO THE CAAP ON

PURSUANT TO

AG/RES. 1 (XLII-E/11)

## PROGRAM-BUDGET OF THE REGULAR FUND OF THE ORGANIZATION FOR 2012

- Reduction of Number and Regularization of Levels of Trust Positions

AG/RES 1 (XLII-E/11) on the "Program-Budget of the Regular Fund of the Organization for 2012 and Contributions to FEMCIDI, Section III.A.7.d", instructed the Secretary General to comply no later than January 31, 2012 with Article 21 of the General Standards, which establishes that the number of trust positions financed by the Regular Fund shall not exceed eight percent of the positions financed by that Fund.

As reported to the CAAP on January 20, 2012 in CP/CAAP-3096/11 add. 4 rev. 1, “Progress Report, Comprehensive Human resource Management Strategy, Phase One”, the Secretary General has reduced, effective February 1, 2012,  the number of positions of trust to a level below eight percent of the 471 positions financed by the Regular Fund for 2012.

The final reduction of positions of trust implemented by the Secretary General, consisted of three following actions:

  - Separating from service, between November 1, 2011 to January 31, 2012, 6 staff members occupying trust positions.

  - Returning 7 staff members holding a trust position to their previous appointment, and,

  - Appointing 6 staff members on fixed-term contracts due to their current functions not fulfilling the condition for a trust position according, to the document CP/.4673/11 Note of the Secretary General to the Chair of the Permanent Council “A strategic Vision of the OAS” presented on December 19, 2011.

Pursuant to the CAAP meeting on January 20, 2012 and as per Member States request, the list of Positions of Trust as of February 1, 2012 was published in the CP/CAAP-3153/12 “Status of Trust Appointments in the General Secretariat” document presented to CAAP on January 31, 2012. According to this table, the total number of positions of trust in the Regular Fund was 37, representing 7.9% of the positions financed by the Regular Fund for 2012.

Below it is presented the List of Positions of Trust as of February 1, 2012 and as of August 31, 2011.

In regard to the positions of trust that held a continuing contract before being appointed to a trust position, and that effective February 1, 2012 were returned to their previous contract, Article 21. Trust Personnel. b. Description and Special Provisions. iv. states that a staff member under a continuing contract and who is appointed to a position of trust shall maintain his/her continuing contract status while in the position of trust and, subject to agreement with the Secretary General, may, upon the termination of the trust appointment, be placed under a continuing contract in a non-trust position at the grade he/she had immediately prior to accepting the trust appointment.

In addition, as requested by Member States, the SAF/DHR estimated the gross savings generated by the reduction of trust positions, which corresponds to $997.6. However, the net savings will be determined once the Cost of Living Adjustment (COLA) is published in April of 2012.

The SAF/DHR will estimate the total net savings of the elimination of trust positions in order to be included in the progress report that will be presented to CAAP in April of 2012.

- ICR Reform

As informed in the CP/CAAP/RVPP-133/12 "Fund for Indirect Cost Recovery (ICR) 2012 projected program-budget" document presented by the Secretariat for Administration and Finance (SAF) on January 30, 2012, the General Secretariat submitted the 2012 projected budget for the Fund for Indirect Cost Recovery. In regard to expenses for 2012, personnel expenses are projected to be $6.5 million dollars based on existing personnel funded by ICR at January 15, 2012.

In the above mentioned document it was informed that the ending cash balance for December 2012 is projecting a year-end cash deficit of approximately $2.5 million dollars. It was also informed that in order to eliminate this deficit, the GS/OAS plans to reduce the personnel costs charged to the ICR budget through a combination of the following:

- eliminating ICR funding for any positions attributable to direct project costs;

- vacancies

- administrative streamlining

In regard to the GS/OAS initiative to explore options that allow staff members whose contracts are currently funded with Specific Funds and Indirect Cost Recovery Fund (ICR) to access to fixed term Series B-long term contracts by way of competition, the Department of Human Resources (DHR) is conducting an analysis to determine the budgetary impact of such option.

A preliminary outcome of such analysis indicates that as of January 31, 2012 there are 134 staff members, 53 contracts funded by ICR and 81 contracts funded by Specific Funds, that may be eligible to compete for a fixed term Series B-long term contract. If these staff members were appointed to a fixed term Series B-long term contract the additional estimated annual cost would be, $385,500 for ICR and $694,500 for Specific Funds as presented in the following chart:

The budgetary impact of granting fixed term Series B-long term contracts to these staff members represents a liability that would need to be covered by the donors that finance such contracts. For these reason, it is necessary to analyze the donor agreements and review if they would be willing and able to cover the aforementioned costs.

As informed in the last progress report, once the costs associated with opening to competition all positions funded by ICR and Specific Funds are approved, the DHR will develop a proposed calendar that will consider to open to competition such positions after the selection competition working plan for positions in the regular fund is completed at the end of the first semester of 2014.  The positions financed by ICR and Specific Funds will follow the same criteria of the current competitions of the regular fund. This means that the DHR will plan to publish 16 cases every 3 months and this period will serve as the estimated time frame in which the selection process should be completed for each group.

- Modernization of Retention Incentives

As informed in CP/CAAP-3096/11 add. 4 rev. 1, “Progress Report, Comprehensive Human resource Management Strategy, Phase One” the GS/OAS has started a benchmark process with IO’S and will continue this initiative with public sector institutions of different Member States in order to benchmark on their retention incentives.

While the GS/OAS has already made initial contact with various Permanent Offices of Member States in order to analyze their retention incentives and career plans, the SAF/DHR developed a preliminary comparative study with IO’s such as United Nations (UN), World Bank, Inter-American Development Bank and Pan American Health Organization on their performance retention incentives.

The preliminary results of this benchmark are presented for your review as follows:

After the DHR identified, reviewed and informed in the last progress report of  its current retention and career development structure, and once the benchmarking with IO’s organization and public sector institutions of different Member States is completed, the GS/OAS will analyze the best practices that best suit the GS/OAS current needs and priorities in order to develop a retention incentive proposal that will permit to attract and maintain the most suitable staff members within the Organization.

- Enhancement of Transparency in Human Resources Practices

In order to assure transparency and, at the same time, timeliness in the GS/OAS human resources practices, SAF/DHR is currently implementing a more structured and expedited procedure for the recruitment and selection of direct hires in positions under fixed term- Series A short term contracts and trust contracts. This mechanism is published in the OAS Web Site as “Call for Resumes”.

This procedure is different from the current regulatory and selection process at the GS/OAS and it is conducted in half of the previous time comprising: the announcement of the Employment Opportunity in the OAS website; prescreening of applicants by the DHR; Panel Interview composed by a DHR representative and two staff members occupying managerial positions at the GS/OAS including the Director of the pertinent area; and final evaluation and recommendation. From September 2011 as of today, the GS/OAS has received 23 applications to two Call for Resumes for employment opportunities at administrative and technical areas within the GS/OAS. In addition, the DHR has designed and implemented a recruitment and selection guide for the hiring areas which delineates the procedures for the selection of the most suitable candidates for short term positions as a result of the call for resumes published in the OAS website.

In view that the above is a newly implemented process, it is subject to revisions and improvements.  However, this mechanism is intended to award merit-based appointments, address organizational needs, and to support the GS/OAS to attract and select top talent human capital through a competitive selection process that is efficient and reliable. The DHR will continue to improve this new process in order to develop a formal policy to apply competitive recruiting practices for vacant positions.

Moreover, as part of the development of a revised career-path cycle and the development of a successful succession planning program, the GS/OAS has estimated the retirement of 50 staff members from the General Secretariat within the next five years. With this information being identified, the SAF/DHR will continue working in the design and implementation of a formal career plan and a successful succession planning program in order to develop potential successors for key positions in the Organization. This initiative could result in the reduction of recruitment costs, retention of good performers within the GS/OAS, and ensure that while staff remain in the organization their skills and knowledge is shared among other staff members. It also provides transparency in the human resources processes within the organization by providing fairness and equal opportunity to all staff members.

The DHR will continue benchmarking the best business practices on career development and succession planning of other IO´s and public sector institutions of the Member States and the results will be analyzed and presented on the following progress reports as well as an analysis to determine which practices could be successfully applied in the Organization considering the GS/OAS regulations as well as its organizational mission and culture.

- Identify General Standards revisions required for implementation of items I – IV above.

The GS/OAS is currently working in order to determine the need to adjust the current regulatory framework and what specific standards/rules should be addressed in order to support the updated and revised human resources management strategy.

Some examples of the current existing rules that were preliminary identified in order to be reviewed include:

Awards, Recognitions and Corrective Measures

- Rule 103.4 Step Increases

- Rule 103.5 Salary Policy on Promotion

- Rule 105.1 Promotions

- Rule 105.10 Staff Incentive Awards

- Rule 114.2 Award of Merit

- Rule 105.4 Reduction in Grade

- Rule 105.8 Training and Career Development

- Rule 111.1 Disciplinary Measures

- Rule 110.4 Termination of Services

Performance Evaluation System

- Rule 105.9 Work Performance Evaluation

Contracting Mechanisms; Recruitment and Selection

- Chapter 4. Types of Employment, Selection and Promotion

- Rule 104.1 Types of Employment

- Rule 104.2 Career Service

- Rule 104.3 Employment for a Limited Time

- Rule 104.4 Trust Appointments

- Rule 104.5 Competition for Filling Vacant Posts

- Rule 104.6 Selection Criteria

- Rule 104.15 Local and International Recruitment

- Rule 104.16 Independent Contractors

- Rule 104.17 Associate Staff Members

- Rule 104.18 Local Professional

- Rule 104.19 Temporary Support Personnel

- Rule 112.2 Reconsideration

- Rule 112.5 Procedure for Reconsideration

- Rule 102.3 Classification Procedure

The SAF/DHR will continue working on the identification and revision of the General Standards and Staff Rules that might require adjustment in order to implement the new Human Resource Management Strategy and will work closely with The Department of Legal Services (DLS) in this initiative.

# Text boxes

Summary

Following-up on the CP/CAAP-3096/11 Human Resources Management Plan document presented to CAAP on March, 2011, and in order to comply with Member States requests under the AG/RES. 1 (XLII-E/11) Program-Budget of the Regular Fund of the Organization for 2012 and Contributions to FEMCIDI III.A.7. Human resource policy, the Secretariat for Administration and Finance (SAF/DHR) delivered to CAAP on December 6th, 2011 the CP/CAAP-3096/11 add.4 rev. 1 Comprehensive Human Resource Management Strategy Phase One Action Plan Guide document, which outlined an HR Phase One Action Plan Guide addressing the following sections:

- The reduction of number and regularization of levels of trust positions in order to comply with Article 21 of the General Standards related to the number of trust positions financed by the Regular Fund,

- Reform of the personnel administered under Indirect Cost Recovery (ICR) and Specific Funds,

- Modernization of retention incentives by benchmarking retention incentives and career development practices, develop a proposal for linkage of performance awards and pay to performance evaluation system, among others,

- Enhancement of transparency in human resources practices by developing a plan to introduce competitive, open, recruitment for fixed term (Series A) and trust contracts and a policy for competitive recruiting to all vacant positions, and,

- Revision of the General Standards to adjust the human resources rules, policies, and practices of the General Secretariat in order to implement the above mentioned initiatives.

Continuing with the initiative to present to CAAP a progress report of the Human Resources Management Strategy every three months, the SAF/DHR presents a third progress report including information of what has been done for each of the abovementioned sections during the last month. The SAF/DHR will continue to benchmark on best practices with IO’s and sector public institutions of different Member States, and implement initiatives in order to develop an updated and reviewed Comprehensive Human Resource Management Strategy which will be presented to CAAP in May of 2012.

2012 Benchmarking with International Organizations on their Performance Retention Incentives

CP28022E01