OEA/Ser.G

CP/doc.5085/14

5 December 2014

Original: English

NOTE FROM THE SECRETARY GENERAL TRANSMITING THE Plan and Chronology to implement the recommendations that fall to the

General secretariat contained in the STRATEGIC PLAN FOR

MANAGEMENT MODERNIZATION AT THE OAS

Plan and Chronology to implement the recommendations that fall to the General Secretariat contained in the STRATEGIC PLAN FOR MANAGEMENT MODERNIZATION AT THE OAS

## AG/RES. 1 (XLVIII-E/14) Program-Budget of the Organization for 2015-2016 states in paragraph 4:

To instruct the Secretariat to present to the Permanent Council for its consideration no later than November 30, 2014 a plan to implement the recommendations included in the Strategic Plan for Management Modernization (CP/doc.5077/14). This plan will include items, which fall under the authority of the General Secretariat, for immediate implementation, and recommendations for medium and long term implementation for the consideration of member states before the next General Assembly.

In compliance with this mandate, the General Secretariat is pleased to present the following information, which should be read in conjunction with the Strategic Plan for Management Modernization (SPMM).

The document organizes the SPMM recommendations which lie under the purview of the General Secretariat into four time windows reflecting when the Secretariat’s intentions to begin implementation.  The time windows are as follows:

- Now until the end of December 2014

- January 2015 until the General Assembly Haiti

- After the General Assembly until December 2015

- 2016 and beyond

In addition to the planned time windows for implementation, each recommendation details the GS’s projections regarding its financial impact, utilizing the following categories:

- None – the implementation of these recommendations have no financial impact.

- Revenue Generating - recommendations will generate income once their implementation has been completed.

- Cost – the implementation of these recommendations will incur cost and require identification of funds for implementation.

Finally, the document attempts to identify the Department within the General Secretariat in charge of the implementation of the recommendation as well as the legal instrument, if any, which will need to be amended or created.

The General Secretariat understands that this document will be considered by the member States and discussed with the Secretariat, possibly in the CAAP, if the Permanent Council should so choose.  At that time, in order to present a more complete picture and to aid the discussion, the Secretariat is prepared to table an additional working document which places ALL recommendations in the SPMM into a similar format.

| Recom. Number | RECOMMENDATION FROM THE STRATEGIC PLAN FOR MANAGEMENT MODERNIZATION | Time Window | Financial Impact | Implementing Department | Legal Instrument for implementation |
| --- | --- | --- | --- | --- | --- |
| 3.1 | OAS maintains and strengthens results-based management | Now-Dec 2014 | None | DPE | Admin Memo |
| 3.2 | Strengthen the Project Evaluation Committee | Now-Dec 2014 | None | DPE |  |
| 8.1 | Require programme areas to monitor and close dormant project accounts | Now-Dec 2014 | None | DFAMS | Directive |
| 8.2 | Require programme areas to report on the reasons for their dormant project accounts | Now-Dec 2014 | None | DFAMS | Directive |
| 25 | Continue practice of proactive disclosure (accountability tab) | Now-Dec 2014 | None |  |  |
| 37 | Increase the parking fees to market rates effective January 2015 | Now-Dec 2014 | Revenue generating | DGS | Admin Memo |
| 39.1 | Continue and increase rental of available facilities to maximize revenues | Now-Dec 2014 | Revenue generating | DGS |  |
| 31.1 | Review and update the 2007 policy on workplace harassment | Now-Dec 2014 | Cost | SAF |  |
| 31.2 | Review and update the harassment recourse mechanisms | Now-Dec 2014 | Cost | SAF |  |
| 30.1 | Gather all the ethics and conflict of interest guidelines and regulations into a single document | Now-Dec 2014 | None | DLS |  |
| 30.2 | Provide this document to all new staff and to all staff attending orientation training | Now-Dec 2014 | Cost | SAF |  |
| 30.3 | Provide a half-day “Ethics at the OAS” session to all staff | Now-Dec 2014 | Cost | SAF |  |
| Recom. Number | RECOMMENDATION FROM THE STRATEGIC PLAN FOR MANAGEMENT MODERNIZATION | Time Window | Financial Impact | Implementing Department | Legal Instrument for implementation |
| 5.2 | Secretary of SAF to determine ICR allocations from 2015 onwards | Jan 2015-GA | None | SAF |  |
| 15 | Consolidate the rules under the SG authority and consider simplification into one document | Jan 2015-GA | None | DLS/SG |  |
| 22.2 | Modify EO such that Project Evaluation Committee becomes the Internal Evaluation Committee | Jan 2015-GA | None | DLS/DPE |  |
| 22.3 | DPE to draft an evaluation policy and guidelines for approval by the PEC | Jan 2015-GA | None | DLS/DPE | Executive Order |
| 22.5 | In 2015, evaluate Scholarship programme, and do a participatory assessment of MS committees | Jan 2015-GA | Cost | DPE | Admin Memo |
| 27.1 | Provide full cost information on translation and clarify translation needs for working documents | Jan 2015-GA | None | DCM |  |
| 36.1 | Issue an Administrative Memorandum to better define Direct Costs in Specific Fund projects | Jan 2015-GA | None | DFAMS | Admin Memo |
| 39.2 | After a transition period, remove rental waiver afforded to organizations using OAS premises | Jan 2015-GA | Revenue generating | DGS |  |
| 41.1 | Strengthen external fund resource mobilization. | Jan 2015-GA | None |  |  |
| 41.2 | Systematic promotion campaign with Specific Fund donors, and through social media | Jan 2015-GA | None | SER |  |
| 44 | SG to issue directive on the appropriate number of OAS staff attending meetings outside DC | Jan 2015-GA | Revenue generating | SG |  |
| 47.1 | Inventory then revoke all existing exceptions to the staff rules | Jan 2015-GA | None |  |  |
| 47.2 | Consider all new requests (including renewals) through Senior Advisory Committee and disclose | Jan 2015-GA | None |  |  |
| 48.1 | Consider a strategic partnership with the planned Smithsonian American Latino Museum | Jan 2015-GA | None | Museum |  |
| 48.2 | Consider a valuation of the artwork owned by the OAS | Jan 2015-GA | Cost | Museum |  |
| 51.1 | Develop an Information Management Policy | Jan 2015-GA | None | DOITS | Admin Memo |
| 10.1 | Create a Senior Advisory Committee to make recommendations to SG on all rule exceptions | Jan 2015-GA | None | SG |  |
| 10.2 | The SG should disclose his/her use of discretionary authority to Member States | Jan 2015-GA | None | SG |  |
| 11 | General Secretariat develop a framework and guidelines governing systematic staff meetings | Jan 2015-GA | Cost | DHR |  |
| 12 | Conduct periodic Staff Engagement surveys before the GA in 2016, 2018 and 2020 | Jan 2015-GA | Cost | DHR |  |
| 13 | Create a formal Staff-Management Consultative Committee | Jan 2015-GA | None | DHR |  |
| 28 | General Secretariat to provide biennial executive orientation seminar to Member States | Jan 2015-GA | Cost | DHR |  |
| 16 | Introduce corporate risk assessment on a pilot basis in third quarter of 2015 | GA-Dec 2015 | Cost | SG |  |
| 36.2 | With new ERP, consider automating the recording of time and labour allocation, to calculate direct labour costs | GA-Dec 2015 | Cost | DFAMS |  |
| 49.1 | Review and update the policy on retention and disposal of paper records | GA-Dec 2015 | None | Library/DOITS |  |
| 49.2 | Vigorously digitize paper documents | GA-Dec 2015 | Cost | Library/DOITS | Admin Memo |
| 49.3 | Close file rooms as paper documents are archived or disposed of | GA-Dec 2015 | Cost |  | Directive |
| 50.1 | Confirm the policy on retention and disposal of electronic records | GA-Dec 2015 | None | DOITS/Library |  |
| 51.2 | Review the Access to Information policy | GA-Dec 2015 | None | SG/DOITS |  |
| 51.3 | Develop a Privacy Policy | GA-Dec 2015 | None | SG/DOITS |  |
| 59.1 | Decisions which are exceptions to the staff rules to be made by Senior Advisory Committee (see recommendation 10.1) | GA-Dec 2015 | None | DHR |  |
| 65.3 | Draft FAQs to enable those familiar with OAS to explain Management Modernization to others | GA-Dec 2015 | None | SER |  |
| 65.4 | Develop key messages for use by incoming SG when meeting high-level dignitaries in DC or field | GA-Dec 2015 | None | SG |  |
| 65.5 | Make external communications products widely available in website and social media | GA-Dec 2015 | None | SER |  |
| 66.2 | Ombudsman to monitor progress and report to all stakeholders | GA-Dec 2015 | None |  |  |
| 65.1 | Develop a Management Modernization information package for external distribution | GA-Dec 2015 | Cost |  |  |
| 65.2 | Provide appropriate communications training and key messages to National Offices | GA-Dec 2015 | None |  |  |
| 17 | Annual audit plan to continue to be guided by an informal process of risk assessment | 2016 and Beyond | None | SG |  |
| 21.2 | Commission an evaluation of the internal audit function (preferably peer review) in 2016 | 2016 and Beyond | Cost |  |  |

# Text boxes

CP33910E04.doc