JOINT WORKING GROUP	OEA/Ser.T/VIII

OF THE PERMANENT COUNCIL AND CEPCIDI	GTC/CASA/doc.125/10 rev. 1

ON THE DRAFT SOCIAL CHARTER OF THE AMERICAS	12 May 2010

Original:  Spanish

_________________________________________________________________________________

WORK PLAN

PRESENTED BY THE CHAIR OF THE JOINT WORKING GROUP

OF THE PERMANENT COUNCIL AND CEPCIDI

ON THE DRAFT SOCIAL CHARTER OF THE AMERICAS

(For the period from May to July, 2010)

- Introduction

The Joint Working group has been busy preparing the Draft Social Charter of the Americas since 2005.  The goal of the Chair is to proceed transparently and at a brisk but safe pace in such a way that, by the end of his term, we will have managed to complete consideration of the Operative Section of the Social Charter and made substantial progress with the Preamble and Plan of Action.

The Working Group still has to complete Chapter IV on Cultural Development, Diversity, and Pluralism and to begin consideration of Chapter V on Solidarity and Collective Effort in the Americas.  There are also some articles pending in Chapters II and III for which consensus has still be reached.

- Mandate

During the Fifth Summit of the Americas, held in Port-of-Spain, Trinidad and Tobago in April 2009, the Heads of State and Government reiterated their support for the objectives of the Social Charter of the Americas and its Plan of Action, which seek to provide all our citizens with greater opportunities to benefit from sustainable development with equity and social inclusion, and they urged that preparation of those instruments and the negotiations be completed by the end of 2009.

Likewise, during the thirty-ninth regular session of the General Assembly, held in San Pedro Sula, Honduras, the member states adopted resolution AG/RES. 2449 (XXXIX-O/09), “Social Charter of the Americas: Renewal of the Hemispheric Commitment to Fight Poverty in the Region,” in which they renewed the commitment they had undertaken and entrusted to the Joint Working Group of the Permanent Council and CEPCIDI on the Draft Social Charter of the Americas to work intensively to conclude negotiations on the Draft Social Charter of the Americas and its Plan of Action and to adopt those documents before the end of 2009.

- Meetings and continuation of the work of the Working Group

The Working Group will work formally in accordance with the schedule included in this document. The Chair hopes to conclude work on the operative section of the Draft Social Charter during the meetings to be held in May and June 2010; the June meetings coming after the end of the fortieth regular session of the General Assembly.

Once consideration of the Operative Section – Chapters IV and V, as well as articles pending from earlier Chapters – the Chair hopes to begin, make headway with, and hopefully reach consensus on the Preambular Section in the month of June.

The Plan of Action is also part of our current mandate.  Consideration of the proposed Plan of Action will begin once consideration of the Preambular Section has concluded.

Over the past nine weeks, a large number of informal meetings have taken place and more will be convened as necessary in order to explain positions and facilitate consensus.

This document proposes key meetings for May and June.  If the political commitment materializes, the Chair would propose holding additional meetings in June in the hopes of achieving a speedy conclusion of the negotiations.  Depending on how much has been achieved by then, proposals will be put forward at the June 22 meeting for meetings in the month of July.

- Negotiations

The Chair recognizes that a spirit of flexibility, friendly camaraderie, and cooperation among the members of the Working Group will be necessary if we are to successfully conclude our work in a productive and timely fashion.  Nevertheless, the Chair will exercise its power to put an end to a debate if, in its opinion, the discussions become unproductive.  The Chair also trusts that the delegations will attend the negotiation sessions equipped with instructions from their departments regarding the proposals to be addressed.

Luis Alfonso Hoyos Aristizábal

Ambassador, Permanent Representative of Colombia to the OAS

Chair of the Joint Working Group of the Permanent Council and CEPCIDI 
on the Draft Social Charter of the Americas

- Schedule of Formal Meetings

SCHEDULE OF FORMAL MEETINGS OF THE JOINT WORKING GROUP

May and June 2010

| DATE input.doc input.doc | - TIME - PLACE | - TOPICS |
| --- | --- | --- |
| - Tuesday, May 11, 2010 | - 3:00 – 5:00 p.m. - Guerrero | - Report of the Chair - Continued consideration of Chapter IV - Start of consideration of Chapter V - Consideration of the draft resolution to be submitted to the General Assembly at its fortieth regular session |
| - Tuesday, May 18, 2010 | - 3:00 – 5:00 p.m. - Guerrero | - Continued consideration of Chapter IV - Start of consideration of Chapter V |
| - Tuesday, May 25, 2010 | - 3:00 – 5:00 p.m. - Guerrero | - Continued consideration of Chapter V (if necessary; if not consideration of articles still pending) |
| - Thursday, June 17, 2010 | - 3:00 – 5:00 p.m. - Bolivar | - Consideration of articles pending in Chapters II and III (or, if agreed upon, start of consideration of the Preambular Section) |
| - Tuesday, June 22, 2010 | - 3:00 – 5:00 p.m. - Bolivar | - Consideration of the Preambular Section - Establishment of the schedule of meetings in July |

Notes	1. Additional meetings of the Working Group could be scheduled for the week beginning on May 24, 2010 and for the week beginning on June 22, 2010.

2. Progress in consideration of the topics depends on the proceedings and agreements reached at meetings. Some topics can be brought forward depending on the dynamics of the negotiations and agreements reached.

input.doc