Joint Working Group of the	OEA/Ser.T/VIII

Permanent Council and CIDI ON THE DRAFT	GTC/CASA/doc.195/12 rev. 1

PLAN OF ACTION OF THE SOCIAL CHARTER	23 October 2012

OF THE AMERICAS	Original: Spanish

_________________________________________________________________________________

WORK PLAN OF THE JOINT WORKING GROUP

OF THE PERMANENT COUNCIL AND CIDI ON THE DRAFT PLAN OF ACTION

OF THE SOCIAL CHARTER OF THE AMERICAS

2012 - 2013

(Approved at the meeting held on September 19, 2012)

- Introduction

By resolution AG/RES. 2056 (XXXIV-O/04) the General Assembly instructed the Permanent Council and the Permanent Executive Committee of the Inter-American Council for Integral Development (CEPCIDI) to jointly prepare a draft Social Charter of the Americas and a Plan of Action that included the principles of social development and established specific goals and targets that would reinforce the existing instruments of the Organization of American States on democracy, integral development, and the fight against poverty.

In order to carry out the task, in September 2005, the Permanent Council and CEPCIDI established the Joint Working Group on the Draft Social Charter of the Americas. In November of that year, at the Fourth Summit of the Americas held in Mar del Plata, Argentina, the Heads of State and Government offered their encouragement to the OAS in drafting the Social Charter of the Americas and its Plan of Action, whose principles and objectives, they said, “will be directed towards the achievement by member states of societies that offer all of our citizens more opportunities to benefit from sustainable development with equity and social inclusion.”

Subsequently, the mandate issued to the Permanent Council and CEPCIDI was reiterated by the General Assembly in resolutions AG/RES. 2139 (XXXV-O/05), AG/RES. 2241 (XXXVI-O/06), AG/RES. 2278 (XXXVII-O/07), AG/RES. 2363 (XXXVIII-O/08), AG/RES. 2449 (XXXIX-O/09), AG/RES. 2542 (XL-O/10), and AG/RES. 2695 (XLI-O/11).

Work on the preparation of the draft Social Charter of the Americas culminated successfully with the adoption by the General Assembly of the Social Charter contained in document AG/doc.5242/12, as reflected in resolution AG/RES. 2699 (XLII-O/12). In that resolution, the General Assembly instructed the Working Group “to conclude negotiations on a draft Plan of Action of the Social Charter prior to the forty-third regular session of the General Assembly.”

- Officers

For the current term, the Permanent Council and the Inter-American Council for Integral Development installed the Working Group on September 6, 2012. In accordance with Article 28 of the Rules of Procedure of the Permanent Council, on that same date Ambassador Walter Jorge Albán Peralta, Permanent Representative of Peru to the Organization of American States (OAS) was elected Chair. The election of the Vice Chair was left pending for a later meeting of the Working Group.

- Mandate

On August 22, 2012, the Permanent Council assigned the Working Group the task of follow-up and implementation of resolution AG/RES. 2699 (XLIIO/12), “Social Charter of the Americas:  Renewal of the Hemispheric Commitment to Fight Poverty in the Region.” That resolution instructed the Working Group to conclude negotiations on a draft Plan of Action of the Social Charter prior to the forty-third regular session of the General Assembly.

- Activities of the Working Group

In order to fulfill the mandate set forth in resolution AG/RES. 2699 (XLII-O/12), the main thrust of the Working Group's activities will be the negotiations on the draft plan of action, based on the framework document presented by the Executive Secretariat for Integral Development, which will be enriched with comments and opinions from member states and from international organizations and specialized agencies invited by the Working Group for that purpose.

The Working Group will hold meetings as per the attached schedule, one of which will be devoted to questions of procedure, another to discussions with specialized agencies, and the remainder to the negotiation of the draft plan of action.

I am pleased to present this Work Plan, which will serve as a general framework for the activities of the Group in the 2012-2013 term and will be open to such amendments as the Working Group may approve or that are deemed necessary as work progresses on the entrusted task for ensuring the best results.

I would like to take this opportunity to say that I welcome any suggestions by member states on this draft work plan and am grateful for your support in completing the work assigned to the Working Group.

Walter Jorge Albán Peralta

Ambassador, Permanent Representative of Peru to the OAS

Chair of the Joint Working Group of the Permanent Council 
and CIDI on the Draft Plan of Action

of the Social Charter of the Americas

ANNEX I

| SCHEDULE OF MEETINGS FOR THE 2012 – 2013 TERM/ |  |
| --- | --- |
| September 2012 –April 2013 |  |
| September 19, 2012 2:30 p.m. – 5:30 p.m. Guerrero Room | - Election of the Vice Chair. - Presentation and adoption of the draft work plan. - Presentation of the “Proposed Structure for the Plan of Action” prepared by the Executive Secretariat for Integral Development through its Department of Social Development and Employment. - Request to the members of the Working Group to submit in writing to the Chair of the Working Group by October 8, 2012, their comments on the document presented by the Secretariat. |
| October 2, 2012 10:00 a.m. – 1:00 p.m. 2:30 p.m. – 5:30 p.m. Simón Bolívar Room | Meeting with invited international agencies (UNDP, ECLAC, PAHO, IDB, ILO, and World Bank) on the status of the social goals of the Americas, the main hemispheric challenges in light of the issues contained in the Social Charter, and proposals for progress on the social goals of the Americas. |
| October 8 | Deadline for member states to submit comments on the document presented by the Secretariat. |
| October 9 to 30 | Preparation by the Chair of the Working Group—with the support of the Secretariat—of a draft plan of action based on the framework document presented at the first meeting of the Group, proposals advanced by member states, and those produced by the meetings with international agencies. The document will be distributed on October 31. |
| November 13, 2012 2:30 p.m. – 5:30 p.m. Guerrero Room | - Adoption of the negotiation procedure. - Start of negotiations on the draft plan of action based on the document presented by the Chair. |
| December 12, 2012 2:30 p.m. – 5:30 p.m. Guerrero Room | Negotiation of the draft plan of action. |
| January 15, 2013 10:00 a.m. – 5:30 p.m. Guerrero Room | Negotiation of the draft plan of action. |
| February 19, 2013 10:00 a.m. – 5:30 p.m. Guerrero Room | Negotiation of the draft plan of action. |
| March 26, 2013 10:00 a.m. – 5:30 p.m. Guerrero Room | Negotiation of the draft plan of action. |
| April 9, 2013 10:00 a.m. – 5:30 p.m. Guerrero Room | - Negotiation of the draft plan of action. - Presentation of the draft resolution |
| April 23, 2013 10:00 a.m. – 5:30 p.m. Guerrero Room | - Negotiation of the draft plan of action. - Negotiation of the draft resolution |
| May 7, 2013 10:00 a.m. – 5:30 p.m. Guerrero Room | - Negotiation of the draft plan of action. - Negotiation of the draft resolution |

input.doc

.	This schedule will be open to such amendments as the Working Group may approve or that are deemed necessary as work progresses on the entrusted task for ensuring the best results.