Committee on Migration Issues	OEA/Ser.W

CIDI/CAM/doc. 46/17

20 November 2017

Original: Spanish

MEDIA CAMPAIGN:

“MIGRANTS COUNT IN THE AMERICAS”

TIMELINE FOR THE CAMPAIGN’S MAIN EVENTS

(Prepared by the Chair of CAM)

Objective: Provide a guide for the main events identified where dissemination efforts will be focused, among other communications activities to be determined./

PHASE ONE: DECEMBER/17-FEBRUARY/18

- Document of messages about core content – migrants’ contributions to destination countries (approved by the states)

- Web page with campaign information on the OAS website – Under the Secretariat for Access to Rights and Equity page – with a link to the CAM page

- Launch video

- Art

- Video – Secretary General + others who join in

Events

December 12, 2017:

- Thematic Meeting I: Migrants’ contributions to destination countries:  Productive endeavors, wealth creation, consumption patterns, taxes, payment for services, cultural contributions, ideas, and identities

- Launch of the Campaign: "Migrants Count in the Americas"

December 18, 2017:

  - International Migrants Day: Recognition of migrants’ contributions to the Hemisphere’s economic and social development

  - Launch of the Fourth Report – International Migration in the Americas 2017

February 2018:

  - CIDI meeting on the Inter-American Program with Program implementers to share progress and exchange best practices

  - Negotiation of the Global Compact on Safe, Orderly, and Regular Migration (UN)

PHASE TWO: MARCH-JUNE/18

- Document of messages on core content – migrants’ contributions to their countries of origin and socio-economic reintegration of returned migrants (approved by the states)

- Facebook Live (list of influencers and persons to be interviewed to be determined)

March 2018:

  - Panel – Thematic Meeting II: Socio-economic reintegration of returned migrants

April 2018:

  - Panel – Thematic Meeting III: Migrants’ contributions to their countries of origin

- Remittances and development

- Diaspora and development: Mobilization of the resources and abilities of the diasporas to invest in and develop their communities of origin

input.doc

.	The events identified may be subject to change and are based on the CAM’s scheduled work plan. New activities could be added in the future based on synergies with other organizations, etc.