INTER-AMERICAN COUNCIL	OEA/Ser.W

FOR INTEGRAL DEVELOPMENT	CIDI/CPD/doc. 4/12 rev. 1

27 November 2012

comMITTEE ON PARTNERSHIP FOR	Original: Spanish

DEVELOPMENT POLICIES

- PROPOSED SCHEDULE FOR FIRST PROGRAMMING CYCLE 
TOURISM HEMISPHERIC FUND

- (Agreed during the meeting held November 27, 2012)

| ACTIVITY / PHASE | DATE |
| --- | --- |
| Send invitations to Member States to make their voluntary contributions to the FHT and instructions for submitting projects under the FHT input.doc input.doc input.doc | December 7, 2012 |
| Send to Member States the Format to Present Projects with its corresponding manual of instructions. input.doc | December 7, 2012 |
| Deadline for the receipt by the Secretariat of voluntary contributions made by States to the FHT | January 31, 2013 |
| Deadline for submission of projects under the FHT | February 15, 2013 |
| Review by the General Secretariat of the projects submitted by the Member States to determine whether they comply with the provisions of the Statutes and Regulations of the FHT | February 28, 2013 |
| Meeting of the Nonpermanent Specialized Committees (CENPE) and presentation of their recommendations to CITUR | March 31, 2013 |
| CITUR virtual meeting and approval of projects. Notification to the Permanent Missions of approved projects | April 11, 2013 |
| Signing of the agreements with the executing agencies of the selected projects. | April 30, 2013 |

CIDRP00119E01