COMmittee for partnership-for-	OEA/Ser.W

development policies		CIDI/CPD/doc.147/17

22 September 2017

Original: Spanish

DRAFT WORK PLAN OF THE COMMITTEE ON

PARTNERSHIP-FOR-DEVELOPMENT POLICIES (CIDI)

(Presented by the Chair and prepared by the Secretariat)

In fulfillment of the functions of the Committee on Partnership-for-Development Policies and of the mandates entrusted to it by CIDI, in 2017-2018, the Committee will focus its work on three fundamental areas and its main tasks will be carried out as described below:

- Review of supplementary information for the development pillar of the Strategic Plan (development pillar)

- Receipt of reports by the technical areas on implementation of the mandates and guidelines for the preparation of the annual report of SEDI to CIDI

- Follow-up to and implementation of the Triennial Ministerial Cycle

- Preparations for the 2018 General Assembly session, including review of the outline of the omnibus draft resolution and its negotiation.

|  | Document | Mandate/CIDI Decision | Dates and work mechanism |
| --- | --- | --- | --- |
| 1 | Strategic Plan of the Organization (development pillar) (CP/doc.5268/17 rev. 1 Español - English) | Review of the supplementary information for the development pillar of the Strategic Plan presented by the Secretariat and presentation of recommendations to CIDI. | Estimated date for completion of task: September and October 2017: Study with a view to presenting recommendations at the meeting of CIDI on November 14. Procedure: (i) Informal meetings with the Secretariat so that the areas can present and answer concerns of the delegations; (ii) if necessary, adjustment of supplementary information presented by the Secretariat and receipt of concrete proposals presented by delegations; (iii) informal meetings to review the recommendations to be presented to CIDI; (iii) formal meeting to approve the recommendations. |
| 2 | Reports Decision of the LXX regular meeting of CIDI and AG/RES. 2904 (XLVII-O/17) “Advancing Hemispheric Initiatives on Integral Development” | - Provide any additional information the delegations deem relevant regarding the annual report of SEDI to CIDI approved (CIDI/doc.226/17 rev. 1 Español - English - Français - Português) | Estimated date for completion of task: September and October 2017: Study with a view to presenting recommendations at the meeting of CIDI on November 14. Procedure: (i) Creation of an informal drafting group to prepare an outline to be used for the report, taking into account the format of the Strategic Plan, (ii) informal discussion and with the Secretariat of the proposed outline; (iii) formal meeting to approve the recommendations |
|  |  | Semiannual reports to the Committee on Policies on the implementation of and follow-up to the mandates, programs, and activities of the integral development pillar. | Estimated date for completion of task: Recurring task to be carried out throughout the year. Procedure: To optimize the use of resources and time, presentations by the technical areas will be scheduled for them to report on both the activities they are carrying out in implementation of the Strategic Plan and of the Triennial Ministerial Cycle. Formal and informal meetings will be scheduled. |
|  |  | Report on progress made in implementing the Triennial Ministerial Cycle (which would also be included in the annual report of CIDI to the General Assembly) (by March 31) |  |
| 3 | Implementation of the Triennial Ministerial Cycle: AG/RES. 2904 (XLVII-O/17) “Advancing Hemispheric Initiatives on Integral Development” | General follow-up to the preparations for ministerial meetings and the stages after they are held so that all processes immediately begin to implement the Triennial Ministerial Cycle in their respective areas, progressively making the necessary adjustments to their work procedures in consultation with the respective sectoral authorities. | (Annexes 1 and 2 include the 2017-2021 schedule of meetings and table with the position of the different stages of the each sector’s ministerial cycle) |
|  |  | Presentation and discussion of the work plans agreed by the sectoral authorities for implementation of ministerial mandates (Stage 3). | Estimated date for completion of task: Recurring task to be carried out throughout the year. Once the authorities of the sectoral process reach agreement on a work plan (Stage 2) in follow-up to the corresponding ministerial meeting, an agenda item will be included so that the technical area can make a formal presentation to the Committee on Policies (Stage 3) Procedure: Agenda item at formal meetings. |
|  |  | Update of the Rules of Procedure of CIDI and harmonization of the Rules of Procedure of the inter-American committees and any other normative document for alignment with the Triennial Ministerial Cycle adopted. | Estimated date for completion of task: Presentation by the Secretariat: by October 31, 2017. Completion of task: by the end of 2017 Procedure: Initial presentation and adoption of the document at a formal meeting. Discussion and negotiation at informal meetings. |
|  |  | Review of the ministerial schedule (6 years, for adoption at the first meeting held by CIDI each year) | Estimated date for completion of task: Presentation in December by the Secretariat of proposal for forwarding recommendation to CIDI in January. Procedure: Initial presentation and final adoption of the document at a formal meeting. Discussion, if necessary, at informal meetings |
| 4 | Preparations for the 2018 OAS General Assembly session | - Review of the outline of the omnibus draft resolution and negotiation of texts to be recommended to CIDI. | Estimated date for completion of task: February to May 2018 Procedure: Formal and informal meetings. |

ANNEX 1:	SCHEDULE OF MINISTERIAL AND HIGH-LEVEL MEETINGS

| Sectoral process | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Education | Education ministerial meeting (Bahamas, February 9-10) | Meeting of CIE | Education ministerial meeting (Antigua and Barbuda) |  | Meeting of CIE | Education ministerial meeting (host country tbd) |
| 2. Labor | Labor ministerial meeting (Barbados, December 7-8) |  | Meeting of Labor working groups (WGs) | Labor ministerial meeting (host country to be determined) |  | Meeting of Labor WGs |
| 3. Tourism |  | Tourism ministerial meeting (Guyana. March 21 and 22) |  | Meeting of CITUR | Tourism ministerial meeting (host country to be determined) |  |
| 4. Science and Technology | Science and Technology ministerial meeting (Colombia, November 1 and 2) |  | Meeting of COMCYT | Science and Technology ministerial meeting (host country to be determined) |  | Meeting of COMCYT |
| 5. Culture |  | Culture ministerial meeting (Barbados) |  | Meeting of CIC | Culture ministerial meeting (Guatemala) |  |
| 6. Sustainable Development |  |  | Sustainable development ministerial meeting (host country tbd) |  | Meeting of CIDS | Sustainable development ministerial meeting (host country tbd) |
| 7. Social Development |  | Social development ministerial meeting (Guatemala) |  | Meeting of CIDES | Social development ministerial meeting (Guatemala) |  |
| 8. Cooperation |  | Cooperation ministerial meeting (OAS headquarters) |  |  | Cooperation ministerial meeting (host country tbd) |  |
| 9. Ports |  | CIP (Mexico) |  | Meeting of CIP (host country tbd) |  | Meeting of CIP (host country tbd) |
| Other meetings* (For reference only) | ECPA ministerial meeting (Chile, September 7 and 8) Americas Competitiveness Forum and RIAC (Mexico , September 13 to 15) Dialogue of High-Level MSME Authorities (Mexico, May 16 and 17) |  | Americas Competitiveness Forum and RIAC (Argentina) Dialogue of High-Level MSME Authorities (El Salvador) |  |  |  |
| * Other meetings of sectoral processes that support the priorities of CIDI but that, at the time of this resolution, are not considered official ministerial processes subject to the Triennial Ministerial Cycle and do not receive funding from the OAS Regular Fund. Abbreviations: CIC: Inter-American Committee on Culture CIDES: Inter-American Committee on Social Development CIDS: Inter-American Committee on Sustainable Development CIE: Inter-American Committee on Education CIP: Inter-American Committee on Ports CITUR: Inter-American Committee on Tourism COMCYT: Inter-American Committee on Science and Technology ECPA: Energy and Climate Partnership of the Americas RIAC: Inter-American Competitiveness Network MSMEs: Micro, small-, and medium-sized enterprise |

ANNEX 2:	SECTORAL PROCESSES OF CIDI AND THEIR POSITION AT EACH STAGE OF THE TRIENNIAL MINISTERIAL CYCLE

CIDRP02034E04

# Footnotes

.	The Committee on Partnership-for-Development Policies (a) To prepare, at the request of the regular meetings of CIDI, the draft strategic plan and draft inter-American programs using, when appropriate, any technical inputs to those drafts that may arise from sectoral or specialized meetings on the corresponding thematic subject; (b) To monitor implementation of the substantive aspects of the inter-American programs and make recommendations necessary to ensure coherence between cooperation policies and the projects and activities undertaken by the  Executive Secretariat for Integral Development and other pertinent areas of the General Secretariat; (c) To prepare the draft yearly schedule of meetings held within the framework of CIDI: sectoral or specialized at ministerial or equivalent level, inter-American committees, and other high-level policy and technical meetings; (d) To analyze the annual work plans and semiannual progress reports of the pertinent areas of the General Secretariat as well as the reports of the IACD, and submit to the regular meetings of CIDI the recommendations that it deems appropriate; and (e) To take up other matters within its sphere of competence that regular or special meetings of CIDI assign to it.

# Text boxes

CIDRP02034E04

cidrp02034s01

JUL

AUG

SEP

OCT

NOV

DEC

JAN

FEB

MAR

APR

MAY

JUN

JUL

AUG

SEP

OCT

NOV

DEC

1

2

3

4

1

2

3

4

1

2

3

4

1

2

3

4

Education

2.Plan

3.Com

4.CIE

Labor

5.CIDI

6.Prep

1.Min

2.Plan

4.Com

Tourism

1.Min

S and T

6.Prep

1.Min

2.Plan

Culture

2.Plan

Sustainable Dev.

Social Dev.

4.

CIDES

Cooperation

Ports

CIP

Ministerial mtgs

Programs for the

year:

Stages

1. Ministerial and/or high-level meeting

Policy dialogue

2. Planning meeting of the authorities of the ministerial process

Defines Work Plan

3.Meeting of the  Committee on Policies

Enriches Work Plan

Implementation of the Work Plan

4. Meeting of IA Committee or IACML working groups

Evaluation, implementation, definition of topics for next ministerial meeting

5. Meeting of CIDI

Formal presentation of ministerial documents and launch of informal negotiation

6.Formal preparatory meeting

Final negotiation of ministerial documents

Education

Labor WGs (IACML);

COMCYT, OAS

Sustainable Development;

CIP

Inter-Anerican Committees:

CIE:

I-A Committee on Education

CITUR:

IA Comm on Tourism;

COMCYT:

IA Comm on Science & Tech.;

CIE:

IA Comm on Culture;

CIDS:

IA Comm on Sustainable Development;

CIDES:

IA Comm on Social Development

The IA Conference of Ministers of Labor does not have an IA Committee.  It has Working Groups

2019

2020

2021

Implementation Work Plan

2022

Education, BAH, Feb.9-10, 2017

S & T, COL, Nov. 1-2, 2017

Labor, BAR, Dec.2017

IA Comm Social Dev (CIDES) OAS, Nov. 9-10

Tourism, GY, Mar. 21-22, 2018;

Culture, BAR, ______________, 2018;

Cooperation, OAS, ______________2018;

CIP, Mexico, July 2018

2017

2018

Education, AB;

Sustainble Development

COMCYT, OAS;

Cooperation, OAS;

COMCYT;

Labor WGs (IACML)

Competitiveness, ARG;

MSMEs, ESV

Labor;

CITUR, OAS;

Science and Tec;h

CIC, OAS;

CIDES, OAS;

CIP

CIE

Tourism;

Culture;

CIDS, OAS;

Social Development;

Cooperation

cidrp02034s01

cidrp02006e01