PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CP/CSH/INF.36/05

7 February 2005	COMMITTEE HEMISPHERIC SECURITY	Original: English

PRESENTATIONS ON MINE ACTION IN THE AMERICAS:

REPORT BY THE OAS MINE ACTION PROGRAM

REPORT OF THE

ORGANIZATION OF AMERICAN STATES MINE ACTION PROGRAM (AICMA)

TO THE

COMMITTEE ON HEMISPHERIC SECURITY

FEBRUARY 2005

REPORT BY THE OAS MINE ACTION PROGRAM

(Delivered by Mr. William McDonough, Coordinator of the OAS Mine Action Program)

General. The Organization of American States (OAS) Mine Action Program, known formally as “Comprehensive Action against Antipersonnel Mines” (or AICMA by its Spanish acronym), has undergone significant growth since its initiation more than twelve years ago. Originally conceived as an assistance program for mine clearance in Central America, the AICMA Program currently supports a wide range of mine action activities in six Member States, including:

- Support for humanitarian demining activities, including survey, mapping, marking, and clearance;

- Mine risk education for people living in affected areas;

- Victim assistance, including physical and psychological rehabilitation and the socioeconomic reintegration of cleared zones;

- Supervision and assistance for the destruction of stockpiled mines;

- Development of mine action databases; and

- Support for a total ban on use, production, stockpile, sale, or transfer of antipersonnel mines.

Mandates.  The Program functions under a series of General Assembly mandates.  The most recent of these include:

- AG/RES. 1995 (XXXIVI-O/04) “Support for the Program of Integral Action Against Antipersonnel Mines in Central America,”

- AG/RES. 2002 (XXXIVI-O/04) “Support for Action Against Mines in Peru and Ecuador,” and

- AG/RES. 2003 (XXXIVI-O/04) “The Americas as an Antipersonnel Land Mine-Free Zone.”

Organization. AICMA currently operates within the General Secretariat under the Department of Multidimensional Security to provide overall coordination of the Program, including solicitation of financial contributions from the international community.  The Inter-American Defense Board (IADB) provides technical assistance through teams of international supervisors and monitors in the mine-affected countries.  The progress achieved by the Program is due in large measure to the support of Member States (Argentina, Bolivia, Brazil, Chile, Colombia, El Salvador, Guatemala, Honduras, Nicaragua, Peru, Venezuela, and United States), who have provided demining trainers and supervisors through the IADB. Financial contributions from major international donors (Australia, Brazil, Canada, Denmark, European Union, France, Germany, Italy, Japan, Norway, Russian Federation, South Korea, Spain, Sweden, United Kingdom and United States) have made the Program possible.

Humanitarian Demining.  From March 2004 through February 2005, the Program made significant progress in its efforts to eliminate the threat of antipersonnel mines in the Americas.  During all of 2004, with the support of AICMA, more than 12,000 mines and unexploded ordnance were destroyed and approximately one-half million square meters of land were cleared in Guatemala, Honduras, Nicaragua, Ecuador and Peru.  Military trainers and other technical experts provided by the IADB conducted training courses for national deminers from mine-affected countries benefiting from the program.  Noteworthy activities in recipient countries include:

- In Guatemala, demining activities have been completed in six departments considered to be high-risk zones, with work underway in the last remaining high-risk departments, as the Guatemalan program moves toward completion in mid 2005.

- Demining operations in Honduras concluded in June 2004, and the country was formally declared mine-safe by the Honduran Government in November 2004.  Overall, more than 2,200 mines and unexploded ordnance and some 446,000 square meters were cleared with the support of the Program.

- The Nicaraguan demining program has completed 80 per cent of the clearance of more than 135,000 mines that were originally emplaced.  Nicaragua is now projected to complete major mine clearance work by the end of 2006, with a significantly reduced effort subsequently planned until mid-2007.

- Along the Peru-Ecuador, demining operations were concluded in the Ecuadorian province of Loja in 2004.  Operations were also initiated in November 2004 in the Cordillera del Condor border region.

- In November 2004, AICMA signed an agreement with the Government of Suriname for support of a two-month demining project to complete mine clearance in the country.  Demining operations are to be accomplished with the support of a small demining unit from Honduras which will also train a team of Surinamese deminers beginning in February 2005.

# Mine-Risk Education.  The mine-risk education programs supported by the Program aim to reduce the number of accidents by promoting safe behavior among inhabitants of mine-affected communities.  The programs emphasize involvement by affected communities in mine awareness initiatives and benefit from their participation through information received about the location of mined areas and explosive devices.  Mine-risk education campaigns have been carried out through community visits, a variety of national radio messages and school programs.  Additionally, national personnel and AICMA staff have been trained to provide mine-risk education in schools and communities in affected areas.  In each of the recipient countries, these campaigns are closely coordinated with demining operations, and in the past twelve months alone, more than 20,000 people living in mine-affected areas have been contacted.

Victim Assistance.  The Program has assisted nearly 600 landmine victims since 1997.  AICMA provides victims who have no social security or military benefits with transportation from their communities to the rehabilitation center, lodging, meals, prostheses, therapy, and medications.  In collaboration with the National Technological Institute of Nicaragua, AICMA developed a vocational training and placement project for landmine victims, which has provided technical job training for 137 landmine survivors in trades including auto mechanics, computer skills, carpentry, shoemaking, tailoring, and cosmetology.  In Ecuador, the Program has provided five victims with prostheses and surgical care and has offered tuition assistance to an Ecuadorian prosthetics technician receiving training in El Salvador.

Stockpile Destruction.  The Program provided technical and financial assistance to the Government of Colombia  in meeting its obligations under the Ottawa Convention by finalizing the destruction of 22,000 mines in its stockpiles  Colombia joined Argentina, Chile, Ecuador, Honduras, Nicaragua and Peru as Member States that have become stockpile-free with the support of the Program prior to the First Review Conference of the Ottawa Convention, which was held in November 2004 in Nairobi, Kenya.   To date, more than one million stockpiled antipersonnel mines have been destroyed in coordination with AICMA, supported largely  through contributions from the Government of Canada.

Support for Antipersonnel Mine Ban.  The Program promoted the interest expressed in OAS General Assembly Resolutions to make the Americas a landmine-free zone by coordinating mine action issues and assisting the Member States with preparation for the Ottawa Convention Review Conference, which took place in November 2004 in Nairobi, Kenya.  AICMA, in conjunction with the Governments of Canada, Peru and Ecuador, sponsored a regional seminar held in Quito, Ecuador in August 2004 aimed at improving mine action cooperation within the Americas.   In previous years, similar regional meetings were held in Miami, Managua and Lima. The Program also participated in various meetings related to the Convention, including the Review Conference, in order to share practical achievements and lessons learned with other global mine action programs and strengthen contacts with international donors.

Coordination with International Entities. A notable element of the AICMA Program relates to collaborative efforts with other international and non-governmental organizations. Cooperation with international entities over the past year, has improved the efficiency and effectiveness of mine action programs throughout the Hemisphere by marshalling available resources from these organizations, particularly in the fields of preventive education and victim assistance. The Program has maintained close and productive relationships with:

- United Nations, primarily through the U.N. Mine Action Service and the U.N. Children’s Fund;

- Geneva International Center for Humanitarian Demining;

- Mine Action Information Center at James Madison University;

- World Rehabilitation Fund;

- Physicians for Human Rights; and the

- South Florida Landmine Action Group.

Resource Mobilization.  The AICMA program has employed various media to inform the international community of the achievements of its program as well as its outstanding needs.  In November 2004, the Program published the “Portfolio of Mine Action Projects, 2004-2005,” which included profiles of all the national programs of the AICMA beneficiary countries as well as the financial requirements for their implementation in 2004. Over the course of 2004, financial contributions amounted to approximately US$ 7.86 million.

Conclusions.  The AICMA Program continues its efforts to support the mine-affected Member States in addressing their landmine problems.  With the continued generous support of the international donor community, the prospects for conclusion of the program in Guatemala this year and in Nicaragua in the 2006-2007 time period will remain positive.  All of the Program’s beneficiary countries continue to sustain their national efforts, but continued international financial support is critical to the full success of the Program.

# Text boxes

CP13851E01