PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CP/CAAP/Rep. 6/06

31 October 2006

COMMITTEE ON ADMINISTRATIVE AND BUDGETARY AFFAIRS	Original: English

REPORT OF THE GENERAL SECRETARIAT

ON THE USE OF THE SPECIAL FUND FOR BUILDING IMPROVEMENTS,

MAINTENANCE SERVICES AND OTHER URGENT NEEDS (BIMS)

FOR THE PERIOD JULY 1 – SEPTEMBER 30, 2006

REPORT ON THE USE OF SPECIAL FUNDS

FOR THE UPGRADE OF OAS BUILDINGS AND FACILITIES

FOR THE PERIOD ENDING SEPTEMBER 30, 2006

In addition to the normal budget authorities in the approved Program Budgets for 2005 and 2006, the Governing Bodies have provided the General Secretariat with three additional funding authorities for the upgrade of Secretariat buildings and facilities, as well as other servicing, security and maintenance needs.  These are described below, under the three headings, along with a progress report as of September 30, 2006.

- Fund for Building Improvement, Maintenance Services, and Other Urgent Needs

In compliance with the AG/RES. 2157, (XXXV-O/05), Program-Budget of the Organization for 2006; Quotas and Contributions to FEMCIDI for 2006, III.GENERAL PROVISIONS, paragraph 4:  Fund for Building Improvement, Maintenance Services, and Other Urgent Needs.

“a.	To instruct the Secretary General to establish a special fund for the deposit of voluntary contributions to finance urgent capital improvements for the OAS buildings, repairs, and other building maintenance expenses which could not be financed under the current program-budget due to the $76,275,500 cap on that budget;

- To urge member states, permanent observers, and other donors to contribute to this voluntary fund, which shall be called the “Fund for Building Improvement, Maintenance Services, and Other Urgent Needs”;

- To authorize the Secretary General to finance from this special fund the urgently needed building capital improvements, repairs, and other maintenance expenses in an amount of up to the total amount contributed to that fund or $1.3 million, whichever is less.  Any balance in this fund not needed for building capital improvements, repairs, and maintenance may be allocated by the Permanent Council to other activities; and

- To instruct the Secretary General to report quarterly to the Permanent Council on the income and expenditures of this special fund.”

To this end, the Secretariat is pleased to provide the Governing Bodies with the following information:

Since the creation of this Fund, it has received voluntary contributions from the Commonwealth of the Bahamas and the Republic of Chile, as shown below:

The Secretariat plans to use these funds in the implementation phase of a Master Renovation Plan.  The Secretariat is in the process of soliciting competitive proposals from firms that are qualified to provide the architectural and engineering services required for an “Existing Conditions and Facilities Assessment Report” on the historic buildings located at the Constitution Avenue Complex (CAC).  This includes the Main Building, the Museum, the Casita, the Administration Building and adjacent grounds. The report will lay the basis for a Master Renovation Plan for the Complex, with emphasis on the Main Building.  It will focus on the site, the exterior envelope, structure, systems, tile safety and security, opportunities for better efficiencies and conservation of energy, and opportunities for LEED (Leadership in Energy and Environmental Design) certification, if the pursuit of this goal is appropriate and feasible.  We anticipate that the study will take place in February 2007 and will be completed by March.  It should provide the Secretariat and Member States with a road map for the upkeep of the historic buildings, prioritize what needs to be done and provide estimated costs.

- Special 2006 Appropriation

  - Background

On March 27, 2006, the Committee on Administrative and Budgetary Affairs (CAAP) “agreed to approve a US$5.2 million appropriation adjustment to the Program-Budget of the Regular Fund for 2006, financed through the Reserve Subfund of the Regular Fund.”

As part of this appropriation adjustment (CP/CAAP/SA-538/06), the Office of General Services within the Secretariat for Administration and Finance was authorized additional funding in the amount of $972,100 to cover recurring costs, as well as to undertake capital investment projects, as follows:

| Recurring Costs |  |
| --- | --- |
| Building maintenance ($121,200 for the CAC and $35,300 for the GSB) | $156,500 |
| One Administrative Building specialist | 92,600 |
| Ten general services personnel (guards, movers, messengers, etc.) | 328,200 |
| Building insurance cost increase | 34,500 |
| Vehicle maintenance cost increase (to cover gasoline, maintenance, & vehicle leases) | 23,000 |
| Total Recurring Costs | $634,800 |
| Capital Investment Projects |  |
| Existing Condition Assessment of Constitution Avenue Complex (CAC) | 75,000.00 |
| Replace chiller in the Main Building | 120,000.00 |
| Repair roof directly above Guerrero Room | 29,300.00 |
| Repair leaks at staircases (Hall of the Americas) | 49,000.00 |
| Repair and paint plaster of Main Building (First and Second Floors) | 64,000.00 |
| Total Capital Investment Projects | $337,300 |
| Grand Total | $972,100 |

  - Recurring Costs Implementation Status

In all cases, the Secretariat is following procurement procedures, in compliance with GS/OAS Standards.

  - Building Maintenance

The purpose of this project was to provide $156,500 in additional funds to cover basic maintenance for both the Constitution Avenue Complex and the General Services (GSB) building.  The original Regular Fund Budget amounts were $1,333,700 and $1,322,400, respectively. The $156,500 was used to cover inflationary and other increases in maintenance contracts, repairs, and supplies.

  - Administrative Building Specialist

This additional amount ($92,600) has been used to finance a short-term contract to support all of the administrative support activities related with the tenants in the GSB building.  The Secretariat currently has the following tenants: IICA and PAHO on the third floor; Albert Sabine Institute, PADF, and the Development Gateway Foundation on the second floor; and the OAS Staff Federal Credit Union and Juan Valdez Coffee Shop at the lobby level.

  - General Services Personnel

In order to reinforce security, cleaning, and general services, and to rehire ten (10) of the 26 general services institutional contract (IBS) personnel cut in 2005 due to budgetary constraints, the Secretariat was authorized $328,200.  The Secretariat has been able to reinforce all of the above-mentioned areas.  However, considering that the hiring process did not start until May 2006, the Secretariat was able to save $117,690 under this line item in 2006.  This saving is being applied to the MNB chiller (see C.2 below).

  - Building Insurance

The original Regular Fund Budget for 2006 authorized the Secretariat a total of $315,500.  This was insufficient and the Secretariat was authorized an additional $34,500, for a total of $350,000.  As of October 2006, the Secretariat expended $308,034 and there is an open obligation of $6,300.  The Secretariat estimates that an additional $12,000 will be required, leaving an estimated positive balance of $23,666.

  - Vehicle Maintenance

The original Regular Fund Budget for 2006 authorized the Secretariat a total of $27,000 for this line item. Considering the much higher operational costs experienced in 2005 due to an aging vehicle fleet, this amount was insufficient and the Secretariat was authorized an additional $23,000 from this additional budget authority to cover the needs of the fleet, for a total budget of $50,000.  The Secretariat already has spent $39,406.

  - Capital Investment Projects

    - Existing Condition and Facilities Assessment Report of Constitution Avenue Complex

The Secretariat is in the process of soliciting competitive proposals from firms that are qualified to provide the architectural and engineering professional services required for an “Existing Conditions and Facilities Assessment Report” on the buildings located near Constitution Avenue (CAC).  The report will focus on the site, the exterior envelope, structure, systems, tile safety and security, opportunities for better efficiencies and conservation of energy, and opportunities for LEED (Leadership in Energy and Environmental Design) certification if the pursuit of this goal is appropriate and feasible (see I. above).  The Secretariat was authorized $75,000 to obtain this report.  As soon as the bidding process is completed, the amount required to purchase this service will be obligated.

2.	Replace Chiller at the Main Building (MNB)

The Secretariat is in the process of soliciting competitive proposals from firms that are qualified to provide the equipment and installation of a chiller in the MNB.  Currently, there are two chillers at the MNB and, originally, the Secretariat planned to replace one in 2006 and the other in 2007. The Secretariat believes, however, that substituting the two for a new, more powerful chiller, will be more effective and efficient to cover the air conditioning requirements of the MNB.  The cost of the new chiller is estimated at $200,000.  The $80,000 negative balance between the estimated cost and the amount authorized this year ($120,000) will be financed from savings realized in the general services personnel, item B.3, above.

- Repair Roof Above the Guerrero Room

The main purpose of this project was to repair and grout the rooftop wall, as well as associated joints, which is the caused of interior leaks to the Dr. José Guerrero room.

The Secretariat received three proposals and the contract was awarded to the lowest bidder, American Architectural Restoration, for $24,750 (see Annex 1, line 6).  The work was completed on August 20, 2006 leaving a positive balance of $4,550.

4.	Repair Leaks at Staircases (Hall of the Americas)

The purpose of this project was to repair and seal the rear stair landings (leading to the Hall of the Americas).  The tasks included landings, steps, and joints that have failed in the sidewalls areas.  The company removed the existing rubberized joints, cleaned the stone and reapplied a cement grout, as originally designed for this building.  This will avoid water leaks in the offices underneath the stairs and in the Simon Bolivar Conference Room.

The Secretariat received three proposals and the contract was awarded to the lowest bidder, American Architectural Restoration, Inc., for $6,750.  The work was completed on October 12th, 2006 leaving a positive balance of $42,250.

5. 	Repair and Paint Plaster in the Main Building (MNB - First and Second Floors)

The purpose of this project is to repair and paint the walls in the halls and ceilings of the Main Building in two phases.  The first phase will be to paint the second floor and then, before the end of the year, paint the first floor.

The Secretariat received three proposals and the contract for the first phase was awarded to Abel Contractors, Inc. for $18,300.

The first phase work will commence the second week of November 2006.  The second phase, which is estimated to cost $26,800, will start the second week of December.

  - Financial Status as of October 20th, 2006

These projects have an approved budget of $972,100 and the total execution to date amounts to $868,710, leaving a balance of $103,390.  The Secretariat estimates that all funds will be obligated by December 31, 2006

- Appropriation from CP/RES. 831

A.	Background

On September 23rd, 2005, the Committee on Administrative and Budgetary Affairs (CAAP) authorized the Secretariat the use of $624,000 from the Capital Building Fund (CP/RES.831) to undertake structural and equipment improvements in the OAS buildings (CP/CAAP/SA-525/05).  The funds were to be invested and distributed as follows:

- General Secretariat Building

a.	Cooling Tower				$239,000

b.	Safety/Security Window Film		$100,000

c.	Garage Structure			$  24,000

- Main Building - Elevator				$200,000

- Museum - Condenser				$  16,000

4.	Voice Mail 					$  45,000

Total		$624,000

- Implementation Status

The Secretariat already completed the installation of the Safety/Security Window Film, repaired the Garage Structure in the General Secretariat Building (GSB) and installed a condenser unit in the Museum.

The projects that are in progress are the installation of the cooling tower in the General Secretariat Building (GSB), which will start by the middle of November 2006; and the installation of the elevator will start by the middle of December 2006.  With regard to the Voice Mail System, the Secretariat is studying the possibility of integrating the voice mail system with other converging technologies, such Internet Telephony (IP) for more integral solution.  See the Secretariat’s Report, CP/CAAP/INF. 1/06 of September 21, 2006, for more details.

# Text boxes

CP17049E01