FIFTH REGULAR MEETING OF THE		OEA/Ser.W/XIII.6.5

INTER-AMERICAN COMMITTEE ON EDUCATION	CIDI/CIE/doc.5/10

November 9-10, 2010	 November 4, 2010

Guayaquil, Ecuador						                          Original: Spanish

DRAFT OF THE CIE WORK PLAN 2010 – 2012

MATRIX

DRAFT OF THE CIE WORK PLAN 2010-2012

| Project | Status | Resource Level | Responsible Entities | Next Steps |
| --- | --- | --- | --- | --- |
| I. EARLY CHILDHOOD DEVELOPMENT, CARE AND EDUCATION |
| I. ACTIVITY 1.1 Follow up to the “Hemispheric Commitment to Early Childhood Education" adopted by the Ministers of Education in 2007 and ratified in 2009. | Special Joint Session of the OAS Permanent Council and CEPCIDI to give political visibility to the highest levels of the OAS, held 02/24/10. First draft of the "Inter-American Program on Comprehensive Early Childhood Care and Education." | Travel expenses for Special Session participants: neuroscientist, economist, Minister of Education. (SEDI/OEC) | Member States and the Technical Secretariat. | Following the Special Session, 34 Member States were asked for feedback on the “Inter-American Program on Comprehensive Early Childhood Care and Education.” Share the Special Session recorded on the OAS website. Approve in the CIE and continue with the Inter-American Program resolution process. |
| I. ACTIVITY 1.2 Project: "Policies and Strategies for a Successful Transition of the Child to Socialization and School". | Two Inter-American symposia completed: a) Understanding State of the Art Care in Early Childhood (Children Ages 0 – 3); b) Transitions. 2 CDs: one book on transitions in two languages. The CDs and both Symposia have been completed. | About to finish CIE funds, US$181,600; UNICEF and others. Search for new funding. | OAS Technical Secretariat, Ministry of Education, Chile-JUNJI (follow-up symposium). | a) Distribute CD, Report and book to Member States, international organizations, and civil society. b) Support Member States in taking actions related to transitions and improving the quality of comprehensive care services. c) Finding resources to support Member States and civil society: training quality improvement, development of guides and materials. |
| I. ACTIVITY 1.3 Expansion of the Hemispheric Commitment to Early Childhood through technology and communication networks. | The “Early Childhood Communications Strategy” is completed; Awareness and Communications Workshops for journalists, educators, University staff, and parents in Argentina, Colombia, Peru, Trinidad and Tobago, and Suriname. Production of guiding documents (awareness and social communication). Creation of Early Childhood Portal in progress. | Funds provided by CIDA-Canada US$161,925 | OAS Technical Secretariat and consultants, in addition to the OAS-van Leer project. | Dissemination of Communications Strategy, and dissemination and advocacy materials on early childhood. Launch the Early Childhood Portal at the V Regular Meeting of the CIE. Socialization of guides and promotional materials. |
| I. ACTIVITY 1.4 "Trends in Transition Policies in Rural, Indigenous and Border Communities" Project (OAS/van Leer project) | Development of case studies (in process): Brazil, Guatemala, Mexico, Bolivia. Development of political, advocacy, and social communication actions in Colombia, Chile, Peru, and Venezuela. | Still pending contribution from Bernard van Leer Foundation $265,000 Euros; Financial support from JUNJI/Chile, UNICEF, OEI Guatemala; US$ 500,000 from the government of the People's Republic of China; CIE/OAS-OEC. | OAS Technical Secretariat, CINDE Colombia, Catholic University of Peru, CECODAP Venezuela, Ministry of Education of Brazil, JUNJI/Chile; UNICEF Bolivia; OEI Guatemala; Indigenous Peoples Foundation of Mexico. | Evaluation of the first phase of the OAS/van Leer project and preparation of the second phase in November 2010. Communications Workshops and delivery of the Colombia and Peru project outputs, November 2010. Dissemination of the two studies in English and Spanish; Multimedia CD and methodology documents, and project results. |
| I. ACTIVITY 1.5 International Symposium and workshop for design innovations, “Comprehensive Attention to Children between the Ages of Zero and Three in Amazonian and Indigenous Communities." | Second OAS/van Leer phase, International Symposium and Workshop in Iquitos, Peru, November 13-16, 2010. Countries with Amazonian populations, as well as those with large percentages of indigenous populations will participate. | Bernard van Leer Foundation contribution of 60,000 Euros in progress; complement from CIE. | Member States; Technical Secretariat; Bernard van Leer Foundation; UNICEF; Save the Children; Ministries of Education, Health, Women and Social Development; and associated international universities, institutions and organizations. | Follow-up on Symposium agreements; Convene the next meeting in Brazil to discuss the experience’s achievements and challenges in 2011. Extend invitation to UNICEF, World Bank, IDB, OEI, and UNESCO to join. |
| I. ACTIVITY 1.6 Second World Conference on Early Childhood Education for Peace, held in Morelia, Mexico. Launching of the Chair on early childhood education for peace, in March 2010. OAS/AMEI | Agenda and logistics for the May 2011 event are in progress. | AMEI U$100,000; OAS-OEC contribution in kind. | AMEI, OAS-OEC | Preparation of the Technical Secretariat logistical; invitations to governmental and international organizations. Provide technical support to the Chair. |
| I. ACTIVITY 1.7 Tenth International Meeting on Early Childhood and Pre-school Education. "Universalization of Early Childhood Care: The Challenge of the 21st Century." Monterrey, Mexico, October 2010, and Preparation of the Third World Congress and Eleventh International Congress in September 2011. | Drafting of agenda on the theme of “Parent and Community Education with Equity and Sustainability.” Coordination between OAS/Government of Nuevo Leon/CENDI, invitations to international organizations, governments and conference participants. | State of Nuevo Leon: U$100,000; Others: U$50,000 | Mexico/Government and Education Secretariat of Nuevo Leon, CENDI Monterrey, Technical Secretariat OEC/OAS | Socialization of the findings of the X Meeting through the Internet and Early Childhood Portal. Support in the organization, execution and assessment of the Third World Congress to be held in September 2011. Preparation of Technical Secretariat logistical documents, and coordination of live transmission. |
| I. ACTIVITY 1.8 Project: Educational Evaluations Focused on Quality: follow-up to the Hemispheric Commitment to Early Childhood. | Follow-up to the sub-regional conferences in: a) Central America, June 2009; b) MERCOSUR and associated countries, December 2009; c) Andean Countries, Colombia, May 2009; and d) EDI Canada Conference, June 2010. Hold a sub-regional evaluation meeting in the Caribbean (Guyana, January 2011), and a hemispheric evaluation meeting in Paraguay, May 2011. | Education subfund (CP/RES 831) $185,000, and the following approximate contributions: UNICEF $200,000; IDB $25,000; governments of Costa Rica, Paraguay, Colombia and Guyana (CARICOM) $100,000. | Ministries of Education of Costa Rica; Paraguay; Colombia; and Guyana. Technical Secretariat and associated international organizations: UNICEF, UNESCO, IDB, OEI, and others. | a) Preparation of Meetings in collaboration with UNICEF and CARICOM in the Caribbean, and Hemispheric Meeting in Paraguay, and Follow-Up Meeting in Costa Rica. Coordinate with UNICEF, IDB, OEI, UNESCO, and the World Bank. b) Dissemination of the agreements and conclusions adopted at OEI-hosted events at the Ibero-American level, and UNESCO events at the international level in Moscow, Russia in September 2010, which outlined the progress on early childhood issues in the Hemisphere. c) Support Member States’ evaluation initiatives. d) Prepare a book on the Hemisphere’s evaluation initiatives. |
| I. ACTIVITY 1.9 Support the consolidation of early childhood education in the Caribbean through technical cooperation with Chile. Memorandum of Understanding between the OAS and the government of Chile. | The conference in Port of Spain was held in January 2010. Thirteen countries, CARICOM, UNICEF and JUNJI, Chile, took part. | Memorandum of Chile-OAS Understanding $100,801 | Ministry of Education of Trinidad and Tobago, JUNJI/Chile, CARICOM and UNICEF, Caribbean. | Dissemination of the final Evaluation Report through the OEC/OAS website, and consultation on new funding. |
| I. ACTIVITY 1.10 International symposium: “Early Childhood and the Challenges of Basic Education in the 21st Century" (Puebla - Mexico, January 2010). | A conference was held January 26-29, 2010. The outcomes will be published in van Leer/OAS CD and the OAS website. | Donation by the People's Republic of China US$ 50,000; and contribution from the van Leer Foundation. | Government of Puebla, Education Secretariat of Puebla and Mexico, and Foundation of Indigenous Peoples. OAS Technical Secretariat. | Dissemination of report at the Meeting of Education Secretariats from Mexico, and unto the Teacher’s Union of Mexico. In Puebla, Mexico, November 2010, implementation of workshops with bilingual teachers to prepare educational materials based on the Symposium’s conclusions. Upon completion of the project in December 2010, new funding will be requested. |
| I. ACTIVITY 1.11 NEW ACTIVITY: Meeting of Early Childhood and Corporate Social Responsibility, in Argentina 2010, and Peru 2011. | Entrepreneurs from Cali, Colombia, and Argentine Dialogue to carry out the meeting: Early Childhood and Corporate Social Responsibility, on September 1 – 3, 2010. | Contributions from entrepreneurs form Colombia and Argentina: US$ 20,000; and from the OAS Technical Secretariat: US$ 5,000. | Ministry of Education of Columbia; entrepreneurs from Cali, Colombia and Educational Consultant Dialogues in Argentina; Cerebrum from Peru; UNICEF; and Save the Children. | a) Dissemination of final report on the OAS website and entrepreneur involvement in OAS and CIE political and technical meetings. b) Support the organization, execution and evaluation of the following even in Lima, Peru in September 2011. |
| I. ACTIVITY 1.12 Online course for professionals: Introduction to Working with Children between the Ages of Zero and Three. | In October 2010, tutor training and the development of the first group of 55 participants began. | Technical Secretariat; NPA Program; and SEDI CapaciNet. | OAS and Member States wishing to participate. | Coordination with UNICEF, OEI and the van Leer Foundation to broaden participation. |

| II. EDUCATION FOR DEMOCRATIC VALUES AND P RACTICES |
| --- |
| ACTIVITY 1. Professional Development and Educational Resources |
| II. ACTIVITY 1.1 Consolidation of the three online courses’ contents and transfer of these courses to the Educational Portal of the Americas | In process: Update the following online courses based on evaluation results and transfer courses to the platform of the Portal of the Americas: 1- Hemispheric Course Evaluation of Policies and Programs in Education for Democratic Citizenship; 2- Hemispheric Course for Teachers: The Inter-American Democratic Charter and the Teaching of Democratic Values and Practices; 3- Education for Democratic Citizenship in the Caribbean: An Online Course for Educators. | Secured: 30,000 (U.S. Permanent Mission remnant funds) | CIE, Technical Secretariat, Educational Portal of the Americas (EPA) | Adapt contents to the methodology used by the EPA and transfer courses. Finalize video on the course in the Caribbean and upload onto website. |
| II. ACTIVITY 1.2 Sustainability of online courses | Design a cost plan for the sustainability of the courses, including payments for tutors, and scholarships for educators and government officials that cannot afford the fee. | Secured: 30,000 (U.S. Permanent Mission) | CIE, Technical Secretariat | Hire consultant to design cost plan. |
| II. ACTIVITY 1.3 “Education for Democratic Citizenship in the Caribbean: A Distance Course for Educators” – Sustainability Strategy | - Develop and implement initiatives and tools for the project to inform Caribbean stakeholders and promote the project results, and to further inform policy in the area of democratic citizenship education. -Re-offer the course to wider audiences, offering partial scholarships. -Continue to work with partner institutions to incorporate education for democratic citizenship into the required courses of study for pre-service and in-service teachers. | Finished Project: US$ 360,000 (CIDA) Required: 96,300 Secured: 38,800 | Member States, “stakeholders,” UWI, CIE/Technical Secretariat. | Publish evaluation (January 2011). Implement activities. |
| II. ACTIVITY 1.4 Publish workshop's proceedings for the Inter-American workshop “The Role of the Arts and Communications Media in Promoting Democratic Values and Practices Among Children and Youth.” | The workshop was carried out in June 17 – 19, 2010 in the Dominican Republic. The previous online forum is still available. | Workshop $ 85,000 (CIE Res. 831, CIC Res. 831, OAS Grants, FEMCIDI, Government of the People’s Republic of China, FUNGLODE, Culture Sec. RR.DD.). Secured for publishing and follow-up: 9,000 (U.S. Permanent Mission) | Technical Secretariat | Publish workshop’s proceedings |
| II. ACTIVITY 1.5 Produce and publish a portfolio of good practices for the Inter-American workshop “The Role of the Arts and Communications Media in Promoting Democratic Values and Practices among Children and Youth.” | The workshop was carried out in June 17 – 19, 2010 in the Dominican Republic. | Secured: 24,000 (U.S. Permanent Mission) | CIE/CIC/Technical Secretariat | Issue call for proposals for good practices the role of the arts and communications media in promoting democratic values and practices among children and youth. |
| II. ACTIVITY 1.6. Launch a special edition of the Inter-American Journal of Education for Democracy on the topic “The role of the arts and communications media in promoting democratic values and practices among children and youth.” | An online bulletin was produced on this topic in 2009. It could serve as basis for the Special Edition of the Inter-American Journal of Education for Democracy. | Secured: 11,600 (U.S. Permanent Mission) | CIE/CIC/Technical Secretariat | Design and issue call for proposals for this special edition. |
| II. ACTIVITY 1.7. Call for a new round of proposals for the Horizontal Cooperation Fund in a joint effort between the Inter-American Commission of Culture and the Inter-American Commission of Education on the topic “The Role of the Arts and Communications Media in Promoting Democratic Values and Practices among Children and Youth.” | Proposal to follow-up on the Workshops of June 2010 on the same topic. | Required: 135,000 Secured: 15,000 (U.S. Permanent Mission) | CIE/CIC/Technical Secretariat | Design and issue call for new round of proposals for Horizontal Cooperation Fund on this specific topic. |
| II. ACTIVITY 1.8. Jointly develop, with SREDECC, a Regional Forum on Citizenship Competencies” | The Regional Forum was successfully carried out. Two OAS Member States (Ecuador and Costa Rica) joined SREDECC. Four countries of the Caribbean participated at the Forum (Bahamas, Guyana, Saint Vincent and the Grenadines and Suriname). | Secured: 24,000 (U.S. Permanent Mission remnant funds) | CIE/Technical Secretariat/SREDECC | Disseminate SREDECC findings and forum’s proceedings, work with participating countries for support in the next phase, integrate results with the Inter-American Program (in its activities such as the Magazine, Bulletin, etc.). |
| ACTIVITY 2. Information Exchange and Multilateral Cooperation |
| II. ACTIVITY 2.1 Call for a New Round of Proposals/Projects under the Horizontal Cooperation Fund for Technical Assistance Missions on Education for Democracy and Related Areas. | A first round of proposals under the Horizontal Cooperation Fund for Technical Assistance Missions was successfully carried out in 2009-2010. A final report containing feedback from participants one year after the technical missions took place will be available in March 2011. | Required: 140,000 Secured: 140,000 (U.S. Permanent Mission new and remnant funds) | CIE/Technical Secretariat | Produce final report on first round of proposals and issue call for second round of proposals in 2011. |
| II. ACTIVITY 2.2 Update content from the Inter-American Program Web Portal. | The Inter-American Program Web Portal is accessible at www.educadem.oas.org | Secured: 7,500 (U.S. Permanent Mission) | CIE/Technical Secretariat | Update content and upload it to web portal. |
| II. ACTIVITY 2.3 Develop new information for the Inter-American Program Web Portal www.educadem.oas.org | A new online bulletin on Financial and Economic Education for Democratic Citizenship will be launched in December 2010. | Required: 32,000 Secured: 16,000 (U.S. Permanent Mission) | CIE/Technical Secretariat | Publish new online bulletin, define topics for next online bulletins and policy briefs. |
| II. ACTIVITY 2.4 Develop a Youth Strategy and Plan of Action (with budget) for the Inter-American Program on Education for Democratic Values and Practices. | Through the Inter-American Program, the Office of Education and Culture is collaborating in a multi-sectorial project involving and targeting youth called “Building a Culture of Peace with Youth in Central America through Arts, Media and Social Dialogue” (i.e. Armando Paz). A more comprehensive strategy on how to incorporate youth to the Inter-American Program is required. | Secured: 18,000 (U.S. Permanent Mission) | CIE/Technical Secretariat | Hire consultant to draft strategy on youth. |
| II. ACTIVITY 2.5. Develop a Communications Strategy with input from stakeholders for the Inter-American Program to expand its visibility and usefulness to Member States | New initiative | Required: 41,300 Secured: 34,300 (U.S. Permanent Mission) | CIE/Technical Secretariat | Develop communications strategy. |
| ACTIVITY 3. Research and Dissemination |
| II. ACTIVITY 3.1 Publish four new editions of the trilingual, peer-reviewed, online Inter-American Journal of Education for Democracy. | To date the Inter-American Journal on Education for Democracy has published 5 editions. Edition number 6 will be published in December 2010. | Required: 52,400 Secured: 29,200 (U.S. Permanent Mission new and remnant funds) | Indiana University/Universidad Nacional Autónoma de México (UNAM)/Technical Secretariat | Publish the sixth edition and transfer editorship from Indiana University (that will remain as a strategic partner) to UNAM in Mexico. |
| II. ACTIVITY 3.2 Compile and publish Portfolio of promising policies and programs. | A first edition of this portfolio was published in 2006. The new revised edition could build on the Good Practices studies on Education for Democracy Programs from the Regional System for the Evaluation and Development of Citizenship Competencies (SREDECC). | Required: 34,000 Secured: 30,000 (U.S. Permanent Mission) | CIE/Technical Secretariat | Coordinate the elaboration of new Portfolio. |
| II. ACTIVITY 3.3 Develop 4 case studies within the framework of the “Education of migrant children and youth” project. | A mapping of existing policies and program on education of migrant children and youth in the Americas has been published. Onsite research in two (Argentina and Costa Rica) of the four case study countries has been carried out. | Secured: 70,000 (CIDA) | CIE/Technical Secretariat | Carry out onsite research in Antigua and Barbuda and the United States (Pennsylvania). Draft and publish case studies. |
| II. ACTIVITY 3.4 Publish and disseminate a policy recommendation report to expand, analyze and disseminate results of research on the education of migrant children and youth. | To be published in 2011 | Secured: 10,000 (CIDA) | CIE/Technical Secretariat | Draft and disseminate report. |
| II. ACTIVITY 3.5 Organize an international seminar on policies and programs for the education of migrant children and youth. | To be organized in 2011 | Required: 73,200 Secured: 37,910 (CIDA) | CIE/Technical Secretariat | Secure outstanding needed funding to organize and carry out international seminar. |
| CROSSCUTTING ACTIVITIES |
| II. ACTIVITY (i) Project “Building a Culture of Peace with Youth in Central America through Arts, Media and Social Dialogue” – Armando Paz | A first round of “Armando Paz” Youth Forums was carried out in El Salvador, Guatemala, Panama and Nicaragua. | Secured 2010: U$202,914 (USAID) Total Secured for 2009-2012: U$526,651 (USAID) | Executive Secretariat for Integral Development/Secretariat of Multidimensional Security/Trust of the Americas | Launch “Peace Challenge” Regional Competition and organize and carry out regional forum in 2011. |
| II. ACTIVITY (ii) Convene Ignite the Americas 2010 to strengthen a network of young leaders in arts and culture programs for positive social change, emphasizing the participation of youth from vulnerable groups or with experience in programs aimed at those groups. | Se-liga Américas 2010 will take place within the framework of the V Inter-American Meeting of Ministers and High Authorities of Culture to be held in Rio de Janeiro, Brazil, from December 1 to December 3, 2010. | Already identified | Ministry of Culture of Brazil | Establish a calendar of preparatory activities and work jointly with the Ministry of Culture of Brazil. |
| III. QUALITY AND EQUITY |
| III. ACTIVITY 1.1 Regional Project on Education Indicators (PRIE) - I, II, III, IV Meeting of Ministers & V Summit of the Americas | Activities carried out in 2009: 1. VII Regional Workshop on Educational Statistics, Cancun, Mexico, December 2009. 2. 5 Missions carried out in June 2009 (St. Vincent and the Grenadines); August 2009 (Suriname); October 2009 (Belize and Grenada); November 2009 (Venezuela) 2010 1. Adoption of the draft of the Educational Panorama 2010 with updated comparable indicators submitted as a draft to the Ministries in September 2010 2. Meeting of the Executive Committee in Washington, DC to report on the project’s progress and discuss its continuity. | Phase III, CIE $62,400 Remnant of Phase II $50,048 SEP $300,821 | Mexico SEP/ UNESCO-ORELAC/ / OAS -OEC | Receive feedback from countries / Ministries regarding data on the Educational Panorama 2010. Determine the transferability of the project to Colombia for a possible next phase. |
| IV. STRENGTHENING TEACHER EDUCATION |
| IV. ACTIVITY 1.1 Online courses for teacher educators to help teachers incorporate information and communications technology in their teaching practice. | The courses were offered twice in 2009. A total of 238 teacher educators from Antigua and Barbuda, the Bahamas, Belize, Jamaica, St. Kitts and Nevis, St. Lucia, St. Vincent and the Grenadines, Suriname, Trinidad and Tobago, Uruguay, Argentina, Chile, Colombia and the Dominican Republican participated. The first cycle of the courses was evaluated. In 2010 course for tutors as well as a new edition of the course was held, both in Spanish. | 2009/ CIE: 20,000.00 2010/Evolution Foundation - iEARN =55,200 OAS Grants= 30,000.00 seeking matching funds from participating countries | CIE/Technical Secretariat, and Portal of the Americas | The same courses will be offered on the Portal of the Americas throughout 2011. |
| IV. ACTIVITY 1.2 Establishment of the Inter-American Teacher Educator Network and development of a website dedicated to initial teacher education in the region. | Surveys were conducted on the participants in online courses and future teachers; the results were compiled and analyzed in order to produce the document that describes what the network will be and its content. A communications strategy was developed which describes the plan of action to be implemented within the communications sector. From this study the following actions were taken in 2010: 1. In collaboration with DOITS the OAS was selected and a platform for the Inter-American Teacher Education Network was created. 2. In collaboration with the OAS institutional image, the ITEN-RIED website was designed and created. 3. ECLAC Negotiations and the Institute of Higher Education for Latin America and the Caribbean (UNESCO/IESALC) for the planning of a teacher education institution map in the Americas, and an observatory on the use of new technologies in initial teacher training. | CIDA 2010 100.000 | CIE/Technical Secretariat | RIED-ITEN diffusion and dissemination Search for strategic alliances for the continuation of the network. |
| V. ADULT LITERACY AND EDUCATION |
| V. ACTIVITY 1 World Conference: "From Literacy to Life-Long Learning: Challenges to Literacy and Adult Education toward CONFINTEA VI," and CONFINTEA VI (World Conference on Adult Education), December 2009, Brazil. | Study on policies and programs in the Caribbean completed, submitted at the pre-conference in Mexico, and to CONFINTEA in Brazil. Participants from countries in the region supported by DHD/OAS grants. | CIE Funds: cover consultant expenses, translations, travel expenses for 2 persons. OAS Grants $25,000 plus matching funds from UNESCO. | UNESCO, Mexico, Brazil and OAS Technical Secretariat. | Disseminate results of CONFINTEA VI. Disseminate study on the Caribbean. |
| VI. SECONDARY EDUCATION (TO BE DICUSSED AT THE V REGULAR MEETING OF THE CIE) **THE GUIDELINES ARE THOSE SGGESTED AT THE X MEETING OF CIE AUTHORITIES** |
| GUIDELINE 1. Strengthening horizontal cooperation and technical assistance processes |
| GUIDELINE 2. Promotion, monitoring and evaluation of equity policies and innovative strategies and experiences to ensure that young people remain in school and complete secondary education |
| a) Activities associated with the Regional Project of Education Indicators (PRIE) |
| GUIDELINE 3. Strengthening the education and professional development of teachers for quality instruction committed to innovation and educational change |
| a) Activities associated to the Inter-American Teacher Education Network |
| GUIDELINE 4. Study, evaluate and disseminate strategies for financing and mobilizing resources for the expansion and strengthening of a quality secondary education for all the youth in the hemisphere based on quality, equity and efficiency |
| GUIDELINE 5. Strengthening strategies, mechanisms and entities to promote the active participation of young people in schools and in their communities |
| a) Activities associated with the Inter-American Program on Education for Democratic Values and Practices |
| GUIDELINE 6. Use of information and communications technology to foster access to quality educational, social and cultural content in support of secondary education reform and modernization |
| GUIDELINE 7. Environment, energy and health: An integral vision of education |
| a) Education – Health Partnership: Work with the Pan American Health Organization on developing information Systems that incorporate data on youth in the education and health sectors. For example, conduct surveys to determine risks and prevention factors, and work jointly on the prevention of school violence. Also join forces in the selection of best practices in the area of integrated sexual education. The following activities are proposals by PAHO. |
| VI. ACTIVITY 7.1 Analyze data from the world survey on risk and protection factors. Submission of notebook with information at the CIE meeting in October 2010. | Underway | PAHO US$25,000 | PAHO |  |
| VI. ACTIVITY 7.2 Key interventions Health - Education: Hemispheric Competition: Sample programs that counteract risk factors. |  |  | PAHO |  |

# CIDI03059E01