OEA/Ser.G

CP/doc.4815/13

11 January 2013

Original: Spanish

DRAFT SCHEDULE OF MEETINGS FOR

STAGES III AND IV OF THE WORK PLAN FOR

IMPLEMENTATION OF RESOLUTION AG/RES. 2761 (XLII-O/12),

“FOLLOW-UP ON THE RECOMMENDATIONS CONTAINED IN THE REPORT OF THE SPECIAL WORKING GROUP TO REFLECT ON THE WORKINGS OF THE INTER-AMERICAN COMMISSION ON HUMAN RIGHTS WITH A VIEW TO STRENGTHENING THE INTER-AMERICAN HUMAN RIGHTS SYSTEM”

(Presented by the Chair of the Permanent Council on January 16, 2013)

Draft Schedule of Meetings for

Stages III and IV of the Work Plan for

Implementation of Resolution AG/RES. 2761 (XLII-O/12),

“Follow-up on the Recommendations Contained in the Report of the Special Working Group to Reflect on the Workings of the Inter-American Commission on Human Rights with a View to Strengthening the Inter-American Human Rights System”

(Presented by the Chair of the Permanent Council on January 16, 2013)

Introduction

On June 5, 2012, the General Assembly, held in Cochabamba Bolivia, adopted resolution AG/RES. 2761 (XLII-O/12), “Follow-up on the Recommendations Contained in the Report of the Special Working Group to Reflect on the Workings of the Inter-American Commission with a View to Strengthening the Inter-American Human Rights System,” in which it welcomed the report of the Special Working Group (document AG/doc.5310/12) and instructed “the Permanent Council, on the basis of the report, to draw up proposals for its application in dialogue with all the parties involved.” In said resolution, the member states also decided that “within a period of six months or no later than the first quarter of 2013, said proposals will be presented for the consideration of a special session of the General Assembly.”

The General Assembly adopted the following definitions in relation to resolution AG/RES. 2761 (XLII-O/12):

1.	Scope of the task: the recommendations adopted by the Permanent Council and endorsed by the General Assembly itself.

2.	Objective: That the Permanent Council draw up proposals for application of the recommendations contained in the Report of the Special Working Group on the Workings of the Inter-American Commission on Human Rights with a View to Strengthening the Inter-American Human Rights System, in dialogue with all the parties involved.

3.	Time frame: six months or no later than the first quarter of 2013.

To carry out the task assigned to it, on September 10, 2012, the Permanent Council adopted a Work Plan, which includes activities divided into four stages. Stage One, the purpose of which was to take receipt of proposals from member states, the IACHR, the General Secretariat, the Inter-American Court of Human Rights, and civil society for implementing the recommendations, concluded on October 31, 2012.

Stage Two, which ran from November 1 to December 31, 2012, entailed the examination of the proposed recommendations contained in the Report of the Special Working Group. Stage Two concluded with the presentation on December 19, 2012, of a semi-official document entitled “Proposed Draft Resolution for the Special Session of the General Assembly and Appendix: Measures for Implementing the Recommendations Contained in the Report of the Special Working Group to Reflect on the Workings of the Inter-American Commission on Human Rights with a View to Strengthening the Inter-American Human Rights System”, document CP/doc.4813/12 corr. 1, submitted by the then-Chair of the Permanent Council, which could serve as a source of reference or the basis for the discussions in Stage Three. At the presentation of the above document, a number of member states considered that upon the commencement of the activities envisaged in Stage Three of the Work Plan it would be necessary to: (1) agree upon a schedule and working procedure for the tasks to be carried out; and (2) decide whether or not document CP/doc.4813/12 corr. 1 should serve as the basis of the discussions to be held.

Building on the work done in Stages One and Two of the Work Plan adopted by the Permanent Council, the objective of Stage Three, which will run from January 1 to February 28, 2013, will be to draw up a report setting out proposals–and the budgetary implications of their implementation–that will be presented to the General Assembly at a special session to be held in March 2013. It is also suggested that the format of the above report be agreed upon during Stage Three.

Stage Four of the Work Plan, scheduled for March 2013, will be the holding of the special session of the General Assembly.

The following schedule is proposed for the activities under Stages Three and Four of the Work Plan:

Schedule of Meetings for Stages Three and Four

(January 1 to March 31, 2013)

| DATE | MEETING AND TIME | TOPICS |
| --- | --- | --- |
| JANUARY |
| Wednesday, 16 | Regular meeting 10:00 a.m. | Presentation of the draft schedule of meetings |
| Friday, 18 | Informal meeting 10:00 a.m. | Draft schedule of meetings Working procedure: decide if document CP/doc.4813/12 corr. 1 should serve as the basis of the discussions agree on the format of the report and if the seven core themes should be retained How to address the proposed reforms presented by the IACHR Meeting with civil society Determination of the date of the special session of the General Assembly |
| Wednesday, 30 | Special meeting: 2:30 p.m. | Adoption of the schedule Adoption of the working procedure Discussion, summary, and agreement on the draft report and draft resolution to be submitted to the General Assembly Establishment of the date and place for holding the special session of the General Assembly |
| FEBRUARY |
| Wednesday, 13 | Special meeting: 10:00 a.m. | Discussion, summary, and agreement on the draft report to be submitted to the General Assembly (cont.) |
| Wednesday, 20 | Special meeting: 2:30 p.m. | Discussion, summary, and agreement on the draft report to be submitted to the General Assembly (cont.) |
| Wednesday, 27 | Special meeting: 10:00 a.m. | Meeting with civil society and other actors and users of the inter-American human rights system (Tentative) Discussion, summary, and agreement on the draft report to be submitted to the General Assembly (cont.) Negotiation of the draft resolution to be submitted to the General Assembly |
| MARCH |
| Wednesday, 13 | Special meeting: 10:00 a.m. | Discussion, summary, and agreement on the draft report a to be submitted to the General Assembly (cont.) Negotiation of the draft resolution to be submitted to the General Assembly (cont.) |
| Monday, 18 | Special meeting: 10:00 a.m. | Decision on the report and draft resolution to be submitted to the General Assembly |
| Friday, 22 | Special session of the General Assembly | Date to be determined |

# Text boxes

CPSC05164E04

CP29984E01